Calderdale Local Area Agreement

Draft Delivery Plan @ 2 April 2007

| Contents |  |
| --- | --- |
|  | Page |
| Themes |  |
| Economy and Enterprise | 2 |
| Environment | 22 |
| Safer and Stronger Communities | 48 |
| Healthier Communities | 96 |
| Older People | 110 |
| Children and Young People | 126 |
| Glossary | 168 |
| Further Information | 170 |

Calderdale LAA Delivery Plan

Economy and Enterprise

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Block - Economy and Enterprise |  |  |  |  |  |  |  |  |
| Outcome | Increased skill levels amongst the district workforce to access quality employment |  |  |  |  |  |  |  |
| Indicators |  |  |  |  |  |  |  |  |
| Ref | Description |  |  |  |  |  |  |  |
| EE01 | Increase nos who have Skills for Life qualifications through Calderdale College delivery supported by strengthened partnership working |  |  |  |  |  |  |  |
| Actions |  |  |  |  |  |  |  |  |
| Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |
| EE01 (1) | Target employees without S4L qualifications through Train to Gain | Calderdale College | Care Homes, Construction Industry businesses, retail | March 2007 recruit learners; August 2007 first tranche qualified 80% achievement; Contract Year 2 recruitment from August 2007 | Mar-07 | Mar 2008 target 100 learners achieved | Train to Gain contract value £400k | CEO and Head of Services to Business |
| EE01 (2) | Young adult integrated S4L vocational programmes | Calderdale College | North Halifax Partnership, Probation Service | Improve facilities North Halifax Skills Centre August 2007; continued recruitment Sept 2007 - July 2008 | Mar-07 | Jul-08 | LSC funding, Additional £50k required for centre extension | CEO and Manager North Halifax Skills Centre |
| EE01 (3) | Targeted additional learning support for adults on vocational programmes | Calderdale College | Employers | Identify and target learners on mainstream vocational programmes Sept 2007; assess train assess methods until July 2008 | Sep-07 | July 2008 780 year one target achieved by July 2008 - final results reported Dec 2008 | LSC funding including additional learning support funds | CEO and Vice Principal |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Economy and Enterprise |  |  |  |  |  |  |  |  |  |
|  | Outcome | Increased skill levels amongst the district workforce to access quality employment |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EE02 | Increase the number of adults achieving a full Level 2 qualification through direct delivery by Calderdale College supported by strengthened partnership working |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EE02 (1) | Identify and recruit employees in health and care sector | Calderdale College | Care Homes and other health sector employers | March 2007 280 employees recruited, August 2007 80% achieve | Mar-07 | Phase one Aug 2008 | Train to Gain funding contract value approx £200k for 2007/8 | CEO and Head of Services to Business |  |
|  | EE02 (2) | Improve advice and guidance including initial assessment of adult learners on entry | Calderdale College | Admissions and Guidance Staff, Employers | Planning for recruitment May - August 2007, Entry phase Sept - Oct 2007 | May-07 | Nov-07 | LSC main contract | CEO and Head of Cross College Curriculum |  |
|  | EE02 (3) | Accelerated learning programmes implemented across all curriculum areas | Calderdale College | Advanced Skills Tutors | Staff Development activity May - July 2007, Implementation Sept 2007, Monitoring Dec 2007 and March 2008 | May-07 | July 2008 620 year one target achieved, final results reported Dec 2008 | LSC mainstream contract | CEO and Assistant Principal (Standards) |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Economy and Enterprise |  |  |  |  |  |  |  |  |  |
|  | Outcome | Increased skill levels amongst the district workforce to access quality employment |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EE03 | Number of people achieving full Level 4 or above qualifications through the Leeds Metropolitan University Annex and other partners |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EE03 (1) | Engage with creative and digital industries - Target 20 | Calderdale College | Employers, Leeds met | Identify employers July 2007, Recruit learners Sept 2008 | Jul-07 | Jul-08 | Higher Education Funding Council | CEO and Head of Art and Design |  |
|  | EE03 (2) | Engage with care sector and CMBC Target 35 | Calderdale College | CMBC | Identify employers and recruit learners by Sept 2007 | Jul-07 | July 2008, at least 45 achieve Level 4 | Higher Education Funding Council | CEO and Head of Faculty Health and Care |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Economy and Enterprise |  |  |  |  |  |  |  |  |  |
|  | Outcome | Increasing employment for disadvantaged groups and workless |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EE04a (RE02) | Number of people moving into full time employment (16 hr per week or more) from incapacity benefit |  |  |  |  |  |  |  |  |
|  | EE04b | Decrease the rate of sick and disabled benefit claimants and improve employment levels |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EE04a (1) | Recruit IB adviser via JCP and write JD/spec for Occupational Health to secondee post(s) to assist Workwise in the achievement of targets ready for start of LAA in April 2007 | CMBC | JCP / PCT | New JCP secondee to replace D. Senior in post along with Occupational Health practitioner and based within Workwise | April / May 2007 | Mar-10 | £35 pa. via PAS grant + £25K P.P. funding | CMBC Workwise & Iscal Manager |  |
|  | EE04a (2) | Marketing of LAA across all partners, referrers with regular presence at JCP, GP surgeries etc. | CMBC Workwise | R to W partners | People supported in placement, job search and relevant training through Back to work initiative | Jun-07 | Mar-10 | £35 pa. via PAS grant + £25K P.P. funding | CMBC Workwise & Iscal Manager |  |
|  | EE04b (1) | Quarterly interrogation and monitoring of IB intervention across district reporting to 'Return to Work' group | JCP | Workwise, R to W partners | Year 1 target met due to inter-agency intervention | annual from April 2007 | Mar-10 | Nil | JCP Business Devt Manager |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Economy and Enterprise |  |  |  |  |  |  |  |  |  |
|  | Outcome | Increasing employment for disadvantaged groups and workless |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EE05 | Nos progressing towards full-time employment through starting permitted work with CMBC |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EE05(1) | Recruit new replacement Incapacity Benefit adviser to secondee post to assist Workwise in the achievement of targets | CMBC Workwise | CMBC | Report prepared and presented to CMBC R&D Scrutiny/visits to personnel | May-07 | Aug-07 | £35 pa. via PAS grant | CMBC Workwise & Iscal Manager |  |
|  | EE05(2) | Internal vacancies identified within CMBC and released to Incapacity Benefit adviser to enable Permitted work starts | CMBC Workwise | CMBC | First 10 clients into Permitted work across CMBC | Sep-07 | Aug-08 | £35 pa. via PAS grant | CMBC Workwise & Iscal Manager |  |
|  | EE05(3) | Continual promotion within CMBC interim report to members etc. on progress, continual achievement of targets | CMBC Workwise | CMBC | Second 10 clients into Permitted across CMBC | Sep-08 | Aug-09 | £35 pa. via PAS grant | CMBC Workwise & Iscal Manager |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Economy and Enterprise |  |  |  |  |  |  |  |  |  |
|  | Outcome | Increasing employment for disadvantaged groups and workless |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EE06 (NTG) | Reduce the proportion of those who are unemployed in the district that are resident in the four wards with the highest unemployment rates |  |  |  |  |  |  |  |  |
|  | EE06a | Ovenden, Park, Town and Illingworth and Mixenden |  |  |  |  |  |  |  |  |
|  | EE06b | Illingworth and Mixenden |  |  |  |  |  |  |  |  |
|  | EE06c | Ovenden |  |  |  |  |  |  |  |  |
|  | EE06d | Park |  |  |  |  |  |  |  |  |
|  | EE06e | Town |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EE06 (1) | To bring all local data together to establish a baseline | CMBC | Economy and Enterprise members | Audit of data completed | Apr-07 | Sep-07 | CMBC team, Partners time | JCP Business Devt Manager |  |
|  | EE06 (2) | Access to Employment providers to link data collection, and delivery methods to address narrowing the gap | CMBC | Economy and Enterprise members | Project managers meet and have agreed data collection | Jun-07 | Sep-07 | CMBC team, Partners time | JCP Business Devt Manager |  |
|  | EE06 (3) | Agree key impact measures, agree timetable and tracking processes | CMBC | Economy and Enterprise members | Impact measures in place, and tracked | Jun-07 | Mar-10 | CMBC team, Partners time | JCP Business Devt Manager |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Economy and Enterprise |  |  |  |  |  |  |  |  |  |
|  | Outcome | Increase attainment levels of young people by age 19 |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EE07a (RE03a) | The total average point score at GCE/VCE for young people aged 19 |  |  |  |  |  |  |  |  |
|  | EE07b (RE03b) | Percentage of young people gaining national level 2 qualification by age 19 |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EE07a (1) | Improve the quality of teaching and learning in sixth forms | Campus Calderdale | Campus Calderdale is a consortium of Calderdale College, Schools, Work based learning providers, Young Peoples service and Connexions partners | Establish lead departments, establish a CPD programme, establish networks, establish a QA monitoring programme. | Jan-07 | Jul-09 | Pooled budget from 13-19 strategy (LSC LIDF, Standards Fund, Connexions grant,) | Campus Calderdale Co Director |  |
|  | EE07a (2) | Improve provision and district wide offer and institutional choice through increased collaboration | Campus Calderdale | Connexions partners and Campus Calderdale collaborative | Audit of L3 provision. Commissioning new courses, joint delivery of minority courses, partially aligned timetables | Jan-07 | Jul-09 | Pooled budget from 13-19 strategy (LSC LIDF, Standards Fund, Connexions grant,) | Campus Calderdale Co Director |  |
|  | EE07b (1) | Increase provision of level two courses post 16 in sixth form and college | Campus Calderdale | Campus Calderdale is a consortium of Calderdale College, Schools, Work based learning providers, Young Peoples service and Connexions partners | Application for specialised diploma gateway, implementation of new L2 courses post 16, publication on area wide prospectus and increased results at end of course | Jan-07 | Jul-09 | Pooled budget from 13-19 strategy (LSC LIDF, Standards Fund, Connexions grant) | Campus Calderdale Co Director |  |
|  | EE07a (2) | Provide independent Information advice and guidance | Campus Calderdale | Connexions partners and Campus Calderdale collaborative | Area wide prospectus, Connexions transition plan | Jan-07 | Jul-09 | Pooled budget from 13-19 strategy (LSC LIDF, Standards Fund, Connexions grant,) | Campus Calderdale Co Director |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Economy and Enterprise |  |  |  |  |  |  |  |  |  |
|  | Outcome | Increase attainment levels of young people by age 19 |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EE08 (NTG) | Indicator to measure education attainment relative to district average |  |  |  |  |  |  |  |  |
|  | EE08a(NTG) | In Ovenden Initiative Neighbourhood Element Area |  |  |  |  |  |  |  |  |
|  | EE08b(NTG) | In Mixenden Initiative neighbourhood management area (NE) |  |  |  |  |  |  |  |  |
|  | EE08c(NTG) | In Park Community Initiative neighbourhood management area (NE) |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EE08 (1) | Development of a wider curriculum offer for young people aged 14-19 especially vocational provision. | Campus Calderdale | Campus Calderdale is a consortium of all providers | Completion of curriculum audit and commissioning of courses to fill gaps, on-line prospectus established, improved attainment at exams in Summer. | Jan-07 | Jul-08 | Pooled budget from 13-19 strategy | Co-Director of Campus Calderdale |  |
|  | EE08 (2) | Improve the quality of provision through improved data analysis and quality assurance mechanisms | Campus Calderdale | Campus Calderdale is a consortium of all providers | Establishment of data analysis group, commissioning of data analysis, dissemination to providers, identification of lead departments, agreed QA protocols. | Jan-07 | Jul-08 | Pooled budget from 13-19 strategy | Co-Director of Campus Calderdale |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Economy and Enterprise |  |  |  |  |  |  |  |  |  |
|  | Outcome | Increase attainment levels of young people by age 19 |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EE09 (M) (NTG) | Percentage of 16-18 year olds not in education, employment or training |  |  |  |  |  |  |  |  |
|  | EE09a (M) | In Calderdale |  |  |  |  |  |  |  |  |
|  | EE09b(NTG) | In Ovenden Initiative neighbourhood management area (NMP) |  |  |  |  |  |  |  |  |
|  | EE09c(NTG) | In Mixenden Initiative neighbourhood management area (NE) |  |  |  |  |  |  |  |  |
|  | EE09d(NTG) | In Park Community Initiative neighbourhood management area (NE) |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EE09 (M) (NTG)(1) | Target young people age 14-16 at risk of being NEET | Campus Calderdale | Campus Calderdale is a consortium of Calderdale College, Schools, Work-based learning providers, Young Peoples service and Connexions partners | Establish programmes with schools, exam results, course recruitment | Jan-07 | Jul-09 | Pooled budget from 13-19 strategy | Co-Director of Campus Calderdale |  |
|  | EE09 (2) | Develop entry to employment provision, entry level, level 1 and level 2 provision | Campus Calderdale | Campus Calderdale is a consortium of Calderdale College, Schools, Work based learning providers, Young Peoples service and Connexions partners | Curriculum audit, commissioning of new courses, recruitment to courses and completion of courses | Jan-07 | Jul-09 | Pooled budget from 13-19 strategy | Co-Director of Campus Calderdale |  |
|  | EE09(3) | Improve access to vocational and work based provision | Campus Calderdale | Campus Calderdale is a consortium of Calderdale College, Schools, Work-based learning providers, Young Peoples service and Connexions partners | Establish a programme of courses with Work-based Learning providers, monitor recruitment and retention. Evaluate achievement | Jan-07 | Jul-09 | Pooled budget from 13-19 strategy | Co-Director of Campus Calderdale |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Economy and Enterprise |  |  |  |  |  |  |  |  |  |
|  | Outcome | Increase attainment levels of young people by age 19 |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EE10 (NTG) | Percentage of young people with learning difficulties / disabilities aged over 16 who remain in full-time education, training or employment |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EE10 (1) | Improve the pathways for young people by increasing provision of pre-entry, entry and level 1 courses. | Campus Calderdale | Campus Calderdale is a consortium of Calderdale College, Schools, Work based learning providers, Young Peoples service and Connexions partners | Audit current provision, create curriculum model, commission new provision. | Jan-07 | Jul-09 | LSC funding identified for LDD provision. & standards fund. | CMBC Principal Officer Inclusion Services |  |
|  | EE10 (2) | Develop quality assurance mechanisms including management information regarding progression of young people especially analysis of comparative providers and destinations | Campus Calderdale | Campus Calderdale is a consortium of Calderdale College, Schools, Work based learning providers, Young Peoples service and Connexions partners | Set up and collect baseline data, establish targets agree protocols, publish findings | Jan-07 | Jul-09 | LSC funding identified for LDD provision. & standards fund. | CMBC Principal Officer Inclusion Services |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Economy and Enterprise |  |  |  |  |  |  |  |  |  |
|  | Outcome | Increase attainment levels of young people by age 19 |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EE11 (NTG) | Ratio of young people leaving care aged 16 or over engaged in full time education, training or employment to the total in the age group |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EE11 (1) | Provide targeted support and mentoring from the LACE service to work with individuals to enhance education provision | Looked after Children education Service (LACE) | Schools, Care services, Campus Calderdale | Establish a statement of action, implementation plan and monitor achievements | Jan-07 | Jul-09 | LSC grant, standards fund, LACE base funding | CMBC Head of Vulnerable Children's Service |  |
|  | EE11 (2) | Provide targeted support from Connexions P.A.s to provide appropriate Information Advice and guidance | LACE | Schools, Care services, Campus Calderdale | Established enhanced Service Level Agreement for LACE. Monitor progress and evaluate outcomes | Jan-07 | Jul-09 | Connexions grant | Partnership Director for Connexions in Calderdale. |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Economy and Enterprise |  |  |  |  |  |  |  |  |  |
|  | Outcome | Increase of successful and sustainable existing and new businesses |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EE12 | Growth in the nos of new businesses being established, including social enterprises |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EE12 | 1) Increase the rate of growth of new businesses in Calderdale being established, including social enterprises. 2) Business support partners will co-ordinate business support activities and share information to increase the rate of growth of new businesses in Calderdale. | CMBC | BLWY, Action Halifax, Halifax Works, Jobcentre Plus, Halifax Opportunities Trust, Calderdale College, MYCCI | 394 businesses established in 2007/8, 414 in 2008/9 and 434 in 2009/2010. | Apr-07 | Mar-10 | Existing and in place | CMBC Economic Devt Manager |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Economy and Enterprise |  |  |  |  |  |  |  |  |  |
|  | Outcome | Increase of successful and sustainable existing and new businesses |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EE13a (RE04) | Increase the proportion of new businesses surviving for at least 1 year in the district |  |  |  |  |  |  |  |  |
|  | EE13b | Increase nos of Tourism related businesses |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EE13a (RE04) | 1) Increase the proportion of new businesses surviving for at least 1 year in the district. 2) Through regular meetings of Calderdale business support partners collect information of business starts. 3) Refer business starts to Business Link West Yorkshire for early support. | CMBC | Business Link WY, Action Halifax, Halifax Works, JobCentre plus, Halifax Opportunities Trust, Calderdale College, MYCCI | 87% (191) survival in 2007/2008, 89% (218) in 2008/2009 and 91% (246) in 2009/2010 | Apr-07 | Mar-10 | Existing and in place | CMBC Economic Devt Manager |  |
|  | EE13b | Increase nos of quality Tourism related businesses | CMBC | Business Link WY, Halifax Works, Yorkshire Tourist Board, MYCCI | To survey the tourism sector in Calderdale to assess options for providing specific business support to this sector. Provision of specific business advice to new and existing businesses, target levels to be determined | Apr-07 | Mar-10 | Staff resource existing for business support. £15k pump priming for tourism business survey. | CMBC Principal Officer (Tourism & Rural Devt) |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Economy and Enterprise |  |  |  |  |  |  |  |  |  |
|  | Outcome | Increase of successful and sustainable existing and new businesses |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EE14 | Improve the supply of developable land for business purposes |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EE14 | 1) Improve the supply of developable land for business purposes; 2) Undertake Employment Land Review of Calderdale; 3) Establish ways of increasing the supply of employment land for business purposes working with private land owners, developers and Yorkshire Forward. | CMBC | MYCCI, Halifax Works | Calderdale Employment Land Survey to be completed in 2007. | Jun-07 | Sep-07 | Funding from CMBC S106 monies | CMBC Economic Devt Manager |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Economy and Enterprise |  |  |  |  |  |  |  |  |  |
|  | Outcome | Increase of successful and sustainable existing and new businesses |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EE15 | Increase nos of Creative and digital sector businesses |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EE15 | 1) Increase the number of creative and digital sector businesses in Calderdale; 2) Undertake survey of Calderdale creative and digital businesses; 3) Establish options to increase the number of creative and digital businesses in Calderdale. | CMBC | Action Halifax, Halifax Works, JobCentre Plus, Halifax Opportunities Trust, Calderdale College, MYCCI | To re-survey the creative business sector in Calderdale (first surveyed in 2004) to assess options for providing specific support to the creative and digital sector. | Sep-07 | Sep-08 | LAA priming grant of £20,000 required to fund this work | CMBC Economic Devt Manager |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Economy and Enterprise |  |  |  |  |  |  |  |  |  |
|  | Outcome | Dynamic and vibrant town centres |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EE16 | Average weekly football in town centres based on counts undertaken three times per annum |  |  |  |  |  |  |  |  |
|  | EE16a | Number of Towns with 3 annual counts |  |  |  |  |  |  |  |  |
|  | EE16b | Average weekly football in Halifax |  |  |  |  |  |  |  |  |
|  | EE16c | Average weekly football in Hebden Bridge |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EE16a (1) | Ensure Engineering Services are informed that counts must be carried out in relevant towns | CMBC |  | Engineering Services to have: 1) dates selected for counts; 2) staff resource identified; 3) counts completed at times required | 1) April 2007; 2) ongoing; 3) each 4 months in each town | 1) April 2007; 2) ongoing; 3) within identified month | Engineering Services have budget/ staff available and methodology is already developed | CMBC Principal Planning Officer (Conservation & Renewal) & CMBC Senior Engineer |  |
|  | EE16b (1) | Depends on EE16a having been completed - then further calculation provides this indicator | CMBC |  | Counts completed; calculation finished | Every 4 months | Within 1 week of each count completion | Engineering Services have budget/ staff available and methodology is already developed | CMBC Principal Planning Officer (Conservation & Renewal) & CMBC Senior Engineer |  |
|  | EE16c (1) | Depends on EE16a having been completed - then further calculation provides this indicator | CMBC |  | Counts completed; calculation finished | Every 4 months | Within 1 week of each count completion | Engineering Services have budget/ staff available and methodology is already developed | CMBC Principal Planning Officer (Conservation & Renewal) & CMBC Senior Engineer |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Economy and Enterprise |  |  |  |  |  |  |  |  |  |
|  | Outcome | Dynamic and vibrant town centres |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EE17 | Achievement of appropriate repairs and / or reuse of listed buildings and buildings in conservation areas as a result of Council / Partner action |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EE17(1) | J Dadd and S Campbell to keep accessible records of buildings receiving grant aid | CMBC RD | Action Halifax, Heritage Lottery Fund, Grant Panel | Composite schedule created of buildings repaired/reused - for keeping updated | Apr-07 | May-07 | 2 people doing complementary work - risk is that one person's contract ends in 2008 and she will be looking for a new job before the end of the grant scheme | CMBC Principal Planning Officer (Conservation & Renewal) |  |
|  | EE17(2) | J Dadd and S Campbell to set up a system to keep records of other buildings where non-grant action has resulted in improvements/reuse | CMBC RD | Action Halifax, Heritage Lottery Fund, Grant Panel | Schedule created to keep records of involvement with buildings where no grant available | Apr-07 | May-07 | 2 people doing complementary work - risk is that one person's contract ends in 2008 and she will be looking for a new job before the end of the grant scheme | CMBC Principal Planning Officer (Conservation & Renewal) |  |
|  | EE17(3) | All relevant officers in CMBC Planning Services made aware of need to keep records of contact with property-related contact | CMBC RD | na | Schedule circulated to relevant officers for ongoing completion | May-07 | May-07 | Graduate Planner to disseminate and monitor information collection | CMBC Principal Planning Officer (Conservation & Renewal) |  |

Calderdale LAA Delivery Plan

Environment

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Environment |  |  |  |  |  |  |  |  |  |
|  | Outcome | Cleaner, greener and safer public spaces |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EV01a | Environmental quality as measured by BVPI 199 - the proportion of relevant land and highways this is assessed as having significant or heavy combined deposits of litter and refuse |  |  |  |  |  |  |  |  |
|  | EV01b (NTG) | Principles of the BV199 survey will be applied at Neighbourhood level. This is over and above DEFRA survey requirements. Working with other partners to develop measures, which reflect overall neighbourhood liveability. |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EV01a (1) | Assessing the effectiveness of the cleansing operation in terms of routes and frequency | CMBC | n/a | The results from each BV199 inspection survey (carried out 3 times per year) will indicate those areas requiring improvement should they fall below standard. Results will be analysed and improvements made where necessary. | Apr-07 | Mar-08 | 360 hrs staff time (1 year) for inspection & adjustments | CMBC Head of Recreation, Sport and Streetscene |  |
|  | EV01a (2) | Educational anti-litter work in schools. Long-term improvements in attitudes towards littering and the local environment. | CMBC | Schools | Number of schools visited each year. Target of 6 in Spring, 5 in Summer, 2 in Autumn and 2 in Winter. | Apr-07 | Mar-08 | £5k over 1 year, 100 hrs staff time (dependent upon PSA monies) | CMBC Head of Recreation, Sport and Streetscene |  |
|  | EV01a (3) | Introduction of cigarette bins in town centres in preparation for the anti-smoking legislation coming into force in July 2007 | CMBC | n/a | 100 bins to be installed in the first year. Monitoring of effectiveness will be undertaken | Apr-07 | Mar-08 | £3,500 for purchase, £2,000 for installation. Maintenance currently unknown | CMBC Head of Recreation, Sport and Streetscene |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Environment |  |  |  |  |  |  |  |  |  |
|  | Outcome | Cleaner, greener and safer public spaces |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EV02 | BV89 - the percentage of residents satisfied with the way the Council has fulfilled its duty to keep relevant land and highways clear of litter and refuse |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EV02 (1) | Begin a programme of street washing in Town Centre areas | CMBC | n/a | To begin the removal of detritus and grime in Halifax town centre. Monitor satisfaction through Tracker survey | Currently unknown awaiting legal contract | Mar-10 | £100k for purchase, £90k operational cost over 3 years | CMBC Head of Recreation, Sport and Streetscene |  |
|  | EV02 (2) | Provide a more localised cleansing service through the Neighbourhood Cleansing Scheme | CMBC | n/a | Maintain local service in 10 areas. Monitor satisfaction through Tracker survey and cleanliness through BV199 | Apr-07 | Mar-10 | £900k over 3 years (existing budgets) | CMBC Head of Recreation, Sport and Streetscene |  |
|  | EV02 (3) | Educational and anti-litter work including promotional and marketing campaigns | CMBC | n/a | Long-term improvements in attitudes towards littering, the local environment and the cleansing service. Monitor satisfaction through Tracker survey. | Apr-07 | Mar-10 | Dependent upon available PSA monies | CMBC Head of Recreation, Sport and Streetscene |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Environment |  |  |  |  |  |  |  |  |  |
|  | Outcome | Cleaner, greener and safer public spaces |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EV03 (M) | Quality of surroundings as measured by the number of green flag parks in Calderdale |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EV03 (M) (1) | Improve the public satisfaction of parks by working towards the principles of green flag criteria. This includes, for example, being well maintained and clean, having regard to sustainability, conservation and heritage and involving the community. | CMBC | Friends/ Community groups | Achieve and maintain 5 green flag awards (1 per year) for Shibden, Manor Heath, Wellholme, People's and Centre Vale park. As each site has to be re-entered every year, continue to meet the criteria to keep the award. Use the principles of green flag to improve other district and local parks in Calderdale. | Apr-07 | Mar-10 | Minimum of £2,000 for entering green flag. Staff hours 962 over 3 yrs | CMBC Head of Recreation, Sport and Streetscene |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Environment |  |  |  |  |  |  |  |  |  |
|  | Outcome | Cleaner, greener and safer public spaces |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EV04 | Quality of surroundings as measured by BV119e - The percentage of residents satisfied with parks and open spaces (adults) |  |  |  |  |  |  |  |  |
|  | EV04a (M) | In Calderdale |  |  |  |  |  |  |  |  |
|  | EV04b (NTG) | In Mixenden Initiative neighbourhood management area (NE) |  |  |  |  |  |  |  |  |
|  | EV04c (NTG) | In Ovenden Initiative neighbourhood management area (NMP) |  |  |  |  |  |  |  |  |
|  | EV04d (NTG) | In Park Community Initiative neighbourhood management area (NE) |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EV04 (1) | To develop a measurement about neighbourhood liveability including cleanliness and safety issues. | CMBC | Ovenden Initiative and Park Community Initiative | Working with national organisations such as APSE and Encams to develop a neighbourhood indicator. | Nov-07 | Mar-08 | 100 hours (estimated time) | CMBC Head of Recreation, Sport and Streetscene |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Environment |  |  |  |  |  |  |  |  |  |
|  | Outcome | Cleaner, greener and safer public spaces |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EV05 (M) | An increase in the percentage of abandoned vehicles removed within 24 hours from the point where local authority is legally entitled to remove the vehicle (BVPI 1218b) |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EV05 (1) | Establishment of partnership arrangement with Kirklees MC and West Yorkshire Police | CMBC | CMBC, Kirklees MC, WY Police | Agreement in place | Ongoing | Mar-10 | Revenue budget of £31,170 pa in place | CMBC Head of Environmental Health |  |
|  | EV05 (2) | Review internal procedures and information systems to ensure optimum performance and full audit trail for performance indicator. Performance is already high and the target of 96% compliance will be dependent on this review. | CMBC | West Yorkshire Police | Procedures in place | Apr-07 | Mar-10 | No additional cost. Current budget of £31,170 pa | CMBC Head of Environmental Health |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Environment |  |  |  |  |  |  |  |  |  |
|  | Outcome | Tackling Climate change through reduced green house gas emissions |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EV06 (RE05) | Achieving enhanced CO2 emission reductions from the Council’s operational buildings and fleets and from schools |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EV06 (1) | Develop a school Carbon Management Strategy based on available emissions data | CMBC | Calderdale Sustainability Forum Alternative Technology Centre | Establishing league table of schools Production of Action Plan | Apr-07 | Jun-07 | School Environmental Coordinator (funded through PPG); Sustainability Officers | CMBC Sustainable Strategy Manager |  |
|  | EV06 (2) | Securing Carbon Trust funding for projects | CMBC | Carbon Trust | Submission of funding bid | Jun-07 | Jul-07 | School Environmental Coordinator (funded through PPG) Energy Manager Match funded from existing energy budget |  |  |
|  | EV06 (3) | 6 month review of projects | CMBC | Calderdale Sustainability Forum Alternative Technology Centre Carbon Trust | Progress report | Jan-08 | Jan-08 | School Environmental Coordinator (funded through PPG) |  |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Environment |  |  |  |  |  |  |  |  |  |
|  | Outcome | Increase access to and enjoyment of green spaces and the countryside |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EV07 | Use of off-highway cycleways |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EV07(1) | Data collection to establish baseline for existing cycle paths | CMBC | BW Sustrans | Establish baseline | Apr-07 | Apr-07 | LTP £20K | CMBC Head of Engineering Services |  |
|  | EV07(2) | Improve paths to provide surface to allow all year use | CMBC | BW Sustrans | Suitable surface agreed with BW | Apr-07 | Mar-09 | LTP £70K | CMBC Head of Engineering Services |  |
|  | EV07(3) | Extend route to complete S Bridge/ Cooper Bridge (CVC) Calder Valley Cycleway | CMBC | BW Sustrans | Design agreements | Apr-07 | Mar-10 | LTP £100K | CMBC Head of Engineering Services |  |
|  | EV07(4) | Publicity/ promotion | CMBC | BW Sustrans | Publish route information packs | Apr-07 | Mar-10 | LTP £20K | CMBC Head of Engineering Services |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Environment |  |  |  |  |  |  |  |  |  |
|  | Outcome | Reduce waste to landfill and increase recycling |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EV08 (M) (RE06) | Reduction in the percentage of municipal waste landfill by increasing the percentage of municipal waste recycled in Calderdale |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EV08 (1) | Vary current waste services contract by agreement with contractor (Focsa). Discussions are in progress to agree the terms of an increase in the tonnage of waste recycled to a level sufficient to achieve the target of 25% recycling from April 2007 to the end of the current contract. This will substantially consist of improved arrangements for recycling at household waste sites through additional staffing. | CMBC | Waste Collection Contractor (FOCSA) | Agreement of variation to contract (asap). Appoint staff and implement new arrangements (April 2007) | Feb 2007 April 2007 | March 2007 July 2008 | Approved revenue budget growth | CMBC Head of Environmental Health |  |
|  | EV08 (2) | Award new waste collection contract(s) in which performance standards are set to achieve required target of 30% recycling in a full contract year. | CMBC | Successful contractor(s) | Contract awarded Contract commences | Dec 2007 latest August 2008 | Mar-10 | Revenue budget | CMBC Head of Environmental Health |  |
|  | EV08 (3) | Improve Household Waste Recycling Sites by reconfiguration of recycling arrangements. This will require the progressing of two capital schemes (one covering Elland and Brighouse and the other Halifax and Todmorden). The first is in progress but underfunded, the other is in the Investment Plan and awaiting approval). The increase to a recycling rate of 30% is dependent upon the completion of these works. | CMBC | CMBC Building Contractors New (main) Waste Collection Contractor | Completion of capital works | Commenced in part | Jul-08 | First scheme in capital budget funded to £270k. A further £365k required due to condition of foundations at Elland, seeking further funding. Exploring 'top slicing of PSA grant. | CMBC Head of Environmental Health |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Environment |  |  |  |  |  |  |  |  |  |
|  | Outcome | Reduce waste to landfill and increase recycling |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EV09a (NTG) | Percentage of households who recycle their waste in Mixenden Initiative neighbourhood management area (NE) |  |  |  |  |  |  |  |  |
|  | EV09b (NTG) | Percentage of households who recycle their waste in Ovenden Initiative neighbourhood management area (NMP) |  |  |  |  |  |  |  |  |
|  | EV09c (NTG) | Percentage of households who recycle their waste in Park Community Initiative neighbourhood management area (NE) |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EV09 (1) | Use funding from Behavioural Change Local Fund to create baseline information and introduce communication and awareness schemes in the three areas. | CMBC | CMBC, Waste Resources Action Programme, local Neighbourhood Management teams | Complete baseline survey | Feb 2007 (Commenced) | Mar-08 | BCLF funding of £150k bid for and achieved | CMBC Head of Environmental Health |  |
|  | EV09 (2) | Secure funding and continue with awareness schemes and annual participation rates. Bid to LAA Pump Priming Fund (150k) | CMBC | CMBC, Waste Resources Action Programme, local Neighbourhood Management teams | Secure funding | Apr-08 | Mar-10 | Dependent on securing further funding of £150k | CMBC Head of Environmental Health |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Environment |  |  |  |  |  |  |  |  |  |
|  | Outcome | Residents have access to affordable, sustainable, good quality housing |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EV10a | The amount of new affordable houses built or refurbished |  |  |  |  |  |  |  |  |
|  | EV10b | Percentage of new planning consents that are either affordable housing, eco-homes or lifetime homes |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EV10 (1) | Delivery of units through National Affordable Housing Programme | CMBC | RSLs | All174 units in NAHP 2006/08 secured by Mar 2008 | Apr-07 | Mar-10 | £7.48m programmed for 2006/08, 2008/10 amount unknown | CMBC Housing and Community Partnerships Manager |  |
|  | EV10 (2) | Implementation of S106 policy requiring 20% of units on qualifying sites and lower threshold to 15 | CMBC | RSLs | Necessary steps taken to lower S106 thresholds in line with PPS3 by Summer 2007 | Apr-07 | Mar-10 | Staff resources within Housing Services. Input from planning required | CMBC Housing and Community Partnerships Manager |  |
|  | EV10 (3) | Use commuted sums to secure affordable, eco and lifetime homes | CMBC | RSLs | Brief inviting expressions of interest by Summer 2007 | Apr-07 | Mar-10 | Staff resources within Housing Service | CMBC Housing and Community Partnerships Manager |  |
|  | EV10 (4) | Develop appropriate supplementary planning policy to manage housing supply | CMBC |  | LDS core documents developed by 2008 | Apr-08 | Mar-09 | Staff resources within planning | CMBC Head of Regeneration and Planning |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Environment |  |  |  |  |  |  |  |  |  |
|  | Outcome | Improved access to affordable rural housing in Calderdale |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EV11 (RE07) | Number of households becoming owners/leaseholders of Low Cost Home Ownership (LCHO) units in rural areas during the period 2007 – 2010, excluding those already agreed through the National Affordable Housing Programme (NAHP) and Section 106 (S106) agreements already signed or to be agreed by 31 March 2007 or shortly thereafter. |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EV11(1) | Appoint Affordable Rural Housing Officer | CMBC |  | Post advertised May 2007. Appointment June 2007 | Jun-07 | Mar-10 | Pump priming grant/ LPSA Reward Grant | CMBC Housing and Community Partnerships Manager |  |
|  | EV11(2) | Review of land and property (both public and private) that may be developable for remodelling of low demand rented stock | CMBC | RSLs |  | Jun-07 | Mar-10 | Staff resources in Housing Services | CMBC Housing and Community Partnerships Manager |  |
|  | EV11(3) | Investigate possibility of 'exception sites' in rural areas per PPS3 | CMBC |  | Necessary policy in place to designate sites solely for affordable housing in rural areas by September 2007 | Apr-07 | Mar-10 | Staff resources in Legal and Planning | CMBC Head of Regeneration and Planning |  |
|  | EV11(4) | Maximise LCHO through S106 agreements, including use of commuted sums | CMBC | RSLs |  | Apr-07 | Mar-10 | Staff resources in Housing Services | CMBC Housing and Community Partnerships Manager |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Environment |  |  |  |  |  |  |  |  |  |
|  | Outcome | The rural and urban heritage and local wildlife habitats in the District are conserved, enhanced and enjoyed. |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EV12 | Council owned land identified as being of ecological importance that is in favourable or recovering condition |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EV12 (1) | Desk top review of sites and drafting of priority listing | CMBC |  | First draft completed by 30/06/07, consultation completed by 31/12/07, completion by 31/03/08 | Apr-07 | Mar-08 | Existing budgets and staff resources | CMBC Head of Recreation, Sport and Streetscene |  |
|  | EV12 (2) | Site surveys to verify desk top survey and collect ecological data | CMBC |  | Total of 6 priority sites this year. 50%completed by 30/06/07, 62.5% completed by 30/09/07, 75% completed by 31/12/07, 100% completed by 31/03/08 | Apr-07 | Mar-08 | Existing budgets and staff resources | CMBC Head of Recreation, Sport and Streetscene |  |
|  | EV12 (3) | Drafting of site management plans | CMBC |  | Total of 6 plans this year. 25% completed by 30/06/07, 50% completed by 30/09/07, 75% completed by 31/12/07, 100% completed by 31/03/08 | Apr-07 | Mar-08 | Existing budgets and staff resources | CMBC Head of Recreation, Sport and Streetscene |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Environment |  |  |  |  |  |  |  |  |  |
|  | Outcome | The transport needs of residents, businesses and visitors in the district are met |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EV13 | On target routes accommodate an expected increase in travel of 3% with an increase in journey time of 5% in 2010/11 (from LTP) |  |  |  |  |  |  |  |  |
|  | EV13a | A629 Huddersfield Road: Average journey time per person mile |  |  |  |  |  |  |  |  |
|  | EV13b | A646 Burnley Road: Average journey time per person mile |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EV13 (1) | Deliver Local Transport Plan | CMBC | WYLTP |  |  |  |  | CMBC Head of Engineering Services |  |
|  | EV13 (2) | Deliver Yorkshire Bus Initiative | METRO | CMBC | Agree priorities; Establish routes; Implement schemes |  |  |  |  |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Environment |  |  |  |  |  |  |  |  |  |
|  | Outcome | Residents and visitors to Calderdale are safe on the District's roads |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EV14a (M) | Percentage of schools with a travel plan |  |  |  |  |  |  |  |  |
|  | EV14b (M) | Modal Share in Travel to School: Pedestrian share of journeys to schools |  |  |  |  |  |  |  |  |
|  | EV14c (M) | Modal Share in Travel to School: Percentage of trips by cycle by year 7 and older students in schools that have implemented travel initiatives for cycling by 2010 |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EV14a (1) (M) | To target an additional 15 schools pa who have not yet engaged in the STP process. | CMBC | LEA, Schools. Local Residents, Healthy Schools co-ordinators, My Bus, DFES, DFT, PCT, DC, Traffic, Highways, | Annually identify schools. Obtain School agreement to STP. Engage through SRS initiatives. Produce plans | Ongoing | Mar-08 | £31,000 pa DFT, DFES, SRTS funding. Three part time STA to progress STP objectives. | CMBC Head of Engineering Services |  |
|  | EV14a (2) (M) | Using local examples of best practice and requests for school site safety improvement to encourage participation | CMBC | As EV14a (1) (M) | Identify best practice; Prepare documentation | Ongoing | Mar-08 | £31,000 pa DFT, DFES, SRTS funding. Three part time STA to progress STP objectives. | CMBC Head of Engineering Services |  |
|  | EV14(b) (1) (M) | To encourage primary schools to participate in the Government led and funded Walking Bus Initiative. To act as consultees in the conjunction with Government Departments | CMBC | LEA, Schools. Local community Groups, Healthy Schools co-ordinators, DFES, DFT | To provide guidance to schools and act as consultees. To sign off 29, 1st tranche applications for funding. April 2007 | Apr-07 | Mar-08 | As EV14a (1) (M). Plus £1000 grant for each school who successfully submitted a grant application (Payable: £1000 each year for a 2 year period). | CMBC Head of Engineering Services |  |
|  | EV14(b) (2) (M) | To develop and deliver a program of education aimed at supporting schools in their aim to increase modal share (Pedestrians). Safe Green Travel Day. | CMBC | Schools | 50% of schools with an active STP to have taken in the training by April 2008 | Apr-07 | Dependent upon DFES and DFT funding | £31,000 pa DFT, DFES, SRTS funding. Three part time STA to progress STP objectives. DFT/DFES funding until 2008 | CMBC Head of Engineering Services |  |
|  | EV14c (1) (M) | To encourage the participation of secondary schools in advanced cycle training for year 7 pupils | CMBC | SSCO's, Schools, Ovenden/Mixenden Initiative | Prepare priority list 1 2 3; Anticipated take up rate of schools: 25% by April 2008; 50% by April 2009 80% by April 2010; Target participation; Develop Best Practice from Yr 1; Target priorities 2 and 3 | Mar-07 | Mar-10 | Funded from revenue funding for cycling initiatives. Additional staff support from SSCO's not costed | CMBC Head of Engineering Services |  |
|  | EV14c (2) (M) | To encourage the take up of bike trains and then working with the transportation team move on to individual route plans for pupils | CMBC | SSCO's, Schools, Transportation | Agree plans with SSCO to develop bike trains. Provide individual route maps for 25% of pupils taking part in advanced cycle training with a personalised cycle route to school | Sep-07 | Mar-10 | As EV14c (2) (M) | CMBC Head of Engineering Services |  |
|  | EV14c (3) | To increase the number and quality of cycle storage facilities at senior schools, supporting the continuation of cycling following advanced training | CMBC | Schools, Transportation. | To establish quality facilities at the Calder High school by Sep 2007. ID best practice. ID other schools for priority | Sep-07 | Mar-10 | Using Schools own STP budget allocation. Additional capital funding not identified at this time. | CMBC Head of Engineering Services |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Environment |  |  |  |  |  |  |  |  |  |
|  | Outcome | Residents and visitors to Calderdale are safe on the District's roads |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EV15 (NTG) | Reduction in road casualties in 11-16 year olds |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EV15 (1) (NTG) | Deliver Road Safety lesson to pupils in year 7 (Zach's Story). Provide off-road loading areas at North Halifax Grammar School. Zebra crossing and parking restrictions at St Catherine High and Holy Trinity | CMBC | CMBC, School Base, Schools, My Bus | Sept 2007 school pupils loading off 75% of year 7 pupils to have taken part in this lesson by July 2007; Highway - Reducing parent parking through improved bus service | Apr 2007 Ongoing | Apr 2008 Review annually | 5K pa Revenue Budget. 114 hours classroom delivery and 50 hours co-ordination; 50,000 zebra and parking restriction; 220,000 My bus | CMBC Head of Engineering Services |  |
|  | EV15 (2) | Develop and deliver a Road Safety lesson for pupils in year 8 | CMBC | Schools | July 2008 to have delivered lessons to a minimum of 50% of year 8 pupils | Oct-07 | Review annually | 5K pa Revenue Budget. 114 hours classroom delivery time and 50 hours co-ordination |  |  |
|  | EV15 (3) | Develop and deliver a two part Road Safety lesson for pupils in year 10 | CMBC | WY Fire and Rescue Service, schools | March 2008 to have delivered lessons to a minimum of 50% of year 10 pupils | Apr-07 | Review annually in conjunction with WYFRS | 5K pa Revenue Budget (CMBC) including delivery and co-ordination. Partner costs? |  |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Environment |  |  |  |  |  |  |  |  |  |
|  | Outcome | Residents and visitors to Calderdale are safe on the District's roads |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | EV16 (NTG) | Reducing road casualties by increasing use of seat belts |  |  |  |  |  |  |  |  |
|  | EV16a | Adult population as a whole |  |  |  |  |  |  |  |  |
|  | EV16b | Adults from Asian community |  |  |  |  |  |  |  |  |
|  | EV16c | Child population (aged 0-15) as a whole |  |  |  |  |  |  |  |  |
|  | EV16d | Children (aged 0-15) from Asian community |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | EV16a (1) | Reducing adult car occupant casualties as a whole through the promotion of seat belt wearing. Using temporary road side posters | CMBC | Community Safety Partnership, WY Police, WYFRS, Highways and Traffic | Submit application through the DFT 'Road Safety Partnership Grant'. £124,440 over 2 years. Results of application will be known by April 2007 | May-07 | Mar-09 | Unless the authority is successful in securing the grant described in Key Milestone then no funding is presently identified to meet this target and no additional project time is available | CMBC Head of Engineering Services |  |
|  | EV16a (2) | To buy in additional Police enforcement 30 weeks per year over a two year period | CMBC | Community Safety Partnership, WY Police, WYFRS | 1) Submit application through the DFT 'Road Safety Partnership Grant'. £124,440 over 2 years. Results of application will be known by April 2007. 2) Employ a seat belt project officer to co-ordinate additional enforcement activity | May-07 | Mar-09 | Unless the authority is successful in securing the grant described in Key Milestone then no funding is presently identified to meet this target and no additional project time is available | CMBC Head of Engineering Services |  |
|  | EV16b (1) | Reducing adult car occupant casualties in the Asian Community through increased community engagement, education, promotion and roadside posters. | CMBC | Community Safety Partnership, WY Police, WYFRS- Working with community groups, community leaders, local businesses | Submitted application through the DFT 'Road Safety Partnership Grant'. £124,440 over 2 years. Results of application will be known by April 2007 | May-07 | Mar-09 | Unless the authority is successful in securing the grant described in Key Milestone then no funding is presently identified to meet this target and no additional project time is available | CMBC Head of Engineering Services |  |
|  | EV16b (2) | To buy in additional Police enforcement 30 weeks per year over a two year period | CMBC | WYFR, Community Safety Partnership, Park Initiative | Submit application through the DFT 'Road Safety Partnership Grant'. £124,440 over 2 years. Results of application will be known by April 2007. Employ a seat belt project officer to co-ordinate additional enforcement activity | May-07 | Mar-09 | Unless the authority is successful in securing the grant described in Key Milestone then no funding is presently identified to meet this target and no additional project time is available | CMBC Head of Engineering Services |  |
|  | EV16c (1) | Reduce child car occupant casulties0-15 years as a whole by providing seat belt training for year 1 pupils across the borough and providing specific information for parents | CMBC | Schools, parents, community groups and Sure Start in regeneration areas | Deliver training to 85% of all year 1 pupils in Calderdale | Apr-07 | Reviewed annually | £6K per annum. Funding already established through RS revenue | CMBC Head of Engineering Services |  |
|  | EV16c (2) | Working with the WYFRS to introduce seat belt wearing information as part of the year 5 fire safety lesson. | CMBC | CMBC, Schools, Parents, WYFRS | Lesson plans and seat belt demonstration equipment to made available by July 2007 | Apr-07 | Reviewed annually | £1000 for seat belt demonstration equipment (One off cost). Fire service personnel costs are limited to development time because lesson is to be incorporated in existing lesson. | CMBC Head of Engineering Services |  |
|  | EV16d(1) | Reducing child car occupant casualties 0-15 years (Asian community). To include initiatives described in EV16c (1&2) and increase the number of whole school initiatives. Providing an enhanced level of communication for parents/carers through the many partner organisation highlighted in section 4. Using Roadside poster to increase awareness. Seat belt wearing education to be included in EV15 (1,2,3) | CMBC | Schools, Community Leaders, Park community Initiative, Parent Groups, Sure Start, Highways and Traffic | Submit application through the DFT 'Road Safety Partnership Grant'.£124,440 over 2 years. Results of application will be known by April 2007 | May-07 | Mar-09 | Unless the authority is successful in securing the grant described in Key Milestone then no funding is presently identified to meet this target and no additional project time is available | CMBC Head of Engineering Services |  |
|  | EV16e(2) | To buy in additional Police enforcement 30 weeks per year over a two year period | CMBC | WY Police, Community Safety Partnership, WYFRS | Submit application through the DFT 'Road Safety Partnership Grant'.£124,440 over 2 years. Results of application will be known by April 2007. Employ a seat belt project officer to co-ordinate additional enforcement activity | May-07 | Mar-09 | Unless the authority is successful in securing the grant described in Key Milestone then no funding is presently identified to meet this target and no additional project time is available | CMBC Head of Engineering Services |  |

Calderdale LAA Delivery Plan

Safer and Stronger Communities

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Reduce Crime |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC01a (M) | Reduction in overall British Crime Survey comparator recorded crime |  |  |  |  |  |  |  |  |
|  | SSC01b (NTG) | Narrow the gap between neighbourhood management areas and the Calderdale average for crime |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC01(1) | Reduce the opportunities for offending through target hardening | West Yorks Police | Business Community and Social landlords, Mixenden, Ovenden and Park Community Initiatives | Review at Strategic Intelligence Assessment- Sept 2007 then every 6 months | Apr-07 | Mar-10 | Crime Reduction Officers | Community Safety Coordinator WY Police; Calderdale Division |  |
|  | SSC01(2) | Use the media to raise awareness and provide reassurance | West Yorks Police | Community Safety Partnership Mixenden, Ovenden and Park Community Initiatives | Release of British Crime Survey - January 2008 | Apr-07 | Mar-10 | Press Office | Community Safety Coordinator WY Police; Calderdale Division |  |
|  | SSC03(3) | Maximise the use of intelligence led activity in hot spot areas with active offender management | West Yorks Police | Area Planning Teams Mixenden, Ovenden and Park Community Initiatives | Review at Strategic Intelligence Assessment- Sept 2007 then every 6 months | Apr-07 | Mar-10 | Extended police family | Community Safety Coordinator WY Police; Calderdale Division |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Reduce Crime |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC02 | Reduction in recorded violent crime |  |  |  |  |  |  |  |  |
|  | SSC02a | In Calderdale |  |  |  |  |  |  |  |  |
|  | SSC02b (NTG) | In Mixenden Initiative neighbourhood management area (NE) |  |  |  |  |  |  |  |  |
|  | SSC02c (NTG) | In Ovenden Initiative neighbourhood management area (NMP) |  |  |  |  |  |  |  |  |
|  | SSC02d (NTG) | In Park Community Initiative neighbourhood management area (NE) |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSCO2 (1) Prevention | Coordinate and proactive visits to identified problem licensed premises with appropriate partners. Utilise schools liaison to raise awareness of and give crime prevention advice to all students. High visibility policing at identified hot spot location and planned events. High visibility policing and increased use of CCTV at identified hot spot locations, planned events and licensed premises. Engage with crime and disorder reduction partnership to develop joint initiatives. Identify and introduce successful prevention strategies utilised in other areas. Media to be used to raise personal safety awareness of drink spiking and drug assisted sexual assault. | West Yorkshire Police | Local licensing authority, trading standards, youth services, press office and the PCT. Mixenden, Ovenden and Park Community Initiatives | Review at Strategic Intelligence Assessment | Apr-07 | Sep-07 | Police, Local authority and Pub watch | Community Safety Coordinator WY Police; Calderdale Division |  |
|  | SSC02 (2) Intelligence | Targeting of prolific and other priority offenders or persons posing a danger to the public. Analyse identification to identify linked crime scenes. Targeting of persons known to use weapons particularly knives, firearms or imitation firearms in the commission of other offences. Focus on identified key events or activities linked with high levels of offence. Focus on problem licensed premises with links to drug and alcohol abuse. Maximise the use of intelligence gathered from victims and witnesses particularly those in crime and domestic violence offences. Prolific and persistent offenders and their networks. Exploit intelligence opportunities through prisoner processing, scene attendance and policing partners and schemes e.g. door schemes. Tasking of intelligence sources. Ensure that any incidents suspected of being hate crime and domestic violence crimes are identified and highlighted. Produce predictive analysis of offenders and offences. | West Yorkshire Police | Voluntary sector and area planning teams. Mixenden, Ovenden and Park Community Initiatives | Review at Strategic Intelligence Assessment | Apr-07 | Sep-07 | Police, Local voluntary groups, Divisional intelligence unit. | Community Safety Coordinator WY Police; Calderdale Division |  |
|  | SSC02 (3) Enforcement | Ensure standards of investigation are adhered to e.g. regular communication with victims. Target persons circulated as wanted for violent crime offences. Early arrest of those responsible for offences of violence. High visibility patrolling strategies within hot spot locations. Effective targeting of offenders and the utilisation of anti social behaviour measures. Maximising the intelligence from forensic identifications. Targeting of repeat perpetrators of violence offences. Effective multi agency approach to tackle public protection issues. Adherence to domestic violence and child protection policy. | West Yorkshire Police | Local authority and area planning teams, Social services and protection agencies. Mixenden, Ovenden and Park Community Initiatives | Review at Strategic Intelligence Assessment | Apr-07 | Sep-07 | Extended police family, local authority, and public protection agencies. | Community Safety Coordinator WY Police; Calderdale Division |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Reduce Crime |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC03 | Reduction in recorded Criminal Damage |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC03 (1) Prevention | Increase effective diversionary activities. Proactive intervention at schools, including the use of school liaison officers. Tasking of Neighbourhood policing teams and partner agencies in patrolling hot spot areas. Problem solving approaches to be used by Neighbourhood Policing Teams and Partners on long term damage issues. | West Yorkshire Police | Youth services, School liaison Officer, Youth Offending teams, Area planning teams, Pennine Housing 2000, Mixenden, Ovenden and Park Community Initiatives | Review at Strategic Intelligence Assessment | Apr-07 | Sep-07 | Extended police family, Social landlords, youth services, area planning teams | Community Safety Coordinator WY Police; Calderdale Division |  |
|  | SSC03 (2) Intelligence | All scenes of criminal damage to be properly recorded, visited and robustly investigated. Identification of repeat locations. Prolific and persistent offenders. Utilise all appropriate forensic opportunities to link offences and offenders. | PH2000 | West Yorkshire Police, Mixenden, Ovenden and Park Community Initiatives | Review at Strategic Intelligence Assessment | Apr-07 | Sep-07 | PH2K, Police. | PH2K Director of Operations |  |
|  | SSC03 (3) Enforcement | Target hotspot locations, Target persistent offenders. | West Yorkshire Police | Local authority area planning teams, Mixenden, Ovenden and Park Community Initiatives | Review at Strategic Intelligence Assessment | Apr-07 | Sep-07 | Extended police family | Community Safety Coordinator WY Police; Calderdale Division |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Reduce Crime |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC04 (M) | Reduction in the proportion of adult and young offenders, and prolific and other priority offenders who re-offend |  |  |  |  |  |  |  |  |
|  | SSC04a | Young Offenders |  |  |  |  |  |  |  |  |
|  | SSC04b | Prolific and priority offenders |  |  |  |  |  |  |  |  |
|  | SSC04c | Adults |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC04a (1) | Formation of a youth crime prevent and deter strategy task group | Calderdale YOT | Police, C&YP, Crown Prosecution Services, Safer communities | Complete Strategy Obtain approval from partners; Implementation of monthly group | To be advised | To be advised | Staff, information | Calderdale YOT Manager / Assistant Chief Officer, Probation Service |  |
|  | SSC04a (2) | Ensure a minimum of 70% of young people are consulted through the use of Asset and Evaluation process | Calderdale YOT |  | Review percentage of completed forms quarterly | Apr-07 | Ongoing |  | Calderdale YOT Manager / Assistant Chief Officer, Probation Service |  |
|  | SSC04a (3) | Collate, review and categorise current offending behaviour programmes | Calderdale YOT |  | Collate current resources; Review range and quality; Identify gaps; Obtain resources and complete staff training | Apr-07 | Sep-07 | Staff | Calderdale YOT Manager / Assistant Chief Officer, Probation Service |  |
|  | SSC04b (1) | Delivery of a 'Premium Service' to all PPOs by all key partners | West Yorkshire Probation Service | Police, YOT, DIP, Housing, ETE providers | 1) Statutory partners review, agree premium service; 2) Non statutory partners agree a premium service; 3) Monitoring and feeding back to SCP | 1) April 2007; 2) May 2007; 3) April 2007 | 1) July 2007; 2) Sept 2007; 3) Ongoing | 1) PPO Strategy Group; 2) Safer Community Partnership; 3) PPO Operational Group | Assistant Chief Officer, Probation Service / Superintendent (Operations) WYP Calderdale Division |  |
|  | SSC04c (1) | Calderdale District of WYPS exceed last years performance for compliance across all cases in the community | West Yorks Probation Service |  |  | Apr-07 | Mar-08 | Probation staff HIMMAT Project | Assistant Chief Officer, Probation Service |  |
|  | SSC04c (2) | Increase the number of DRR starts and completions from 06/07 performance | West Yorks Probation Service | SMS DRR workers, DIP, ROB |  | Apr-07 | Mar-08 | Probation staff HIMMAT Project | Assistant Chief Officer, Probation Service |  |
|  | SSC04c (2) | Increase the number of offenders who gain employment during period of supervision | West Yorks Probation Service | Job Centre, ETE providers, Special initiatives |  | Apr-07 | Mar-08 | Probation staff HIMMAT Project | Assistant Chief Officer, Probation Service |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Reduce Crime |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC05 (RE08) | Reducing alcohol related harm by increasing the number of hazardous, harmful and dependent drinkers who will be screened and receive brief interventions |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC05 (1) | Finalise service specification | Calderdale PCT | PCT, CHFT, WY Police, CMBC, Probation Service, Pennine Housing | 1)PCT Board agreement as to the direction of travel in respect of service provision. 2) Final draft of specification. 3) Specification to in-house provider or out to tender dependent on above agreement | 1) Feb 2007, 2) Feb 2007 | 1) Mid March 2007; 2) Mid March 2007; 3) 1 April 2007 | 1) Existing staff hours; 2) Existing staff hours; 3) TBC | PCT Public Health Manager |  |
|  | SSC05 (2) | Implement WHO screening tool in baseline settings | Calderdale PCT | PCT, CHFT, WY Police, CMBC, Probation Service, Pennine Housing | 1) map current baseline service providers. 2) Produce monitoring forms to include age, ethnicity, gender and post code | 1) Feb 2007, 2) Mid March 2007 | 1) Mid March 2007; 2) 1 April 2007 | 1) Existing staff hours; 2) Existing staff hours | PCT Public Health Manager |  |
|  | SSC05 (3) | Establish performance management arrangements | Calderdale PCT | PCT, CHFT, WY Police, CMBC, Probation Service, Pennine Housing | 1) Establish database of people screened, numbers receiving brief interventions and impact on World Health Organisation tool score. 2) Set up quarterly reporting mechanisms | 1) Feb 2007, 2) Feb 2007 | 1) Feb 2007; 2) April 2007 | To be confirmed | PCT Public Health Manager |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |
|  | Outcome | Reduce Crime |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |
|  | SSC06 | Increase the numbers of offences, which are brought to justice |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |
|  |  |  | West Yorkshire Police |  |  |  |  |  | Superintendent (Operations) WYP Calderdale Division |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Reassure the public, reducing the fear of crime |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC07 (NTG) | The % of residents surveyed who feel "fairly" or "very safe" when outside in Calderdale during the day |  |  |  |  |  |  |  |  |
|  | SSC07a | In Calderdale |  |  |  |  |  |  |  |  |
|  | SSC07b | In Mixenden Initiative neighbourhood management area (NE) |  |  |  |  |  |  |  |  |
|  | SSC07c | In Ovenden Initiative neighbourhood management area (NMP) |  |  |  |  |  |  |  |  |
|  | SSC07d | In Park Community Initiative neighbourhood management area (NE) |  |  |  |  |  |  |  |  |
|  |  | The % of residents surveyed who feel "fairly" or "very safe" when outside in Calderdale after dark |  |  |  |  |  |  |  |  |
|  | SSC07e | In Calderdale |  |  |  |  |  |  |  |  |
|  | SSC07f | In Mixenden Initiative neighbourhood management area (NE) |  |  |  |  |  |  |  |  |
|  | SSC07g | In Ovenden Initiative neighbourhood management area (NMP) |  |  |  |  |  |  |  |  |
|  | SSC07h | In Park Community Initiative neighbourhood management area (NE) |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC07(1) linked to SSC08 (3) | Develop a Partnership Communications plan including the promotion of activities which take place on a neighbourhood level | CMBC | Police Probation Local media PH2k Mixenden, Ovenden and Park Community Initiatives | Strategy and action plans agreed | Apr-07 | Oct-07 | Staff time 20 hours | CMBC Community Safety Manager |  |
|  | SSC07(2) | Develop work to produce a Partnership Toolkit CDRom | CMBC | Police Probation Local media PH2k Mixenden, Ovenden and Park Community Initiatives | Strategy and action plans agreed | Apr-07 | Oct-07 | Staff time 148 hours | CMBC Community Safety Manager |  |
|  | SSC07(3) | Proactive work with local media to instigate a campaign working in partnership with the Courier to address criminal damage | CMBC | Police Halifax Courier Mixenden, Ovenden and Park Community Initiatives | Agree Action Plan with Courier | Mar-08 | Mar-08 | Staff time | CMBC Community Safety Manager |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Reassure the public, reducing the fear of crime |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC08 (NTG) | The % of residents surveyed who feel "fairly" or "very safe" when outside in their local area during the day |  |  |  |  |  |  |  |  |
|  | SSC08a | In Calderdale |  |  |  |  |  |  |  |  |
|  | SSC08b | In Mixenden Initiative neighbourhood management area (NE) |  |  |  |  |  |  |  |  |
|  | SSC08c | In Ovenden Initiative neighbourhood management area (NMP) |  |  |  |  |  |  |  |  |
|  | SSC08d | In Park Community Initiative neighbourhood management area (NE) |  |  |  |  |  |  |  |  |
|  |  | The % of residents surveyed who feel "fairly" or "very safe" when outside in their local area after dark |  |  |  |  |  |  |  |  |
|  | SSC08e (NTG) | In Calderdale |  |  |  |  |  |  |  |  |
|  | SSC08f | In Mixenden Initiative neighbourhood management area (NE) |  |  |  |  |  |  |  |  |
|  | SSC08g | In Ovenden Initiative neighbourhood management area (NMP) |  |  |  |  |  |  |  |  |
|  | SSC08h | In Park Community Initiative neighbourhood management area (NE) |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC08 (1) | Implement a programme of pro-active multi-agency action days in hot spots with high profile | CMBC | Police Probation local media Ph2k, Mixenden, Ovenden and Park Community Initiatives | One focus area per month. Pilots to run from April - September 2007 | Apr-07 | Sep-07 | Staff time in co-ordination and planning 40 hours; Deployment of resources | CMBC Community Safety Manager / Community Safety Coordinator WY Police; Calderdale Division |  |
|  | SSC08 (2) linked with SSC18 (3) | Organise "Face The People" events to complement the borough wide Action Days | CMBC | Police Probation local media Ph2k Mixenden, Ovenden and Park Community Initiatives | Small working group agree format Publish dates |  | Reday for launch at above events | Partnership Officer time approx 30 hours + cost of venue | CMBC Community Safety Manager |  |
|  | SSC08 (3) linked with SSC07 (1) | Develop a partnership Communications Plan with focussed activities on borough wide issues | CMBC | Police Probation local media Ph2k, Mixenden, Ovenden and Park Community Initiatives | Strategy and action plans agreed sTRA | Apr-07 | Oct-07 | Staff time 20 hours | CMBC Community Safety Manager |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Reduce the harm caused by illegal drugs |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC09(M) | Reduction in the public perceptions or local drug dealing and drug use as a problem |  |  |  |  |  |  |  |  |
|  | SSC09a | In Calderdale |  |  |  |  |  |  |  |  |
|  | SSC09b (NTG) | In Mixenden Initiative neighbourhood management area (NE) |  |  |  |  |  |  |  |  |
|  | SSC09c (NTG) | In Ovenden Initiative neighbourhood management area (NMP) |  |  |  |  |  |  |  |  |
|  | SSC09d (NTG) | In Park Community Initiative neighbourhood management area (NE) |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC09a (M) | 1) Police activity reducing supplies 2) Community drugs awareness involvement through APTs 3) Develop reporting process and clear up drug taking paraphernalia | CMBC | WY Police, CMBC, PH2K, Safer Communities Partnership, Mixenden, Ovenden and Park Community Initiatives | Talkback' results compared with results from 2005/6 and 2006/7 | Apr-07 |  |  | Calderdale DAAT Manager |  |
|  | SSC09b (NTG) | 1) Police activity reducing supplies 2) Community drugs awareness involvement through APTs 3) Develop reporting process and clear up drug taking paraphernalia | CMBC | WY Police Mixenden IN Area, PH2K Safer Communities APT Mixenden, Ovenden and Park Community Initiatives | 1) Drug awareness materials developed. 2) Reporting process developed. | Apr-07 |  |  | Calderdale DAAT Manager |  |
|  | SSC09c (NTG) | 1) Police activity reducing supplies 2) Community drugs awareness involvement through APTs 3) Develop reporting process and clear up drug taking paraphernalia | CMBC | WY Police Mixenden IN Area, PH2K, Safer Communities APT; Mixenden, Ovenden and Park Community Initiatives | 1) Drug awareness materials developed. 2) Reporting process developed. | Apr-07 |  |  | Calderdale DAAT Manager |  |
|  | SSC09d (NTG) | 1) Police activity reducing supplies 2) Community drugs awareness involvement through APTs 3) Develop reporting process and clear up drug taking paraphernalia | CMBC | WY Police Mixenden IN Area, PH2K, Safer Communities APT, Mixenden, Ovenden and Park Community Initiatives | 1) Drug awareness materials developed. 2) Reporting process developed. | Apr-07 |  |  | Calderdale DAAT Manager |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Reduce the harm caused by illegal drugs |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC10 | Reduction in offending by drug users engaged in structured treatment programmes |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC10 | Calderdale treatment system for drug misuse will demonstrate impact on the level of drug related crime committed by drug users engaged in structured treatments. | Calderdale PCT | Lifeline Vocational Skills Service, National Probation service, CMBC Housing, Calderdale User Forum | Develop a monitoring system | April 2006 | Sep-06 | Police Drug Testing Staff - Drug Treatment Provider Staff - DAAT Research Staff | PCT Partnership Commissioning Manager |  |
|  |  | Baseline will record the number of individual drug users testing positive for Class A drug use within Calderdale's Test on Arrest scheme who are already engaged in Tier 3 structured drug treatment. This will be expressed as a percentage, this cohort of MDT positives against a denominator of the total engaged in T3 treatment and reported each quartile. | Calderdale PCT | Police, Providers, DAAT | Establish a baseline | Apr-06 | Mar-07 | AA | PCT Partnership Commissioning Manager |  |
|  |  | Establishing as part of Local Outcome Measures | Calderdale PCT | SSC | Becomes part of Partnership outcome monitoring framework | Apr-07 |  | Partnership | PCT Partnership Commissioning Manager |  |
|  |  | Enhancing local performance management of service delivery | Calderdale PCT | SSC | Built into contract performance management with service providers as part of service level agreements | Apr-07 | TBA | Partnership Commissioning Manager | PCT Partnership Commissioning Manager |  |
|  |  | Improving treatment effectiveness | Calderdale PCT | Providers | Increase the number of drug users accessing > 1 structured treatment programme at any one time to improve outcomes | Apr-07 | Mar-10 | Partnership Commissioning Manager and Treatment Providers | PCT Partnership Commissioning Manager |  |
|  |  | Improving multi agency service co-ordination | Calderdale PCT | Providers | Ensure there is effective co-ordination of substance misuse treatment programmes across Calderdale | Apr-07 | Mar-10 | Models of care Co-ordination Group | PCT Partnership Commissioning Manager |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Build Respect in communities and reduce anti-social behaviour |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC11 (M) | Increase in percentage of people who feel informed about what is being done to tackle anti-social behaviour in their local area |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC11 (1) | Organise and Anti-Social Behaviour Awareness Event | CMBC | CDRP, Police, CPS, Fire and Rescue, RSLs Mixenden, Ovenden and Park Community Initiatives | Plan ready by 23rd May 2007 | 6th June 2007 | 7th June 2007 | Partnership Officer time (approx 40 hours + cost of venue) | CMBC Community Safety Manager |  |
|  | SSC11 (2) | Produce a leaflet, outlining the contribution of partners to tackling Anti-Social Behaviour | CMBC | Police, Probation, Ph2k Mixenden, Ovenden and Park Community Initiatives | Small working group agree format. Publish leaflet & copy to existing media sources |  | Ready for launch at above event | Partnership Officer time (approx 20 hours + cost of printing) | CMBC Community Safety Manager |  |
|  | SSC11 (3) linked with SSC08 (2) | Organise "Face The People" events to complement the borough wide Action Days | CMBC | CDRP, Police, CPS, Fire and Rescue, RSLs Mixenden, Ovenden and Park Community Initiatives | Small working group agree format. Publish date ? |  | Ready for launch at above event | Partnership Officer time (approx 30 hours + cost of venues) | CMBC Community Safety Manager |  |
|  | SSC11 (4) | Implement the Government's 'No witness, No justice campaign' | CMBC | Police, Probation, Ph2k Mixenden, Ovenden and Park Community Initiatives | Develop Delivery Action Plan | Apr-07 | Oct-07 | Staff time | CMBC Community Safety Manager |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Build Respect in communities and reduce anti-social behaviour |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC12 (M) | Increase the percentage of people who feel that parents in their local area are made to take responsibility for the behaviour or their children |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  |  |  | CMBC |  |  |  |  |  | TBC |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Build Respect in communities and reduce anti-social behaviour |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC13 (M) | Increase the percentage of people who feel that people in their area treat them with respect and consideration |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC13 (1) | Implement Anti-Social Behaviour Strategy | CMBC | Safer Communities Partnership Mixenden, Ovenden and Park Community Initiatives |  | Apr-07 | Mar-10 | CMBC and other agency staff time | CMBC Housing and Community Partnerships Manager |  |
|  | SSC13 (2) | Facilitate programme of inter-generational cohesion projects, incorporating results from youth survey | CMBC | VCS, schools, Youth Service Mixenden, Ovenden and Park Community Initiatives | Potential projects identified by June 2007. Programme begins September 2007 | Apr-07 | Mar-10 | LPSA reward grant | CMBC Housing and Community Partnerships Manager |  |
|  | SSC13 (3) | Undertake research to investigate what can make people feel they are not treated with respect and formulate subsequent action plan | CMBC | VCS, Mixenden, Ovenden and Park Community Initiatives | Research completed by December 2007 | Jun-07 | Mar-10 | LPSA reward grant | CMBC Housing and Community Partnerships Manager |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Build Respect in communities and reduce anti-social behaviour |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC14(M) | Reduction in people's perceptions on ASB (using the 7 issues stated in the survey) |  |  |  |  |  |  |  |  |
|  | SSC14a | Overall |  |  |  |  |  |  |  |  |
|  |  | 7 issues are defined as |  |  |  |  |  |  |  |  |
|  | SSC14b | Noisy neighbours or loud parties |  |  |  |  |  |  |  |  |
|  | SSC14c | Teenagers hanging around on the streets |  |  |  |  |  |  |  |  |
|  | SSC14d | Rubbish and litter lying around |  |  |  |  |  |  |  |  |
|  | SSC14e | Abandoned or burnt out cars |  |  |  |  |  |  |  |  |
|  | SSC14f | Vandalism, graffiti and other deliberate damage to property or vehicles |  |  |  |  |  |  |  |  |
|  | SSC14g | People being victimised or harassed because of their skin colour, ethnic origin or religion |  |  |  |  |  |  |  |  |
|  | SSC14h | People being drunk and rowdy |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC14 (1) | Consolidate the DPPO restrictions of street drinking | CMBC | Community Safety Partnership - Specifically PCT, DAAT and NPT | Safer Drinking Publicity Event | By June 2007 | Ongoing | Partners Staff time and Publicity | CMBC Community Safety Manager |  |
|  | SSC14 (2) | Develop a Borough wide Graffiti database | CMBC | Police, Police Authority, Probation, Ph2k | Graffiti data to be included in Partnership Strategic Assessment | Oct-07 | Mar-08 | Staff time | CMBC Community Safety Manager |  |
|  | SSC14 (3) | Implementation of Designated Public Places Order (DPPO) | CMBC | Police, Police Authority, Probation, Ph2k | Signs up around Borough and information provided to the public | Apr-07 | Sep-07 | Staff time | CMBC Community Safety Manager |  |
|  | SSC14 (4) | Run Programme of Test Purchases at Off Licences | CMBC | Police, Police Authority, Probation, Ph2k Trading standards | Test Purchases carried out in Hotspot areas | Apr-07 | Sep-07 | Trading Standards | CMBC Community Safety Manager |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Build Respect in communities and reduce anti-social behaviour |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC15 | Reduction in the number of first time entrants to the youth justice system |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC15 (1) | Formation of a youth crime prevent and deter strategy task group | Calderdale YOT | Police, CYP, CPS, Safer Communities, Mixenden, Ovenden and Park Community Initiatives | Terms of reference. Obtain approval from partners. Implementation of a monthly group | Apr-07 | Ongoing | Staff and Information | Calderdale YOT Manager |  |
|  | SSC15 (2) | Development of a protocol to identify and divert potential first time entrants | Calderdale YOT | Police, C&YP, CPS | Completion of protocol; Approval from partners secured; Implementation of protocol | Apr-07 | Jul-07 | Staff | Calderdale YOT Manager |  |
|  | SSC15 (3) | Review range of current targeted prevention programme/activities in Calderdale to assure effectiveness | Calderdale YOT | C&YP, VCS, Mixenden, Ovenden and Park Community Initiatives | Prepare documentation; Complete self assessment; Complete report | Apr-07 | Mar-08 | Staff time | Calderdale YOT Manager |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Build Respect in communities and reduce anti-social behaviour |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC16 | Increase in the percentage of young offenders supervised by the Youth Offending Team who are in full time education, training or employment: Full time being 25 hrs per week |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC16 (1) | Develop in-depth relationship with cluster of Schools in Calderdale with high offending profile | Calderdale YOT | C&YP | Generate accurate data by school (April 2007). Call Head Teacher Meeting (May 2007). Action planning with schools (June 2007). Implementation (Sept 2007) | Apr-07 | Sep-07 | Staff time | Calderdale YOT Manager |  |
|  | SSC16 (2) | Needs analysis of those not achieving 25 hours ETE | Calderdale YOT | C&YP, VCS | Undertake assessments (June 2007). Collate findings (Sept 2007). Identify and agree developments (Dec 2007) | Jul-07 | Dec-07 | Staff time | Calderdale YOT Manager |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |
|  | Outcome | Build Respect in communities and reduce anti-social behaviour |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |
|  | SSC17a | Reduction by 10% in the number of deliberate primary fires |  |  |  |  |  |  |  |
|  | SSC17b | Reduction by 10% the number of secondary fires (this excludes seasonal grass fires) |  |  |  |  |  |  |  |
|  | SSC17c | Reduce accidental dwelling fire injuries by 20% |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |
|  | SSC17a (1) | Working with the Police and Youth services to identify high risk areas and strategies for managing these | WY Fire Service | Police CMBC | Establish risks and develop protocols with Police, CMBC/Highways | Apr-07 | Apr-08 | Station Managers/ Operational Fire-fighters | CMBC Inclusion Support Worker (Family Support Services) |
|  | SSC17a (2) | Working with Youth justice bodies to ensure that possible offenders know the consequences of causing deliberate fires | WY Fire Service | Police/YJB | Link Calderdale Offenders to WYFRS Fire Setting programme, linking closely with Neighbourhood policing teams | Apr-07 | Apr-08 | Operational Fire-fighters/ Community Safety Officers |  |
|  | SSC17b (1) | Visiting schools to educate young people | WY Fire Service | CMBC Schools | All 5 year pupils in Calderdale receive safety information | Apr-07 | Apr-08 | Operational Fire-fighters/ Community Safety Officers |  |
|  | SSC17c (1) | Carrying out 14000 Household Fire and Safety Checks over the next 3 years | WY Fire Service | DWP/CMBC/Voluntary/Community organisations | Quarterly review of progress towards an annual target | Apr-07 | Mar-08 | Operational Firefighters/ Community Safety Officers |  |
|  | SSC17c (2) | Working with other agencies at events such as crucial crew and multi agency interventions | WY Fire Service | Police, CMBC | Establish Todmorden as an alternative site for crucial crew. Support Alcohol Impact course | Apr-07 | Apr-08 | Operational Firefighters/ Community Safety Officers |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Build Respect in communities and reduce anti-social behaviour |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC18 | Maintain in the percentage of repeat victims of reported hate crime |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC18 (1) | Broaden membership of Calderdale Hate Crime Partnership and review structures such as casework panel and 3rd party reporting centres | CMBC | Current members of Hate Crime Partnership | Review completed by December 2007 | Apr-07 | Mar-10 | CMBC and Police staff | CMBC Housing and Community Partnerships Manager |  |
|  | SSC18 (2) | Explore possibility of funding a dedicated officer to support and advise victims | CMBC | Victim Support, Police | Officer appointed by September 2007 | Apr-07 | Mar-10 | LPSA Performance Reward Grant | CMBC Housing and Community Partnerships Manager |  |
|  | SSC18 (3) | Run a 'zero tolerance' publicity campaign to deter potential offenders and reassure victims | CMBC | VCS, Police, local media, other statutory agencies, PH2K | Materials developed by October 2007 | Oct-07 | Mar-10 | LPSA Performance Reward Grant | CMBC Housing and Community Partnerships Manager |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Empower local people to have a greater voice and influence over local decision making and a greater role in public service delivery |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC19 (M) | Increase in the percentage of residents who feel they can influence decisions affecting their local area |  |  |  |  |  |  |  |  |
|  | SSC19a | In Calderdale |  |  |  |  |  |  |  |  |
|  | SSC19b (NTG) | In Mixenden Initiative neighbourhood management area (NE) |  |  |  |  |  |  |  |  |
|  | SSC19c (NTG) | In Ovenden Initiative neighbourhood management area (NMP) |  |  |  |  |  |  |  |  |
|  | SSC19d (NTG) | In Park Community Initiative neighbourhood management area (NE) |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC19 (1) | Research factors most likely to impact on outcome | CMBC | PCT, PH2K, Police | Report to LSP October 2007 | Apr-07 | Oct-07 | Staff time | CMBC Head of Housing and Community Support |  |
|  | SSC19 (2) | Implement refreshed consultation and participation framework incorporating response to Local Government White Paper | CMBC | PCT, PHK2, Police | Report to LSP October 2007 | Apr-07 | Apr-08 | Staff time | CMBC Head of Housing and Community Support |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Empower local people to have a greater voice and influence over local decision making and a greater role in public service delivery |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC20 (M) | Increase in the percentage of people who feel that their local area is a place where people from different backgrounds can get on well together |  |  |  |  |  |  |  |  |
|  | SSC20a | In Calderdale |  |  |  |  |  |  |  |  |
|  | SSC20b (NTG) | In Mixenden Initiative neighbourhood management area (NE) |  |  |  |  |  |  |  |  |
|  | SSC20c (NTG) | In Ovenden Initiative neighbourhood management area (NMP) |  |  |  |  |  |  |  |  |
|  | SSC20d (NTG) | In Park Community Initiative neighbourhood management area (NE) |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC20 (1) | Deliver Community Cohesion Action Plan priorities | CMBC | Schools, PH2K, VCS, Police | Action plan reviewed by Calderdale Forward Board April 2007 | Apr-07 | Mar-10 | LPSA Reward Grant | CMBC Housing and Community Partnerships Manager |  |
|  | SSC20 (2) | Support for community based organisations | CMBC | VCS | Grants programme 2007-10 agreed by March 2007 | Apr-07 | Mar-10 | Community Services Grants | CMBC Community Services Grants |  |
|  | SSC20 (3) | Promotion of volunteering | CMBC | VCS Calderdale Cares | Council response to White Paper | Apr-07 | Mar-10 | Community Services Grants | CMBC Community Services Grants |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Improved quality of life for people in the most disadvantaged neighbourhoods; service providers more responsive to neighbourhood needs; and improved service delivery |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC21 (M) (NTG) | Percentage of residents (in areas receiving this funding) reporting an increase in satisfaction with their neighbourhoods |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  |  |  | TBC |  |  |  |  |  | TBC |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Reduce re-offending (through addressing the using and support needs of offenders) |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC22 (RE09) | Reduce levels of re-offending by increasing the number of those involved in criminal justice interventions provided with suitable and settled accommodation |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC22 (RE09) (1) | Establish Steering Group who will lead the work needed to achieve the target, monitor success and identify and manage potential risk | CMBC | Drug Intervention Programme Team, Probation Services, Benefits Service, Housing Associations, Private Landlords, Housing Support Providers, Police | First meeting of group and terms of reference agreed | Apr-07 | May-07 | Using existing staffing resources | CMBC Housing Access Manager (Supporting People) |  |
|  | SSC22(RE09) (2) | Develop and agree monitoring structures, to ensure consistent and acceptable data on clients being rehoused | CMBC | Drug Intervention Programme Team, Probation Services, Benefits Service, Housing Associations, Private Landlords, Housing Support Providers, Police | Working structures in place and able to be used | Apr-07 | Jun-07 | Using existing staffing resources | CMBC Housing Access Manager (Supporting People ) |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Improved services for victims of domestic violence through targeted schemes |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC23 | Reduction in the re-offending by perpetrators of domestic violence |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC23 (1) | WYPB will initiate Integrated Domestic Abuse Programme work with all new cases made subject to statutory orders imposed on Calderdale in 2007/08. Target 24 completions in 2007/08. Offenders refusing to cooperate with the programme will be returned to Court for re-sentence | W Yorks Probation Service | Police Calderdale Women's Centre MARAC Partners | First phase will be individual work, followed by the group work programme. April 2007. MAPPA/MARC to provide prioritisation info to IDAP tutors in the event waiting list situation for group (after individual work) June 2007. Produce baseline information on re-offending before and after group commencement for last year. June 07. Production of compliance data for IDAP cases June 07 | April 07 June 07 June 07 | Onwards | MAPPA system, MARAC system, IDAP Tutors, Probation Service, Victim Services Unit and probation information | Assistant Chief Officer, Probation Service |  |
|  | SSC23 (2) | Increase the numbers of partners of IDAP attendees directly contacted by Victim Services Unit staff | Probation | Police Calderdale Women's Centre | Produce baseline information for last year, May 07. VSU to offer specific home visit appointments to all partners April 2007 | May 07 April 07 | 01/03/2008 Onwards | Halifax Probation and Information Service staff Progs and information staff Probation VSU | Assistant Chief Officer, Probation Service |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Improved services for victims of domestic violence through targeted schemes |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC24 | Actions against domestic violence (BV225) |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC24(1) | Continue to co-ordinate the Domestic Violence Forum and address issues of funding for provision of support services | CMBC | Police Womens Centre Probation PCT | Audit existing provision | Apr-07 | Oct-07 | DV Co-ordinator time (funded through PRG) | CMBC Community Safety Manager |  |
|  | SSC24(2) | Promote services available to those at risk or suffering from domestic violence | CMBC | Police Womens Centre Probation PCT | Update Directory of Services, include on CD Rom and update website information | Apr-07 | Sep-07 | DV Co-ordinator time (funded through PRG) | CMBC Community Safety Manager |  |
|  | SSC24(3) links to SSC23 | Continue to support and coordinate the Multi Agency Risk Assessment Conference (MARAC) process through developing Partnership admin support for process | CMBC | Police Womens Centre Probation PCT | Appoint Admin Officer | Apr-07 | Jun-07 | PRG funding for Admin Officer) | CMBC Community Safety Manager |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Enrich individual lives, strengthen communities and improve places where people live through culture and sport, including libraries and the historic environment |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC25 | Increase in the take up of cultural opportunities per 1,000 population in Calderdale: |  |  |  |  |  |  |  |  |
|  | SSC25a | Overall |  |  |  |  |  |  |  |  |
|  | SSC25b | Theatre |  |  |  |  |  |  |  |  |
|  | SSC25c | Cinema |  |  |  |  |  |  |  |  |
|  | SSC25d | Museums and art galleries |  |  |  |  |  |  |  |  |
|  | SSC25e | Libraries |  |  |  |  |  |  |  |  |
|  | SSC25f | Sports facilities |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC25c | Audience Development Programme | CMBC |  | Broaden artistic programme at Victoria Theatre and Hebden. Bridge Picture House. | Apr-06 | Dec-08 | Production Budget | CMBC Theatres Manager |  |
|  | SSC25e | Audience Development Programme | CMBC |  | Membership drive for Libraries. | Mar-07 | Mar-08 | Rev marketing budget | CMBC Libraries Operations and Customer Service Manager |  |
|  | SSC25d | Audience Development Programme | CMBC |  | Learning Access Programme for Schools, Museums and Galleries | Jul-07 | Jun-09 | Existing Revenue budget | CMBC Principal Officer (Museums and Galleries - Administration) |  |
|  | SSC25f(1) | Develop a programme of fitness and exercise classes | CMBC | West Yorkshire Sport, Ovenden, Mixenden and Park Community Initiatives | One new Programme in each SOA per year | Apr-07 | Mar-10 | Staff time, facility hire, equipment | CMBC Activity and Community Development Manager |  |
|  | SSC25F(2) | Market the physical activity message | CMBC | Calderdale Activity Network | Set up a dedicated website. Produce publicity material i.e. leaflets banners etc | Apr-08 | Mar-10 | Officer time, website design, publicity materials | CMBC Activity and Community Development Manager |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Enrich individual lives, strengthen communities and improve places where people live through culture and sport, including libraries and the historic environment |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC26 | Increase overall satisfaction with cultural offer in Calderdale: |  |  |  |  |  |  |  |  |
|  |  | Theatre |  |  |  |  |  |  |  |  |
|  |  | Museums |  |  |  |  |  |  |  |  |
|  |  | Libraries |  |  |  |  |  |  |  |  |
|  |  | Sport facilities |  |  |  |  |  |  |  |  |
|  |  | Parks and open spaces |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC26(1) | Complete current phase of the Service Asset Management Plan - building improvements | CMBC |  | 1) Sept 2007 Refurbish Victoria Theatre dressing rooms. 2) Dec 2007 New Shelf Library 3) Jan 2008 New Customer facilities at Bankfield Museum. 4) March 2008 Refurbishment of Brighouse Art Gallery and Library. 5) Apr 2008 New stalls seating at Victoria Theatre. 6) Jan 2009 Refurbishment and extension of Hebden Bridge Library. | Apr-07 | Mar-09 | Capital funds are allocated to all milestones projects | CMBC Head of Libraries, Museums and Arts |  |
|  | SSC26 (a) | Develop facility improvement plans based on the findings of existing user and lapsed user surveys | CMBC | Voluntary Sector clubs/organisations | Action plans developed. Repeat survey carried out and analysed | Apr-07 | Mar-10 | Existing | CMBC Activity and Community Development Manager |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | To strengthen the Voluntary and Community Sector's (VCS) role in strategic decision making and in the planning and delivery of public services |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC27 | Increase in the number of Voluntary Community Sector (VCS) groups who are members of Calderdale Forum or the Community Network |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC27 | Publicise and promote CCF within the VCS | CCF | VCS | Formal membership established | Jun-07 |  | 100 CCF / NDO hours | CCF Chair |  |
|  |  |  |  |  | Yearly membership count | Sep-07 | Sep-09 | 200 CCF / NDO hours p.a. | CCF Chair |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | To strengthen the Voluntary and Community Sector's (VCS) role in strategic decision making and in the planning and delivery of public services |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC28 | Increase in the percentage of VCS groups and organisations confirming growth in activity in terms of: |  |  |  |  |  |  |  |  |
|  | SSC28a | Financial stability |  |  |  |  |  |  |  |  |
|  | SSC28b | Volunteering |  |  |  |  |  |  |  |  |
|  | SSC28c | Support volunteering good practice |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC28a(1) | Training programmes | VAC | WYCAS, Fit4Funding, VCS organisations | Quarterly programmes | Apr-07 | Mar-10 | 100 hours | VAC Chief Officer |  |
|  | SSC28a (2) | One-to-one organisational development support | VAC | VCS organisations |  | Apr-07 | Mar-10 | 200 days | VAC Chief Officer |  |
|  | SSC28a (3) | Ad hoc events | VAC | VCS organisations and sub regional VCS organisations | Annual Funding Fair | As above | As above | 100 hours | VAC Chief Officer |  |
|  | SSC28b (1) | Volunteer Supervisors Network meetings | VAC | VCS organisations who involve volunteers | 5 meetings per year | As above | As above | 40 hours | VAC Chief Officer |  |
|  | SSC28b (2) | See SSC 30 | VAC | VCS organisations who involve volunteers |  |  |  |  | VAC Chief Officer |  |
|  | SSC28c (1) | Volunteer Supervisors Network meetings | VAC | VCS organisations who involve volunteers | 5 meetings per year | As above | As above | 40 hours | VAC Chief Officer |  |
|  | SSC28c (2) | One-to-one support sessions for volunteer co-ordinators | VAC | VCS organisations who involve volunteers |  | As above | As above | 100 hours | VAC Chief Officer |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | To strengthen the Voluntary and Community Sector's (VCS) role in strategic decision making and in the planning and delivery of public services |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC29 | Satisfaction with influence of VCS in: |  |  |  |  |  |  |  |  |
|  | SSC29a | Planning of public sector services |  |  |  |  |  |  |  |  |
|  | SSC29b | Delivery of public sector services |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC29(1) | Undertake research to demonstrate influence of VCS in planning/delivery of public sector services | CCF | VCS | Annual research report | Sep-07 | Dec-09 | 250 CCF/ NDO hours p.a. | CCF Chair |  |
|  | SSC29(2) | Engagement through networks and Forum events to demonstrate opportunities for VCS influence in planning/delivery of public sector services | CCF | VCS | Yearly survey of satisfaction evidencing ongoing increase | Dec-07 | Dec-09 | 200 CCF / NDO hours p.a. | CCF Chair |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Safer and Stronger Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | To strengthen the Voluntary and Community Sector's (VCS) role in strategic decision making and in the planning and delivery of public services |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | SSC30 (M) | Increase in the number of people recorded as, or reporting that, they have engaged in formal volunteering on an average of at least two hours per week over the past year |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | SSC30 (1) | Events during Volunteers Week (First week of June) | VAC | VCS organisations that involve volunteers | Volunteers Week celebration event | Apr-07 | Mar-10 | 100 hours | VAC Chief Officer |  |
|  | SSC30 (2) | Volunteer Bureau Facilities | VAC | VCS organisations that involve volunteers; General public | Five drop-ins per week | As above | As above | 780 hours | VAC Chief Officer |  |
|  | SSC30 (3) | Bi-monthly Volunteer Survey | VAC | Volunteers who have registered with VAC | Survey results x 6 | As above | As above | 50 hours | VAC Chief Officer |  |
|  | SSC30 (4) | Paper based Volunteer Directory | VAC | VCS organisations/ general public | Three directories per year | As above | As above | 100 hours | VAC Chief Officer |  |
|  | SSC30 (5) | Web based volunteer directory | VAC | VCS organisations who involve volunteers/ general public | Weekly updates | As above | As above | 520 hours | VAC Chief Officer |  |
|  | SSC30 (6) | VAC/ CCF/ CMBC Survey | VAC | CCF, CMBC, VCS organisations | Annual Survey | Jan-08 | Mar-10 | 200 hours | VAC Chief Officer |  |

Calderdale LAA Delivery Plan

Healthier Communities

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Healthier Communities |  |  |  |  |  |  |  |  |
|  | Outcome | Improved Health and reduced health inequalities |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |
|  | HC01(M) (NTG) | Reduce health inequalities within local authority area, by narrowing the gap in all-age, all-cause mortality |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |
|  | HC01(M) 01 (NTG) | Develop action plans with those practices, which have highest proportion of patients living in 20% most disadvantaged areas. | Calderdale PCT | general practice | 1) identify practices; 2) identify qof outcomes in CHD and diabetes domains; 3) establish at risk registers; 4) agree lifestyle pathways | 1) March 07; 2) April 07; 3) May 07; 4) June 07 | Jun-07 |  | PCT Assistant Director of Public Health |
|  | HC01(M) 02 (NTG) | Develop agreed action plans on improving health within the workplace as part of the health improvement specification | Calderdale PCT | local employers Businesses | 1) Action plans agreed; 2) Plans implemented | May-07 | Mar-09 |  | PCT Senior Health Promotion Specialist |
|  | HC01(M) 03 (NTG) | Specific health improvement action plans in disadvantaged areas as part of health improvement specification | Calderdale PCT | Provider services, community and voluntary agencies | 1) Specification agreed; 2) Action plans with partners in defined areas | Mar-07 | Apr-07 |  | PCT Assistant Director of Public Health |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Healthier Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Reduce premature mortality rates and reduce inequalities in premature mortality rates between wards / neighbourhoods with a particular focus on reducing the risk factors for heart disease, stroke and related diseases (CVD) (smoking, diet and physical activity) |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | HC02 (RE10) (NTG) | Increase in the number of 4-week smoking quitters. |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | HC02 (RE10) (NTG) 1 | Implement a locally enhanced service agreement with GP practices in Calderdale to ensure quality of services remain equal across the borough | Calderdale PCT | GP practices | LES agreed with 95% GP practices | Apr-07 |  | £ payment for return of Department of Health monitoring forms | PCT Smoking Cessation Service Coordinator |  |
|  | HC02 (RE10) (NTG) 2 | Train local authority frontline staff in brief intervention skills for smoking cessation | Calderdale PCT | CMBC | 50% (2007), 75% (2008), 90% (2009) frontline staff trained in brief intervention | Apr-07 |  | Band 6 x 20 hrs training time (££) Band 3x5hrs admin time. Band 2 10hrs prep time resources free from DH | PCT Smoking Cessation Service Coordinator |  |
|  | HC02 (RE10) (NTG) 3 | Agree health improvement specification with Community provider including additional smoking cessation targets. Deliver additional stop smoking services in areas with high smoking prevalence (ie: above 30%) | Calderdale PCT | Primary care provider services, voluntary sector pharmacists | Increase staff levels and access & choice for smokers by providing clinics in more diverse areas | Apr-07 |  | Band 6x100 hrs training time; Band 3x10hrs admin time. Band 2x20hrs prep time Paper resources free from DH | PCT Smoking Cessation Service Coordinator |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Healthier Communities |  |  |  |  |  |  |  |  |
|  | Outcome | Reduce premature mortality rates and reduce inequalities in premature mortality rates between wards / neighbourhoods with a particular focus on reducing the risk factors for heart disease, stroke and related diseases (CVD) (smoking, diet and physical activity) |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |
|  | HC03 | Reduction in smoking at delivery. |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |
|  | HC03 (1) | Train all midwives in Calderdale (107) in brief intervention smoking skills | Calderdale PCT | CHT/ Sure Start WYSSS | Decrease numbers of pregnant women smoking by 2% year on year | Apr-07 |  | Employ a Band 6 WTE (£21k-30.500k) on secondment to deliver training to midwives and build networks, Band 2 admin support | PCT Smoking Cessation Service Coordinator |
|  | HCO3 (2) | Increase awareness the effects second hand smoke can have on babies and children’s health | Calderdale PCT | CMBC, Sure Start | Increase numbers of homes signing up to the smokefree home pledge-2007/08-500, 2008/09-1000 | Apr-07 | 2009 | Employ a Band 4 WTE (£14k-£19k) to deliver training and raise awareness | PCT Smoking Cessation Service Coordinator |
|  | HC03 (3) | Health improvement specification with CHT and community provider to includes targets for pregnancy and smoking | Calderdale PCT | CHT/ PCT provider services | Specification produced performance management arrangements and reporting levels agreed | Apr-07 | Apr-07 |  | PCT Assistant Director of Public Health |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Healthier Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Reduce premature mortality rates and reduce inequalities in premature mortality rates between wards / neighbourhoods with a particular focus on reducing the risk factors for heart disease, stroke and related diseases (CVD) (smoking, diet and physical activity) |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | HC04 (RE11) | Increase in the number of recorded obese individual losing weight through a personalised weight management programme |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | HC04 (1) | Develop community weight management service specification | Calderdale PCT | LAA Delivery Group Member Organisations | 1. Service specification agreed by PCT and partners. 2.Targets and incentives agreed. | Mar-07 | Mar-07 | Staff hours | PCT Health Promotion Dietician / PCT Assistant Director of Public Health |  |
|  | HC04 (2) | Develop and implement database and robust monitoring system for data collection | Calderdale PCT | LAA Delivery Group Member Organisations | 1. Database, monitoring, referral and return forms developed. 2. Pathway identified and agreed. 3. Robust monitoring system implemented. | Mar-07 | Apr-07 | Staff hours. Budget to develop database. Recruit admin. | PCT Health Promotion Dietician / PCT Assistant Director of Public Health |  |
|  | HC04 (3) | Recruit, train and establish a network of Open College Network Accredited community weight management course leaders | Calderdale PCT | LAA Delivery Group Member Organisations | 1. Map current local weight management activity. 2. Recruit course leaders from a variety of settings. 3. Train all leaders in monitoring system, each leader identified as responsible for reporting. 4. Train all leaders in accredited weight management course (OCN Units 1,4 and 5). 5. Network established. 6. Regular training and update meetings held. | Apr-07 | Apr-10 | Staff hours. OCN accreditation. Equipment/ resources provided. | PCT Health Promotion Dietician / PCT Assistant Director of Public Health |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Healthier Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Reduce premature mortality rates and reduce inequalities in premature mortality rates between wards / neighbourhoods with a particular focus on reducing the risk factors for heart disease, stroke and related diseases (CVD) (smoking, diet and physical activity) |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | HC05 | Prevalence of obesity among primary school aged children |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | HC05 (1) | Establish a baseline of prevalence of obesity among primary school age children | Calderdale PCT | YHPHO | 1) Upload the data collected 2007 2) Set targets based on the baseline 3) Annual measurement or Y Reception and Y 6 children | 1) Jan 07; 2) Mar 07; 3) Sep 07/08/09 | 1) Mar 07 2) Mar 07 3) Dec 07/08/09 |  | PCT Public Health Manager |  |
|  | HC05 (2) | Implement school meals agenda | Calderdale PCT | CMBC (Healthy Schools, School Meals Group) | 1) Ensure all schools achieve national food-based standards. 2) All schools catering providers to have nutritionally analysed menus) | 1) April 07 2) April 07 | 1. Dec 07 2a.Sept 08 (primary) 2b. Sept 09 (secondary schools) | 1) Community Nutrition Assistant and Public Health Specialist staff time. 2) Nutritional Analysis Programme | PCT Health Promotion Dietician |  |
|  | HC05 (3) | Partnership agreement and implementation of childhood obesity strategy | Calderdale PCT | CMBC, community providers, Community and voluntary groups, Foundation trust | 1) Agree obesity strategy. 2) ensure NICE guidance is implemented within the appropriate settings | 1) April 07; 2) April 07 | 1) May 07; 2) July07 |  | PCT Public Health Manager |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Healthier Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Reduce premature mortality rates and reduce inequalities in premature mortality rates between wards / neighbourhoods with a particular focus on reducing the risk factors for heart disease, stroke and related diseases (CVD) (smoking, diet and physical activity) |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | HC06 (NTG) | Increase in breastfeeding maintenance rates: Narrow the gap between % of women in the most deprived quintile breastfeeding at first visit and District average |  |  |  |  |  |  |  |  |
|  | HC06a | Calderdale average |  |  |  |  |  |  |  |  |
|  | HC06b | Most deprived quintile |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  |  | Improvement in universal breast feeding support through increased antenatal support (as described in Child Health promotion programme) and development and implementation of a Post natal pathway - multiagency | Calderdale PCT | CHFT | Information to HV's re antenatal aspect of CHPP; Activity monitoring of antenatal contacts; Establish development group for post natal ICP; Develop ICP; Implement ICP, including training | Mar-07 | Jun-07 | Health Visitor, Midwife and Nursery nurse resource | Community Matron (Child and Family Services) |  |
|  |  | Introduce pilot work in key areas (N Halifax) this may include peer breast feeding supporters, baby café | Calderdale PCT | Sure Start Neighbourhood management community and voluntary groups | Establish steering group; Scope potential options; engage with community; agree projects and evaluation methods; implement, evaluate, share lessons | Apr-07 | Oct-07 | HV/ NN within locality / existing locality services / intelligence | Community Matron (Child and Family Services) |  |
|  |  | Action on improving Breastfeeding rates will form part of the health improvement specification for the NHS community provider | Calderdale PCT |  | Specification produced March; performance management arrangements and reporting levels agreed | Mar-07 | Apr-07 | PCT | PCT Assistant Director of Public Health |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Healthier Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Reduce premature mortality rates and reduce inequalities in premature mortality rates between wards / neighbourhoods with a particular focus on reducing the risk factors for heart disease, stroke and related diseases (CVD) (smoking, diet and physical activity) |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | HC07 | Reduction in people looking at sedentary lifestyle through an increase in the % of people taking part in 1x30 minutes of moderate intensity physical activity per week |  |  |  |  |  |  |  |  |
|  | HC07a | In Calderdale |  |  |  |  |  |  |  |  |
|  | HC07b (NTG) | In Ovenden, Mixenden and Park neighbourhood management areas |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | HC07, HC07a, HC07b | Roll out the Better Health @ Work initiative across Calderdale, specifically targeting the Ovenden, Mixenden & Park neighbourhood management areas. Offering support, advice and practical opportunities to organisations within Calderdale to enable them to promote healthy lifestyle issues to their staff (such as physical activity, stop smoking support, healthy eating and so on), as well as providing expertise to ensure that the working environment and culture is a healthy one. | Calderdale PCT | CMBC, HSE (Better Health @ Work steering group) | 1. Recruit and train X workplace health project workers. 2. X businesses engaged in the initiative 3. Network of "Workplace Champions established" | Apr-07 | Apr-10 | Staff time (limited) | PCT Senior Health Promotion Specialist |  |
|  | HC07b | Pilot the Lifestyles Pathway within Primary Care settings in Ovenden, Mixenden and Park neighbourhood management areas (providing support, motivation and a variety of appropriate lifestyle opportunities as part of a general population prevention approach) | Calderdale PCT | CMBC, Primary Healthcare Professionals, West Central Halifax Healthy Living Partnership, Ovenden, Mixenden & Park Neighbourhood Management projects | 1) Recruit, train & support a minimum of 1 "Lifestyle Advisor" per GP Practice. 2) Develop a comprehensive range of lifestyle opportunities (e.g. walking groups, community/facility based activities, ped-o-meters, weight management sessions, brief interventions and support) | 01/05/2007 | Apr-10 | Staff time (limited) | PCT Senior Health Promotion Specialist |  |
|  | HC07, HC07a, HC07b | District-wide roll-out of the Lifestyles Pathway (providing support, motivation and a variety of appropriate lifestyle opportunities as part of a general population prevention approach) | Calderdale PCT | CMBC, Primary Healthcare Professionals, West Central Halifax Healthy Living Partnership, Ovenden, Mixenden & Park Neighbourhood Management projects | 1) Recruit, train & support a minimum of 1 "Lifestyle Advisor" per GP Practice. 2) Develop a comprehensive range of lifestyle opportunities (e.g. walking groups, community/facility based activities, ped-o-meters, weight management sessions, brief interventions and support) 3) Recruit, train and support members of the local community as "Lifestyle Advisors" based within community settings 4) Create a "Lifestyles Advisor" network to share good practice, offer support, update on knowledge, skills and so on. | Apr-08 | Apr-10 | Staff time (limited) | ?? PCT Senior Health Promotion Specialist |  |
|  |  | As part of overall physical activity strategy a 45+ physical activity plan agreed | ? | CMBC, Primary Healthcare, age concern | 1) Plan developed 2) Commitment from partners | Apr-07 |  | Judy Stewart, PCT Public Health Specialist (Older People) | ? |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Healthier Communities |  |  |  |  |  |  |  |  |  |
|  | Outcome | Oral Health |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | HC08 | Reduce levels of decayed missing and filled (dmf) teeth in children under 5 |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | HC08 (1) | Continue with 'Brushing for Life' scheme, at baby developmental health checks with PCT funding | Calderdale PCT | Health Visitors, Oral Health Promotion | Evaluate distribution and contact with parent/carer. Training updates | current | ongoing | HVs Nursery Nurses | Consultant in Dental Public Health / Oral Health Promotion Officer |  |
|  | HC08 (2) | Cute Fruit Plus Dental Health Award (Healthy Eating Policy) in early years settings in disadvantaged wards | Calderdale PCT | Surestart, CMBC, Oral Health Promotion | Training to staff and carers in Nurseries etc. Extend to Calderdale as programme rolls out | current | ongoing | Staff in Nurseries, limited PCT staff time | Oral Health Promotion Officer / Sure Start WCHx Oral Health Promoter |  |
|  | HC08 (3) | Toothbrushing programme - early years settings in disadvantaged wards e.g. Park Ward | Calderdale PCT | CMBC, Nursery staff | Identify settings, steering group to set up for implementation. Target other wards in year 2 | Sep-07 | Sep-10 | Utilise existing staff/ volunteers. Purchase materials | Consultant in Dental Public Health |  |
|  | HC08 (4) | Fluoride varnish on teeth (3-5yr. olds) in Park, Ovenden, Town wards - to build up incrementally | Calderdale PCT | Dental staff (GDS / CDS) | Monitor activity data. Dental health survey in 2009/10 | Sep-07 | Sep-10 | Limited time of dentists. Materials needed | Consultant in Dental Public Health / PCT Head of Services Primary Care (Locality Manager) |  |

Calderdale LAA Delivery Plan

Older People

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Older People |  |  |  |  |  |  |  |  |  |
|  | Outcome | Improved Health |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | OP01 (RE12) | Reduction in the number of emergency unscheduled bed days occupied by a person aged 65 and over |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | OP01(1) | Development of new joint community-based service models for IV Antibiotics, COPD and Heart Failure to prevent or divert patient from hospital | Calderdale PCT | CMBC (SSD), C&H NHS Trust, Age Concern | (a) New community IV Antibiotic service in place; (b) New community Pulmonary Rehabilitation service in place; (c) New cardiac Rehabilitation service in place | (a) 1-Apr-07; (b) 01-Jun-07; (c) 1-Apr-07 | (a) 01-Jul-07; (b) 01-Jun-08; (c) 01-Jul-08 | Commissioning staff in place (1.0 wte). Resources committed via savings made in-year on the C&HT Contract for non-elective activity. ;(a) Value of community IVF Service is £308k pa. (b) Value of COPD activity £323kpa (c) Value of HF activity £228k | PCT Manager (Medical and Elderly Redesign Programme) |  |
|  | OP01(2) | Development of new patient flow models to ensure that patients receive timely and effective transfer of care from hospital into community-based services | Calderdale PCT | CMBC (SSD), C&H NHS Trust, Age Concern | (a) Development of MAU Rapid Assessment Service at CRH, inc new MAU consultant (b) Piloting of new model transfer of care and patient flow model at CRH, inc introduction of standardise joint MDT working (c) Joint tracking of all patients waiting 7plus days for discharge (d) Pilot new Supported Discharge Project | (a) 01-Jul-07; (b) 01-Apr-07; (c) 01-Apr-07; (d) 01-Jun-07 | (a) 01-Apr-08; (b) 01-Nov-07; (c) 01-Dec-07; (d) 01-Jul-09 | (a) Resources put into CRH contract for 07/08 = £93k (b) Staff time provided by PCT and CHT - 0.5 wte (c) Staff time provided by PCT and CHT 0.2 wte (d) £68k POPPs Funding | PCT Manager (Medical and Elderly Redesign Programme) |  |
|  | OP01(3) | Development of new integrated models for delivery of rehabilitation services | Calderdale PCT | CMBC (SSD), C&H NHS Trust | (a) New joint rehabilitation model (inc community-based beds) in place and commissioned; (b) New Falls Practitioner recruited and modelling completed (c) New Falls Assistant Practitioners recruited and trained; (d) New staff trained to undertake comprehensive falls assessments | (a) 01-Apr-07; (b) 01-Apr-07; (c) 01-Aug-07; (d) 01-Jul-07 | (a) 01-Apr-08; (b) 01-Nov-07; (c) 01-Dec-07; (d) 01-Dec-07 | (a) 20k 1.0 wte Business Change Manager (Rehab) for 6 month by PCT (b) 20k 0.5 wte Business Change Manager (falls) for 6 months then 1.0 wte substantive roll @ 42k by PCT (c) 2.0 wte falls assistants at £55k - POPPs Funding. (d)20 Band 5/6 staff trained - costs to be included within current staff costs by PCT and CHT | PCT Manager (Medical and Elderly Redesign Programme) |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Older People |  |  |  |  |  |  |  |  |  |
|  | Outcome | Improved Quality of Life |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | OP02 | Improvements in the levels of satisfaction of people aged 65 and over using home services |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | OP02 (1) | Home Care Commissioning Strategy and retender of Home Care service. | CMBC Adult services | Independent sector providers | Finalise commissioning strategy and tender services. | Mar-07 | May-08 | Existing budget | CMBC Service Manager - Home Care |  |
|  | OPO2 (2) | Improve co-ordination of complaints monitoring. | CMBC Adult services | Independent sector providers | Development of commissioning section in Adult services | Mar-07 | Apr-08 | Existing budget | CMBC Head of Adult Services |  |
|  | OPO2 (3) | Implement flexible staffing solutions to meet service demands and reduce absence. | CMBC Adult services | PCT Housing Providers | Reduce time taken to recruit staff, improve sickness procedure | Jun-07 | Jun-09 | Existing budget | CMBC Service Manager - Home Care |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Older People |  |  |  |  |  |  |  |  |  |
|  | Outcome | Improved Quality of Life |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | OP03 | The number of private sector properties occupied by vulnerable households brought up to decent home standards with assistance from the local authority (Non-RSL) in each year |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | OP03 (1) | Identify private sector properties that fail the decent homes standard occupied by vulnerable households | CMBC Home Improvement Service | Older Peoples groups, HIA, HET, Env Health | Private Sector Stock Condition Survey. Data from PCT, Env. Health & Adult Services | April-07 | August-07 | Approx. £60K.RHB funds. PCT informatics dept. Staff time | CMBC Private Sector Housing Manager |  |
|  | OP03 (2) | Promote the sources of financial help available to householders to assist them to make improvements | CMBC Home Improvement Service | Older Peoples groups, HIA, HET, Env Health | Article in local newspaper, presentations to groups of older people and key agencies | April-07 | Mar-07 | Staff time | CMBC Private Sector Housing Manager |  |
|  | OP03 (3) | Assist households to prioritise and carry out works to their homes in order to achieve decent home standards | CMBC Home Improvement Service | Older Peoples groups, HIA, HET, Env Health | Inspect houses, make information available, and make finance available. | April-07 | Mar-10 | RHB funds, private finance, Staff time | CMBC Private Sector Housing Manager |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Older People |  |  |  |  |  |  |  |  |  |
|  | Outcome | Improved Quality of Life |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | OP04 | Increase in the % of assessments of older people completed within 4 weeks |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | OPO4 (1) | Implement flexible staffing solutions to meet service demands and reduce absence. | CMBC Adult services | N/A | Reduce time taken to recruit staff, improve sickness procedure | Jun-07 | Jun-08 | Existing budget | CMBC Chief Operations Manager (Adult Services) |  |
|  | OPO4 (2) | Greater locality integration. | CMBC Adult services | PCT NHS SWYMHT | 1) Develop integration model; 2) Appoint Project Officer | 1) Mar 07; 2) July07 | 1) June 07; 2) Jan 09 | POPPS funding | CMBC Chief Operations Manager (Adult Services) |  |
|  | OPO4 (5) | Monitoring and tracking assessments | CMBC Adult services | N/A | Improve management information systems for Team managers | Mar-07 | On-going | Existing budget | CMBC Chief Operations Manager (Adult Services) |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Older People |  |  |  |  |  |  |  |  |  |
|  | Outcome | Make a positive contribution |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | OP05a | Increase in the number of older people using local facilities |  |  |  |  |  |  |  |  |
|  | OP05a | Increase in the number of older people volunteering and participating more in the community generally. |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Older People |  |  |  |  |  |  |  |  |  |
|  | Outcome | Make a positive contribution |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | OP06 | Reduction in the percentage of 50+ people inactive in the labour market |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | OP06 (1) | To deliver Welfare Reform programmes for over 50's | Jobcentre Plus | Contracted providers | 1) Deliver ND50+ programme; 2) Implementation of Pathways to Work | 1) April 07 2) October 07 | 1) March 2010; 2) March 2010 | 1.0 Adviser resource Approx £3 million for West Yorkshire | JCP Business Devt Manager |  |
|  | OP06 (2) | Marketing strategy developed with partners. | Jobcentre Plus | Public, Private, Vol/ Comm sectors | 1) Key partners identified 2) Strategy produced & implemented 3) Evaluate and review | 1) April 07; 2) June 07; 3) March 08 | 1) Ongoing 2) Ongoing 3) March 08 | Resource contribution in kind from partners | JCP Business Devt Manager |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Older People |  |  |  |  |  |  |  |  |  |
|  | Outcome | Choice and Control |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | OP07a | Increase in the number of older people supported via Supporting People services |  |  |  |  |  |  |  |  |
|  | OP07b | Reduction in the number of people aged 65 and over being admitted to residential / nursing care |  |  |  |  |  |  |  |  |
|  | OP07c | Availability of Extra Care Housing Tenancies provided |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | OP07a | Increase in the number of older people supported via Supporting People services | CMBC | CMBC Adult Social Services, PH2K, Anchor Trust, English Churches Housing Group, Hanover Housing Association, Headrow HA, Housing 21, Jephson HA, Places for People, Sanctuary HA, Connect HA, Trustees - Finn Gledhills and Yorkshire Community Housing Ltd | April 2007 - new Home Improvement and Small Repairs Service contract commences (ensure new service is publicised and reaches new customers, particularly hard to reach clients) April 2009 - new extra care scheme in place and development of floating support for older people (be an active member of the project group set up to develop the new extra care scheme and work in partnership with all Housing Associations to develop floating support services - via involvement on the Sheltered Housing Sub Group) | Apr-07 | Mar-10 | Current resources spent on older people from the Supporting People budget is forecasted to be £939,589 | CMBC Housing Access Manager (Supporting People) |  |
|  | OPO7b1 | Increased use of Telecare technology. | CMBC Adult services | Calderdale PCT, SWYMHT | Implement Telecare infrastructure | Mar-07 | Mar-08 | Preventative Technology Grant | CMBC Chief Operations Manager (Adult Services) |  |
|  | OPO7b2 | Increased link to Direct Payments | CMBC Adult services | Voluntary sector | Targeting setting for locality teams. Review policies. | Mar-07 | Apr-08 | Existing budgets | CMBC Chief Operations Manager (Adult Services) |  |
|  | OPO7b3 | Development of integrated care plans through Single Assessment Process | CMBC Adult services | PCT SWYMHT | Introduction of Single Assessment and electronic data sharing | Apr-07 | Apr-08 | Existing budgets | CMBC Chief Operations Manager (Adult Services) |  |
|  | OP07c1 | a) Strategic meeting between Adult Social Services, Planning Services and PH2K to discuss Planning Officers requirements | PH2K | CMBC Adult Social Services, Housing Services, Calderdale PCT, South West Yorkshire Mental Health Trust, Planning Services, Recreation, Sport and Streetscene Services, Older Person's representatives, Carer representatives and Southdale Homes | Obtain planning approval for Melrose Court scheme | Jun-07 | Aug-07 | Using existing staffing resources | PH2K Head of Sheltered Services |  |
|  | OP07c2 | b) Prepare bid and liase with Housing Corporation and Housing Services re. Capital funding (including slippage opportunities) | PH2K | CMBC Adult Social Services, Housing Services, Calderdale PCT, South West Yorkshire Mental Health Trust, Planning Services, Recreation, Sport and Streetscene Services, Older Person's representatives, Carer representatives and Southdale Homes | Gain capital funding for the scheme (via the Housing Corporation bidding round - 2008-11) | Jun-07 | Apr-08 | Using existing staffing resources | PH2K Head of Sheltered Services |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Older People |  |  |  |  |  |  |  |  |  |
|  | Outcome | Choice and Control |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | OP08 (RE13) | Adults and older people receiving direct payments at 31 March per 100,000 population aged 18 or over |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | OPO8 (1) | Promoting DP as widely as possible to service users, carers and staff. | CMBC Adult Services | VCS Groups | All key groups seen. Publicity created and circulated. | Apr-07 | Jun-07 | Current staff. Pump priming money. | CMBC Community Manager (Older People and Physical Disabilities) |  |
|  | OPO8 (2) | Expand choice of services and ease with which these can be accessed. | CMBC Adult Services | Independent Sector + PCT | Cabinet Report April 07 Implement new service options | Feb-07 | Jun-07 | Additional budget (earmarked) | CMBC Community Manager (Older People and Physical Disabilities) |  |
|  | OPO8 (3) | Target low take up groups inc. mental health and BME. | CMBC Adult Services | SWYMHT | Presentation to MH managers/staff. Campaign via CEW | Mar-07 | Sep-07 | Current staff. | CMBC Community Manager (Older People and Physical Disabilities) |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Older People |  |  |  |  |  |  |  |  |  |
|  | Outcome | Economic Wellbeing |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | OP09a | Increased level of take up of key benefits amongst older people (60+) |  |  |  |  |  |  |  |  |
|  | OP09b (NTG) | Narrow the gap in level of benefit take up amongst older people (60+) in the district |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | OP09a (1) | Obtain confirmation in writing from all partners that common processes are used when providing assistance to clients in claiming benefits and allowances. | CMBC Benefits Service | DWP LPS Calderdale -AC, CAB, DART | When all partners have formerly confirmed there is a common approach to providing appropriate assistance to clients | During March 2007 | End of March 2007 | CMBC staff time | CMBC Chief Benefits Officer |  |
|  | OP09a (2) | Consider new ways of promoting benefit/allowances take up. | CMBC Benefits Service | DWP LPS Calderdale -AC, CAB, DART | Establishing and agreeing if there are any new ways to promote increased take up. | Beginning of April 2007 | End of April 2007 | Meeting time of representatives from each partner agency | CMBC Chief Benefits Officer |  |
|  | OP09a (3) | Set up monitoring arrangement for establishing level of individual benefits take up to confirm whether or not target levels are being achieved. | CMBC Benefits Service | DWP LPS | Each quarterly period within each financial year | 1st April in each FY commencing 2007/08 | 31st March in each FY end 2009/10 | CMBC & LPS staff time | CMBC Chief Benefits Officer |  |
|  | OP09b (3) | Collect and analyse data to be used for addressing indicator requirements. | CMBC Benefits Service | DWP LPS Calderdale -AC, CAB, DART | To be completed by end of June 2007 | 1st April 2007 | 30th June 2007 | CMBC & LPS staff time | CMBC Chief Benefits Officer |  |

| ### Calderdale LAA Delivery Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Block - Older People |  |  |  |  |  |  |  |  |  |
|  | Outcome | Economic Wellbeing |  |  |  |  |  |  |  |  |
|  | Indicators |  |  |  |  |  |  |  |  |  |
|  | Ref | Description |  |  |  |  |  |  |  |  |
|  | OP10 (RE15) | Number of vulnerable households with affordable warmth measures are installed |  |  |  |  |  |  |  |  |
|  | Actions |  |  |  |  |  |  |  |  |  |
|  | Ref | Description | Lead Agency | Partners | Key Milestones | Start Date | Finish Date | Resources available | Lead Officer |  |
|  | OP10 (RE15) (1) | Increase Staff resources of the Housing Energy Team (HET) | CMBC HET | PCT, Adult Services, Housing | Recruitment, Induction, training & retention of staff | Mar-07 | Mar-10 | LAA Pump priming funds approx 22K/year | CMBC Private Sector Housing Manager |  |
|  | OP10 (RE15) (2) | Identify areas of greatest need by analysis of research data | CMBC Housing | PCT, HET, Adult Services | Private Sector Stock Condition Survey. Map excess winter deaths & cold related conditions | Apr-07 | Aug-07 | Approx. £60K RHB funds. PCT informatics dept. Staff time | CMBC Private Sector Housing Manager |  |
|  | OP10 (RE15) (3) | 4 Key aims of the Affordable Warmth Strategy Review 2007-10 | CMBC Housing | Calderdale Affordable Warmth Partnership | Achieve sign-up of key agencies to the strategy review. Achieve main tasks within strategy review. | Mar-07 | Mar-10 | LAA pump priming funds £1500/year. Key agency staff time. Grant funds. | CMBC Private Sector Housing Manager |  |

Calderdale LAA Delivery Plan

Children and Young People

CHILDREN AND YOUNG PEOPLE’S PLAN 2007 – 2010

EVERYONE DIFFERENT: EVERYONE MATTERS

VERSION 11 – 5 MARCH 2007

| 1. Being Healthy |  |  |  |  |  | Lead Officer Head of Children’s Services (PCT) |
| --- | --- | --- | --- | --- | --- | --- |
| To achieve our priority outcomes |  |  |  |  |  |  |
| Measures | 2006/07 Actual | Targets |  |  | Linkages with other plans etc. |  |
|  |  | 2007/08 | 2008/09 | 2009/10 |  |  |
| CYPP BH1: Teenage pregnancy: the rate of conceptions among girls aged under 18 resident in the area, per 1,000 females 15-17 resident in the area. | 39.7 (2006-7 target) 43 (2004 data) | 36.7 | 33.9 | 31.3 | Futures Plan 2006/09 Corporate Plan 2006/09 CMBC Children and Young People’s Services Directorate Plan 2006 – 09 (CYPS Plan) Teenage Pregnancy Strategy Sexual Health and Relationship Strategy and Action Plan LAA 2007 – 10 (CYP) |  |
| CYPP BH2: The rate of conceptions among girls under 18 resident in North Halifax per 1000 females 15-17 in the area. | 82 (2001-3 data) | 64.6 (2004-6 data) | 60 (2005-7 data) | 55.1 (2006-8 data) | LAA 2007 – 10 (CYP) |  |
| CYPP BH3: Reduce health inequalities : Infant mortality rate per thousand | 5.52 | 6.5 | 6.4 | 6.3 | Futures Plan 2006/09 Corporate Plan 2006/09 Health Inequalities Strategy |  |
| CYPP BH4: Reduce health inequalities: Low birth weight per thousand | 7.83 | 8.1 | 8.0 | 7.9 | Futures Plan 2006/09 Corporate Plan 2006/09 Health Inequalities Strategy |  |

| Measures | 2006/07 Actual | Targets |  |  | Linkages with other plans etc. |
| --- | --- | --- | --- | --- | --- |
|  |  | 2007/08 | 2008/09 | 2009/10 |  |
| CYPP BH5: Reduction in smoking at delivery | 18.3% (2005/06) | 17.3% | 16.3% | 15.3% | LAA 2007 – 10 (Healthier Communities) Calderdale LAA Delivery Plan HC03, p93 |
| CYPP BH6: Increase in breastfeeding maintenance rates: Narrow the gap between % of women in the most deprived quartile breastfeeding at first visit and District average |  |  |  |  | LAA 2007 – 10 (Healthier Communities) Calderdale LAA Delivery Plan HC03, p93 |
| CYPP BH6.1: Most deprived quintile | 40% (2005/6) | 40% | 42% | 44% | LAA 2007 – 10 (Healthier Communities) Calderdale LAA Delivery Plan HC03, p93 |
| CYPP BH6.2: Calderdale average | 52% (2005/6) | 52% | 53% | 54% | LAA 2007 – 10 (Healthier Communities) Calderdale LAA Delivery Plan HC03, p93 |
| CYPP BH7: Prevalence of obesity among primary school aged children | Baseline to be available Feb 2007 | Target agreed Feb 2007 | Target agreed Feb 2007 | Level as per 08/09 year ie halted year on year increase | LAA 2007 – 10 (Healthier Communities) Calderdale LAA Delivery Plan HC05, p96 |
| CYPP BH8: Healthy School Scheme status: proportion of schools to achieve Healthy School Status The Healthy School Standard changed in September 2005. The 2006/07 target is based on schools achieving the required standard (old/new) as at their most recent assessment. The targets are set by the Government with the 2008/09 target relating to participation. | 6 as at Dec 2006 | 50% | TBC | TBC | Futures Plan 2006/09 Corporate Plan 2006/09 CYPS Plan 2006 -09 Health Inequalities Strategy Teenage Pregnancy Strategy Young People Substance Misuse Pack CAMHS Strategy |
| Measures | 2006/07 Actual | Targets |  |  | Linkages with other plans etc. |
|  |  | 2007/08 | 2008/09 | 2009/10 |  |
| CYPP BH9: Healthy exercise: the percentage of 5-16 year olds engaged in 2 hours a week minimum on high quality PE and school sport within and beyond the curriculum. | 84% as at 31st Dec 2006 | 80% | 85% | TBC | Futures Plan 2006/09 Corporate Plan 2006/09 Health Inequalities Strategy |
| CYPP BH10: Full range of CAMHS services for children and young people with learning disabilities | 1 (2005/6) 3 (2006/7 baseline) | 3 | 4 | 4 | LAA 2007 – 10 (CYP) |
| CYPP BH11: 16 and 17 year olds who require mental health services have access to services appropriate to their age and level of maturity | 4 (2005/6) 4 (2006/7 baseline) | 4 | 4 | 4 | LAA 2007 – 10 (CYP) |
| CYPP BH12: Arrangements in place to ensure that 24 hour cover is available to meet urgent mental health needs of children and young people and for a specialist mental health assessment to be undertaken within 24 hours or the next working day, where indicated | 3 (2005/6) 4 (2006/7 baseline) | 4 | 4 | 4 | LAA 2007 – 10 (CYP) |
| CYPP BH13: Protocols in place for partnership working between agencies for children and young people with complex, persistent and severe behavioural and mental health needs | 1 (2005/6) 3 (2006/7 baseline) | 3 | 4 | 4 | LAA 2007 – 10 (CYP) |

| Measures | 2006/07 Actual | Targets |  |  | Linkages with other plans etc. |
| --- | --- | --- | --- | --- | --- |
|  |  | 2007/08 | 2008/09 | 2009/10 |  |
| CYPP BH14: Reduce levels of decayed missing and filled (dmf) teeth in children under 5. | 2.04 decayed missing and filled teeth (July 2006) | Action Plans in place | 1.9 decayed missing & filled teeth ( data available July 08 survey) | 1.7 decayed missing & filled teeth data available July 2010 survey) | LAA 2007 – 10 (Healthier Communities) Calderdale LAA Delivery Plan HC08, p102 |

| Self- Assessment Score | Actions | Time Scales | Costs/Budgets | Officer Responsible |
| --- | --- | --- | --- | --- |
| Improve young people’s sexual health and reduce the number of teenage pregnancies |  |  |  |  |
|  | (CYPP BH1a / CYPP BH2a) Implement Calderdale’s Teenage Pregnancy Strategy and Sexual Health and Relationship Strategies and Action Plans - Implementation of 07-08 annual work plan - Develop 2007-12 strategy - Integrate 1st phase Strategy pilots/service changes into mainstream service deliver (within Authority and partner organisations) - Ensure young parents Strategy is integrated into CYP Services/Family services - Ensure Teenage Pregnancy Implementation grant is spent in accordance with grant conditions | April 2006 – April 2009 | Base budget and £136k Teenage Pregnancy Grant (multi-agency strategy) | Teenage Pregnancy Co-ordinator |
| - Reduce children and young people’s health inequalities and increase healthy lifestyles |  |  |  |  |
|  | (CYPP BH7a / CYPP BH14a) Develop and implement health support programmes for Park, Field Lane, Ovenden and Mixenden and Ferney Lee. | April 2006 – April 2009 | Activities to be funded from £2.1 million Sure Start Local Programmes £1.1 million children’s centres revenue grant | - Head of Children’s Services (PCT) |
| Self- Assessment Score | Actions | Time Scales | Costs/Budgets | Officer Responsible |
|  | (CYPP BH) Implement the Children and Young People’s Preventative Strategy. | April 2006 – April 2009. To be reviewed by March 2007, then annually. | £200K – CMBC base budget | - Head of Family Support Services |
|  | (CYPP BH8a) Implement the new Healthy School Scheme support programme. | April 2006 – April 2009. To be reviewed by March 2007, then annually | £175K – CMBC and PCT base budget + Standards Fund | Head of Learning Services |
|  | (CYPP BH8b) Co-ordinate the Calderdale School Meals strategy in response to Government guidelines. | April 2006 onwards. To be reviewed by March 2007 | £132,417retained from school meals grant. | Head of Learning Services |
|  | (CYPP BH9a) As part of the review of out of school sports, leisure and cultural opportunities, develop more targeted out of school sport and leisure programmes for children and young people. | Review to be undertaken by October 2006. Strategy to be developed by January 2007, to be implemented April 2007 onwards. | £30K consultancy costs to undertake review and draft strategy – CYPS strategic priorities budget (realigned 2005/06 service budgets) | Head of Family Support Services |
|  | (CYPP BH9b) Implement PE and Sports Strategies with schools. | April 2006 onwards. To be reviewed by March 2007 then annually. | £3K – CMBC base budget | Head of Learning Services |
| - Ensure children and young people’s mental health well-being |  |  |  |  |
|  | (CYPP BH10-13) Implement action within the 2007-10 CAMHS strategy focusing on priorities across all tiers of intervention | April 2007 onwards to be monitored September 2007 | Use of CAMHS grant allocations of £514,000 agreed by partners | Head of Commissioning and Partnership Services |

| 2. Staying Safe |  |  |  |  |  | Lead Officer Head of Care Services |
| --- | --- | --- | --- | --- | --- | --- |
| To achieve our priority outcomes |  |  |  |  |  |  |
| Measures | 2006/07 Actual | Targets |  |  | Linkages with other plans etc. |  |
|  |  | 2007/08 | 2008/09 | 2009/10 |  |  |
| CYPP SS1: Child protection reviews: Of the children on the child protection register who had been on the register continuously for 3 months, the percentage that were reviewed within timescales | 98% (2005-06 actual) 95.5% (31st Dec 2006) 100% (2006-07 target) | 100% | 100% | 100% | CYPS Plan 2006/09 |  |
| CYPP SS2: Improved services for victims of domestic violence through targeted schemes: Reduction in the re-offending by perpetrators of domestic violence | TBC Dec 2007 | TBC Dec 2007 | TBC Dec 2007 | TBC Dec 2007 | LAA 2007 – 10 (Safer & Stronger Communities) Calderdale LAA Delivery Plan SSC23, p82 |  |
| CYPP SS3: Improved services for victims of domestic violence through targeted schemes: | 64% (2005/6) 100% (2006/7 target) | 100% | 100% | 100% | LAA 2007 – 10 (Safer & Stronger Communities) Calderdale LAA Delivery Plan SSC24, p83 |  |

| Measures | 2006/07 Actual | Targets |  |  | Linkages with other plans etc. |
| --- | --- | --- | --- | --- | --- |
|  |  | 2007/08 | 2008/09 | 2009/10 |  |
| CYPP SS4: Initial assessments: proportion of initial assessments completed within timescales | 76.8% (2005/6 actual) 75% (2006/7 target) 63.8% (as at 31 Dec. 2006) | 79% | 83% | 87% | LAA 2007 – 10 (CYP) Futures Plan 2006/09 Corporate Plan 2006/09 CYPS Plan 2006/09 JAR Action Plan |
| CYPP SS5: Core assessments: proportion of core assessments completed within timescales | 63.3% (2005/6 actual) 70% (2006/7 target) 66.4%( as at 31st Dec 2006) | 72% | 77% | 82% | LAA 2007 – 2010 (CYP) Futures Plan 2006/09 Corporate Plan 2006/09 CYPS Plan 2006/09 JAR Action Plan |
| CYPP SS6: Child protection referrals: number of children on the child protection register per 10,000 aged under 18 | 19.3 (2005/6 actual) 23 (2006/7 target) 25.9% (as at 31st Dec 2006) | 24 | 25 | 25 | LAA 2007 – 2010 (CYP) CYPS Plan 2006/09 JAR Action Plan CSCB annual report |
| Measures | 2006/07 Actual | Targets |  |  | Linkages with other plans etc. |
|  |  | 2007/08 | 2008/09 | 2009/10 |  |
| CYPP SS7: Child protection referrals: re-registrations on the Child Protection Register | 16.4% (2005/6 actual) 13% (2006/7 target) | 12% | 12% | 12% | LAA 2007 – 2010 (CYP) CYPS Directorate Plan 2006 – 2009 CYP Plan 2006 – 2009 CSCB annual report. |

| Self- Assessment Score | Actions | Time Scales | Costs/Budgets | Officer Responsible |
| --- | --- | --- | --- | --- |
| Improve multi-agency capacity for assessment, prevention and service provision for vulnerable children and young people |  |  |  |  |
|  | (CYPP SS4a / CYPP SS5a) Establish multi-agency referral and assessment team as part of Children and Young People’s Services Directorate structure. | Pilot in North Halifax Extended to 31 March ’07. Plan to roll out ISA over next quarter. Pilot to be extended to North of the Borough by 30 April 2007. Strategic Leads and CAF Champions to be identified by 31 March ’07. Recruitment and Selection to start by 31 March ’07. IT Solution to be agreed by 31 May ’07. CMAS to be launched by 31 July ’07. | £20K – CMBC base budget Implementation costs not yet known. | Head of Commissioning and Partnership Services |

| Self- Assessment Score | Actions | Time Scales | Costs/Budgets | Officer Responsible |
| --- | --- | --- | --- | --- |
|  | (CYPP SS4c / CYPP SS5c) Develop and implement strategy for the development of Calderdale’s local child information sharing index (ISI) | Local timeline – development of systems and data (e.g. early years, alternative provision) which will feed the ISI by June 2007 National timeline – readiness assessment and pre-deployment work by Spring 2006, commencement of data management stage by June 2007, completion end 2008. | £34K – CMBC base budget Data validation and management £68,355 in 2006/07, £164,000 in 2006/07. DFES specific funding. | Principal Officer Performance Support and ICT |

| Self- Assessment Score | Actions | Time Scales | Costs/Budgets | Officer Responsible |
| --- | --- | --- | --- | --- |
|  | (CYPP SS4d / CYPP SS5d) Implement the termly school census and individual level early years census, develop additional PLASC data sets for vulnerable children and young people | Exclusions by May 2006 Addresses for year 11s for IS Index by May 2006, all pupils by Jan 2007 Post 16 learning aims by September 2006 Attendance by May 2006 for secondary, all pupils by January 2008 (pilot) Early Years Jan 2007 Termly school census 2008 to include maintained nurseries, hospital special schools, PRUs, general hospital schools and alternative provision. In all 7 different census collections in 2008. | £26K – CMBC base budget | Principal Officer Performance Support and ICT |

| Self- Assessment Score | Actions | Time Scales | Costs/Budgets | Officer Responsible |
| --- | --- | --- | --- | --- |
|  | (CYPP SS4e / CYPP SS5e) Roll-out common assessment framework across Calderdale. | Pilot in North Halifax extended to 31/03/07. Plan to roll out over next quarter. Pilot to be extended to North of the Borough by 30 April 2007. Strategic Leads and Change Agents for CAF to be identified in all agencies. Pilot to be extended to North of the Borough by 30 April 2007 | Costs for team incorporated in Change Grant – £90K to December 2006. Ongoing costs incorporated into CMAS costs January 2007 onwards | Head of Commissioning and Partnership Services |
|  | (CYPP SS1a / CYPP SS6a / CYPP 7a) Finalise the implementation of the outstanding serious case review action plans. | To be completed by June 2007 | £5K – CMBC base budget + Calderdale Safeguarding Board Children’s Board (CSCB) budget | Head of Care Services Safeguarding Manager |
|  | (CYPP SS1b / CYPP SS6b / CYPP 7b) Disseminate the CSCB’s/West Yorkshire child protection and safeguarding guidance to all agencies and organisations and to provide additional training as appropriate.. | April – July 2007 | £3K Safeguarding base budget and Training budget Cost of producing guidance for one quarter £1,306.25 | Safeguarding Unit Manager |
|  | (CYPP SS4f / CYPP SS5f) Implement Preventative Strategy to support early assessment and intervention. | Implement July 2006 – March 2009, to be reviewed annually. | £200K – CMBC base budget + grant and partner funding | Head of Commissioning and Partnership Services |
|  | (CYPP SS) Review procedures and guidance to respond to requirements of new adoption legislative requirements. | Implement September 2006 onwards, to be reviewed by March 2008. | £7K – CMBC base budget | Head of Care Services |
| Self- Assessment Score | Actions | Time Scales | Costs/Budgets | Officer Responsible |
|  | (CYPP SS) Implement joint procedures for children and young people missing from home in the light of new guidance | Implement by September 2007 | £1.5K – CMBC base budget | Head of Care Services |
|  | (CYPP SS) Implement the Looked After Children Strategy and action plan | Implement from 2007-20010 and review annually | £3K CMBC base budget and £35K CYPS strategic priorities budget | Head of Care Services |
|  | (CYPP SS) Implement the Looked After Children Placement Commissioning Framework and Action Plan | Implement form April 2007 - 2010 | £5K CMBC base budget plus CYPS strategic priorities budget | Head of Care Services |
|  | (CYPP SS) Implement disabled children and young people’s strategy to improve the integration of services for disabled children and young people and their families with an emphasis on early identification and diagnosis, multi-agency packages, transition planning and addressing barriers to inclusion through mechanisms such as direct payments. | Strategy approved by Cabinet by February 2007. Implement March 2007 – September 2010 and review annually | £10K base budget and £40K CYPS strategic priorities | Head of Care Services |
|  | (CYPP SS) Work with partners to implement CYP Plan actions to improve accommodation options for children and young people who are at risk. | April 2007 – March 2010 and to be reviewed annually | £15K – CMBC base budget | Head of Care Services |
| - Reduce the number of children and young people who are affected by domestic violence |  |  |  |  |
|  | (CYPP SS2a) Work with partners to develop a strategy to mainstream response to children affected by domestic violence through prevention, early identification, intervention and support | Strategy, implementation plan and resources to be finalised by October 2007. Implementation October 2007 – March 2008. | £3K – CMBC base budget Costs March 2007 onwards not yet known. | Head of Commissioning and Partnership Services |
| Self- Assessment Score | Actions | Time Scales | Costs/Budgets | Officer Responsible |
| - Reduce the number of children and young people who are at risk of sexual exploitation |  |  |  |  |
|  | (CYPP SS) Implement the strategy for children at risk of sexual exploitation. | Implement 2007 – 2008 and to review in October 2007. | £34K CMBC base budget, Connexions and CAMHS funding | Safeguarding Manager |

| 3. Enjoying and Achieving |  |  |  |  |  | Lead Officer Head of Learning Services |
| --- | --- | --- | --- | --- | --- | --- |
| To achieve our priority outcomes |  |  |  |  |  |  |
| Measures | 2006/07 Actual | Targets |  |  | Linkages with other plans etc. |  |
|  |  | 2007/08 | 2008/09 | 2009/10 |  |  |
| CYPP EA1: Key Stage 2 results: the percentage of pupils in schools maintained by the authority achieving level 4 or above in Key Stage 2 English test. *NB the 2007 targets are intended to be lower than those for 2006. This reflects the outcome of detailed analysis of local data, based on Fischer Family Trust analyses, since we are no longer required to agree a target imposed by the DfES. ** There is a formal and well developed National target setting process. We cannot pre-empt this process as our predictions may conflict with the actual statutory targets – therefore N/A | 80% | 84%* | 84% | N/A** | Learning Services School Improvement Plan 2006/07 CYPS Plan 2007/10 |  |

| Measures | 2006/07 Actual | Targets |  |  | Linkages with other plans etc. |
| --- | --- | --- | --- | --- | --- |
|  |  | 2007/08 | 2008/09 | 2009/10 |  |
| CYPP EA2: Key Stage 2 results: the percentage of pupils in schools maintained by the authority achieving level 4 or above in Key Stage 2 Mathematics test. | 80.2% | 84%* | 85% | N/A | Learning Services School Improvement Plan 2006/07 CYPS Plan 2007/10 |
| CYPP EA3: Key Stage 3 results: the percentage of pupils in schools maintained by the authority achieving level 5 or above in Key Stage 3 English test. | 74.4% | 79%* | 81% | N/A | Learning Services School Improvement Plan 2006/07 CYPS Plan 2007/10 |
| CYPP EA4: Key Stage 3 results: the percentage of pupils in schools maintained by the authority achieving level 5 or above in Key Stage 3 Mathematics test. | 78.3% | 79%* | 81% | N/A | Learning Services School Improvement Plan 2006/07 CYPS Plan 2007/10 |
| CYPP EA5: Key Stage 3 results: the percentage of pupils in schools maintained by the authority achieving level 5 or above in Key Stage 3 Science test. | 73.6% | 79%* | 80% | N/A | Learning Services School Improvement Plan 2006/07 CYPS Plan 2007/10 |
| CYPP EA6: GCSE or equivalent results: the percentage of pupils in schools maintained by the authority achieving 5 or more GCSE or equivalent grades A* - C including English and mathematics. | 43.8% (2006/7) | 46% | 51% | TBC Jan 2008 | Futures Plan 2006/09 Corporate Plan 2006/09 CYPS Plan 2007/10 13-19 Strategy LAA 2007 – 10 (CYP) |

| Measures | 2006/07 Actual | Targets |  |  | Linkages with other plans etc. |
| --- | --- | --- | --- | --- | --- |
|  |  | 2007/08 | 2008/09 | 2009/10 |  |
| CYPP EA7: GCSE or equivalent results: the percentage of 15 year old pupils in schools maintained by the authority achieving 5 or more GCSEs at A* - C grades or equivalent | 58.1% (2006/7) | 61% | 63% | TBC Jan 2008 | LAA 2007 – 10 (CYP) |
| CYPP EA8: Attainment of North Halifax Cluster |  |  |  |  |  |
| CYPP EA8.1: The percentage of pupils in the 6 primary schools in the North Halifax Federation achieving level 4 or above in the Key Stage 2 English test | 68% - compared to 80% across Calderdale | 74% | TBC May 2007 | TBC May 2008 | LAA 2007 – 10 (CYP) |
| CYPP EA8.2: The percentage of pupils in the 6 primary schools in the North Halifax Federation achieving level 4 or above in the Key Stage 2 Maths test | 73% - compared to 80% across Calderdale | 77% | TBC May 2007 | TBC May 2008 | LAA 2007 – 10 (CYP) |
| CYPP EA8.3: The percentage of pupils in the secondary school in the North Halifax Federation achieving level 5 or above in the Key Stage 3 English test | 29% | 61% | TBC May 2007 | TBC May 2008 | LAA 2007 – 10 (CYP) |
| CYPP EA8.4: The percentage of pupils in the secondary school in the North Halifax Federation achieving level 5 or above in the Key Stage 3 Maths test | 41% | 56% | TBC May 2007 | TBC May 2008 | LAA 2007 – 10 (CYP) |

| Measures | 2006/07 Actual | Targets |  |  | Linkages with other plans etc. |
| --- | --- | --- | --- | --- | --- |
|  |  | 2007/08 | 2008/09 | 2009/10 |  |
| CYPP EA8.5: The percentage of pupils in the secondary school in the North Halifax Federation achieving level 5 or above in the Key Stage 3 Science test | 35% | 53% | TBC May 2007 | TBC May 2008 | LAA 2007 – 10 (CYP) |
| CYPP EA8.6: The percentage of pupils in the secondary school in the North Halifax Federation achieving 5 or more GCSE or equivalent passes at A*-C | 19% | 24% | TBC May 2007 | TBC May 2008 | LAA 2007 – 10 (CYP) |
| CYPP EA8.7: The percentage of pupils in the secondary school in the North Halifax Federation achieving 5 or more GCSE or equivalent passes at A*-C including English and Maths | 4% | 13% | TBC May 2007 | TBC May 2008 | LAA 2007 – 10 (CYP) |
| CYPP EA9: Attendance of Schools in the North Halifax Federation Percentage of half days missed by pupils in the primary schools in the North Halifax Federation | 2006/7 |  |  |  | LAA 2007 – 10 (CYP) |
| CYPP EA9.1: Dean Field | 7.7% | 7.0% | TBC Jan 08 | TBC Jan 09 | LAA 2007 – 10 (CYP) |
| CYPP EA9.2: Lee Mount | 5.8% | 4.9% | TBC Jan 08 | TBC Jan 09 | LAA 2007 – 10 (CYP) |
| CYPP EA9.3: Whitehill | 5.3% | 4.1% | TBC Jan 08 | TBC Jan 09 | LAA 2007 – 10 (CYP) |

| Measures | 2006/07 Actual | Targets |  |  | Linkages with other plans etc. |
| --- | --- | --- | --- | --- | --- |
|  |  | 2007/08 | 2008/09 | 2009/10 |  |
| CYPP EA9.4: Abbey Park | 5.0% | 4.1% | TBC Jan 08 | TBC Jan 09 | LAA 2007 – 10 (CYP) |
| CYPP EA9.5: Ash Green | 5.6% | 4.1% | TBC Jan 08 | TBC Jan 09 | LAA 2007 – 10 (CYP) |
| CYPP EA9.6: Moorside | 6.1% | 6.0% | TBC Jan 08 | TBC Jan 09 | LAA 2007 – 10 (CYP) |
| CYPP EA10: Percentage of half days missed by the pupils in the secondary school in the North Halifax Federation | 17.7% | 13.0% | TBC Jan 08 | TBC Jan 09 | LAA 2007 – 10 (CYP) |
| CYPP EA11: Achievement of looked after children: Of looked after children in year 11 who were eligible for GCSE or equivalent, the proportion who achieved 5 GCSE’s at grades A*-C | 12% (2005/6) 21% (2006/7) | 16% | 19% | 22% | LACYP Strategy 2006/09 LAA 2007 – 10 (CYP) |
| CYPP EA12: Achievement of looked after children: Of looked after children in year 11 who were eligible for GCSE or equivalent, the proportion who sat at least 1 GCSE or equivalent | 75% (2006/7) | 82% | 86% | 90% | LAA 2007 – 10 (CYP) |

| Measures |  | 2006/07 Actual | Targets |  |  | Linkages with other plans etc. |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2007/08 | 2008/09 | 2009/10 |  |  |
| CYPP EA13: Use of libraries and art galleries: % of library users under 16 who view their library service as good. |  | 85.1% (result from Oct 05 survey published Q3 2006) 77% (target) | 77% | TBA | TBA | Corporate Plan 2006/09 |  |
| CYPP EA14: Quality of early years provision: the percentage of registered childcare settings with quality assurance accreditation. |  | 17% (as at 31st Dec 2006) 40% (06/7 target) | 50% | 50% | TBA | Corporate Plan 2006/09 Early Years Development and Childcare Plan |  |
| Self- Assessment Score | Actions |  | Time Scales |  | Costs/Budgets |  | Officer Responsible |
| Ensure sufficient educational opportunity for personalised learning |  |  |  |  |  |  |  |
|  | (CYPP EA) Support schools to implement primary and secondary national strategies |  | April 2007 – March 2010, to be reviewed annually |  | £9K – Primary and secondary national strategies Standards Fund grant |  | Head of Learning Services |
| Self- Assessment Score | Actions |  | Time Scales |  | Costs/Budgets |  | Officer Responsible |
|  | (CYPP EA) Continue to develop targeted youth work support in schools. |  | April 2007 – March 2010 reviewed annually. |  | £2K from £350K 13-19 Strategy pooled budget |  | Head of Learning Services |
|  | (CYPP EA) Make core learning platform software available to schools which includes a personalised learning space to support e-portfolios, email to all teachers and students, and integrated learning and management systems |  | DfES target date - 2008 |  | Standards Fund – connectivity and learning systems. Amount to be determined when other calls on the budget are known. |  | Principal Officer Technology and Performance Support |

| Self- Assessment Score | Actions | Time Scales | Costs/Budgets | Officer Responsible |
| --- | --- | --- | --- | --- |
|  | (CYPP EA8a / CYPP EA9a) Implement the agreed outcomes of the review of education provision in North Halifax. To include: - reduction of surplus primary places in North Halifax; - implementation of statements of action for St Catherine’s Catholic High School and The Ridings School (both in special measures); -implementation of statement of action for Moorside Primary School (notice to improve); - development of alternative secondary provision in North Halifax in line with recommendations of the review. | April 2007 – September 2010 St Catherine’s Statement of Action – September 2006 – April 2008, to be reviewed termly; Ridings Statement of Action – March 2007 – July 2009, to be reviewed termly; North Halifax review consultation completed by June 2007 Recommendations on surplus places made to Cabinet by July 2007 Recommendations on primary provision to be made to Cabinet by October 2007; implemented by September 2008. Recommendations on secondary provision to be made to Cabinet by October 2007; implemented by September 2010 | £10K Council base budget. Full costs of review implementation not yet known | Group Director Children and Young People’s Services |

| Self- Assessment Score | Actions | Time Scales | Costs/Budgets | Officer Responsible |
| --- | --- | --- | --- | --- |
|  | (CYPP EA) Scope and develop the proposed Calderdale Challenge project to enable all Calderdale’s children and young people to achieve their full potential. To include: - recruitment and retention of school senior leaders; - further development of collaboration, choice and diversity in schools; - challenge and support to enable all children and young people make good progress in schools; - preparation of the education rationale for Calderdale’s building schools for the future submission | September 2007 – July 2008 Project to be launched September 2008 – August 2011 | £25K Council base budget. Full cost of Calderdale Challenge programme not yet known. | Group Director Children and Young People’s Services |
|  | (CYPP EA) Participate in the national Making Good Progress pilot project | April 2007 – July 2009 | Funding provided by DfES special grant – full amount not yet known | Head of Learning Services |

| Self- Assessment Score | Actions | Time Scales | Costs/Budgets | Officer Responsible |
| --- | --- | --- | --- | --- |
| Ensure the personal development needs of all children and young people, including the most vulnerable, are addressed both in school and the community |  |  |  |  |
|  | (CYPP EA) Work with schools to develop and implement a co-ordinated strategy for behaviour management and support, including the invest to save bid to reduce out of Borough SEN placements, the establishment of behaviour support secondary school clusters, a review of current behaviour support provision for all schools and the development of part of the Wellesley Park unallocated buildings to provided enhanced and extended accommodation for the KS4 PRU. | Strategy to be developed by June 2007. Phase 1 of the strategy to be implemented September 2007 – July 2008 | £25K – CMBC base budget £1.6million invest to save bid | Head of Family Support Services |
|  | (CYPP EA) Work with schools and other partners to review and refocus the work of the Educational Psychology Service. | Review to be undertaken by July 2007. Recommendations to be implemented by December 2007 | £4.5K – CMBC base budget | Head of Family Support Services |
|  | (CYPP EA) Support schools to increase their capacity to manage support at the lowest level of vulnerability (pupil disaffection and prevention measures). | Strategy to be implemented April 2007 – March 2008, to be reviewed by March 2008. | £8K – CMBC base budget | Head of Family Support Services |
|  | (CYPP EA) Improve procedures for transition of children with special educational needs between early years settings and primary schools, primary to secondary and into post-16 provision. | New procedures implemented April 2007 – March 2009, to be reviewed by March 2008. | £2.5K – CMBC base budget | Head of Family Support Services |
| Self- Assessment Score | Actions | Time Scales | Costs/Budgets | Officer Responsible |
|  | (CYPP EA) Review systems, prioritise and plan for the development of in depth data sets in respect of vulnerable children and young people, for tracking achievement and outcomes. | Work to be brought across from Health and Social Care in April 2007. Work programme to be developed from April 2007. Implemented April 2007 – March 2009 | £26K – CMBC base budget | Principal Officer Technology and Performance Support |
|  | (CYPP EA) Undertake a review of community provision for all children and young people, including youth service, recreation, leisure and culture, and targeted provision offered by the Council, other public and private services and the voluntary and community sector and develop a framework for a co-ordinated and planned range of both universal and targeted provision across Calderdale. | Develop recommendations of the review from April 2007 | £40K – CMBC base budget and consultancy support to be funded from CYPS strategic priorities budget | Head of Family Support Services |
|  | (CYPP EA13a) Develop and implement the Learning and Access Strategy for Museums, Galleries and Arts. | L&A strategy is being developed in tandem with adoption and embedding of MLA’s Inspiring Learning for All across the service. This has led to a longer timescale than originally anticipated. The Strategy will now be finalised by end June 2007 with implementation from September 2007 | £5K CMBC budget | Head of Libraries, Museums and Arts. |
| Self- Assessment Score | Actions | Time Scales | Costs/Budgets | Officer Responsible |
|  | (CYPP EA13b) Develop a 3 year strategic Education Development Plan for Museums, Galleries and Arts. | Extensive consultation is taking place with schools and CYP Services to develop integrated Libraries and Museums education ‘offer’. Following completion of consultation in mid March, the Development Plan will be finalised and in place by September 2007 | £2K CMBC base budget | Head of Libraries, Museums and Arts |

| 4. Making a Positive Contribution |  |  |  |  |  | Lead Officer Head of Family Support Services |
| --- | --- | --- | --- | --- | --- | --- |
| To achieve our priority outcomes |  |  |  |  |  |  |
| Measures | 2006/07 Actual | Targets |  |  | Linkages with other plans etc. |  |
|  |  | 2007/08 | 2008/09 | 2009/10 |  |  |
| CYPP MPC1: Youth offending: the percentage of youth offenders supervised by the Youth Offending Team who are in full time education, training or employment | 51% - 55% for Quarters 1-3 90% (target) | 90% | 90% | 90% | Corporate Plan 2006/09 Futures Plan 2006/09 Community Safety Strategy 2006/09 |  |
| CYPP MPC2: Youth offending: The re-offending rate with respect to pre-court, first tier penalties, community penalties and custodial penalties. | 12% improvement recorded between 2000 and 2006. 44% (2005/6) 42% (target 2006/7) | Reduce by 5% on 2002 baseline | Reduce by 5% on 2002 baseline | New national targets expected | Corporate Plan 2006/09 Futures Plan 2006/09 Community Safety Strategy 2006/09 |  |

| Measures | 2006/07 Actual | Targets |  |  | Linkages with other plans etc. |
| --- | --- | --- | --- | --- | --- |
|  |  | 2007/08 | 2008/09 | 2009/10 |  |
| CYPP MPC3: Youth offending: The number of first time entrants to the Youth Justice System | 370 (as at 31st Dec 2006) Projection for year is 493 – target was 406 | 5% reduction on 2006/07 | 5% reduction on 2007/08 | New national targets expected | Corporate Plan 2006/09 Futures Plan 2006/09 Community Safety Strategy 2006/09 Preventative Strategy 2006/09 |
| CYPP MPC4: Offending of looked after children: the percentage of children aged 10 – 17 who have been looked after for 12 months or more who were convicted, received a final warning or reprimand | 11.2% (2006/7) | 11% | 10% | 9% | LAA 2007 – 10 (CYP) Corporate Plan 2006/09 LACYP Strategy 2006/09 |
| CYPP MPC5: Level of satisfaction of young people aged 13-19 years with regard to their opportunities to influence important decisions | 34% (2006/7 actual) | 35.2% | 45% | 50% | LAA 2007 – 10 (CYP) |
| CYPP MPC6: Level of satisfaction of those children and young people who have participated actively in decision making that they have been able to influence decisions | Baseline and targets to be confirmed by May 2007 | TBC Sept 2007 | TBC Sept 2007 | TBC Sept 2007 | LAA 2007 – 10 (CYP) |

| Self- Assessment Score | Actions | Time Scales | Costs/Budgets | Officer Responsible |
| --- | --- | --- | --- | --- |
| Increase individual and collective opportunities for active participation of children and young people in service development, provision and evaluation |  |  |  |  |
|  | (CYPP MPC5a / CYPP MPC6a) Revise structure of Participation Project to ensure full and meaningful participation in decision making about services that affect children and young people both in and beyond school. | Revised structure and action plan to be implemented from April 2007 – March 2009, to be reviewed by January 2008, then annually. | £15K – CMBC base budget | Principal Officer Commissioning and Partnership Services |
|  | (CYPP MPC 5b / CYPP MPC6b) Respond to Youth Matters by:- a) Working in partnership with young people to develop provision using Youth Capital and Youth Opportunities funds. b) By working with partners in order to deliver the Youth Offer for young people. | Project plan implemented from April 2007 – March 2008 Round 2 of YOF/YCF to be allocated through the grants panel – starts Feb 07 Plan to be in place by June 2007 for implementation in this and subsequent years. | £2.5K – CMBC base budget | Principal Officer Young People’s Services |
|  | (CYPP MPC5c / CYPP MPC6c) Review the role and remit of the Youth Parliament in the context of the development of the wider children and young people’s participation project. To develop Calderdale Youth Council which will have representation from school councils, area youth fora and specialist interest groups. | Review to be completed by March 2007 Revised structure to be in place by April 2007 | Costs incorporated into CY3P review | Principal Officer Commissioning and Partnership Services |
| Self- Assessment Score | Actions | Time Scales | Costs/Budgets | Officer Responsible |
|  | (CYPP MPC5d / CYPP MPC6d) Review representation of children and young people on CYPMG and determine the most effective links to CYPMG. | Review to be completed by March 2007 Revised arrangements to be implemented from September 2007 | Costs incorporated into CY3P review | Head of Commissioning and Partnership Services |
|  | (CYPP MPC5e / CYPP MPC6e) Support schools in developing effective citizenship programmes and school councils. | Current work to be reviewed by July 2007 | Healthy Schools budget | Head of Learning Services |
|  | (CYPP MPC5f / CYPP MPC6f) Develop local forums for children and young people within their communities in order that they might take part in decision-making processes. | Strategy being developed from July 2006 - March 2008 | £1.5K CMBC base budget | Head of Family Support Services |
|  | (CYPP MPC5g / CYPP MPC6g) Review texting project and develop opportunities for children and young people to express their views. | Current project to be reviewed by March 2007 Strategy to be further developed and integrated with CY3P plan. | £1.5K – CMBC base budget | Head of Family Support Services |
|  | (CYPP MPC5h / CYPP MPC6h) Implement the Young People First action plan, ensuring regular feedback to children and young people about progress. | October 2006 – September 2007 | £1.5K – CMBC base budget | Principal Officer Commissioning and Partnership Services |

| Self- Assessment Score | Actions | Time Scales | Costs/Budgets | Officer Responsible |
| --- | --- | --- | --- | --- |
| Increase opportunities and support for children and young people to make a positive contribution and reduce youth offending |  |  |  |  |
|  | (CYPP MPC1a) Youth Offending Team (YOT), Connexions and schools and other partners to work together to increase the numbers of young offenders in full time education, training or employment. | April 2006 – March 2009, to be reviewed by March 2007 then annually as part of the development of Calderdale’s Prevent and Deter Strategy | £109.5K Connexions funding to YOT for Operations Manager, Accommodation Officer and Link Worker. | YOT Manager |
|  | (CYPP MPC1b) Further develop the 13-19 Strategy to support all vulnerable groups, including young offenders to remain in full time education, training or employment | April 2006 – March 2009, to be reviewed by March 2007 then annually. | £2K – 13-19 Strategy pooled budget | Head of Family Support Services |
|  | (CYPP MPC1c) Implement YOT Prevent and Deter Strategy | Link with Preventative Strategy, review annually | £ 144k Arrest Referral £113k Children’s Fund £86k Youth Inclusion Programme £45k Junior Interventions Project £40k Arts Dev Officer £35k Anti-Social Behaviour Officer £30k Parenting Worker £25k Victim Liaison Officer | YOT Manager |

| Self- Assessment Score | Actions | Time Scales | Costs/Budgets | Officer Responsible |
| --- | --- | --- | --- | --- |
|  | (CYPP MPC) Ensure timely referrals to CAMHS through development of a service level agreement between YOT and CAMHS and improved data collection in YOT Health Needs Assessment (HNA) agreed by YOT Management Board for YOT young people in order to inform development of SLA between YOT and PCT. Primary Mental Health Worker agreed 1 day a week to assist. Development of electronic HNA for use with young people. Using Health Needs Assessment develop services specifically suited to needs of young offenders. YOT to work closely with CAMHS Strategy Group and Children and Young People’s Commissioning Group. | June 07 January 07 onwards April 07 July 07 | £5k per annum £4k 2 days YOT Operations Manager time | YOT Manager |
|  | (CYPP MPC1-4) Integrate the Home Office Pilot scheme for Arrest Referral into the Prevent and Deter Strategy for Calderdale in order to inform future commissioning activity over prevention services. Arrest Referral Pilot Steering Group to integrate project into Prevent and Deter Strategy for Calderdale and link with Children and Young People’s Commissioning Group with a view to achieving longer term funding. | March 07 May 07 | Home Office have confirmed by letter bridging funding of the Arrest Referral Pilot Scheme until September 2007 with a grant of £72,000. | DAAT /YOT Manager |
| Self- Assessment Score | Actions | Time Scales | Costs/Budgets | Officer Responsible |
|  | (CYPP MPC) Review the outcomes of time limited funded projects including Positive Activities for Young People (PAYP), the Youth Inclusion Programme (YIP), Children’s Fund activities in North Halifax and the Positive Futures Programme in North Halifax and develop a sustainable long term programme | Review of current preventative activities to be completed by March 2007. Revised programme to be implemented from September 2007. | Consultant to facilitate work around setting new priorities (£3,000 costs share between CYPD, Connexions, YOT for May 2006 work) | Head of Family Support Services |
|  | (CYPP MPC) Implement Preventative Strategy to provide targeted support for children and young people who are at risk of engaging in anti-social behaviour or offending. | July 2006 – March 2009, to be reviewed by March 2007 then annually. | £200K CMBC base budget + partnership and grant funding (already identified) | Head of Family Support Services |
|  | (CYPP MPC) Implement a Youth Management Information System to enable the service to monitor and review services. | Full implementation by April 2007 To be reviewed annually | £5K CMBC base budget £10k cost of system – from CMBC base budget | Principal Officer Young People’s Services |
|  | (CYPP MPC5i / CYPP MPC6i) Audit, analyse and develop the range of local volunteering opportunities for young people. | To be updated September 2007 | £2K – CMBC base budget | Principal Officer Young People’s Services |

| 5. Achieving Economic Well-Being |  |  |  |  |  | Lead Officer Head of Learning Services |
| --- | --- | --- | --- | --- | --- | --- |
| To achieve our priority outcomes |  |  |  |  |  |  |
| Measures | 2006/07 Actual | Targets |  |  | Linkages with other plans etc. |  |
|  |  | 2007/08 | 2008/09 | 2009/10 |  |  |
| CYPP AEW1: Improving level 2 skills: Percentage of young people gaining national level 2 qualification by age 19 | 66.8% (Summer 2006) | 67% without stretch | 68% without stretch | 69% without stretch 71% with stretch Enhance-ment of 2% points increase in young people gaining nat-ional level 2 qualifica-tions | LAA 2007 – 10 (Economy & Enterprise) Calderdale LAA Delivery Plan EE07b, p9 |  |

| Measures | 2006/07 Actual | Targets |  |  |  |  | Linkages with other plans etc. |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2007/08 |  | 2008/09 | 2009/10 |  |  |
| CYPP AEW2: The total average point score at GCE/VCE for young people aged 19 | 701 (2005/06) | 710 without stretch |  | 722 without stretch | 740 without stretch 760 with stretch Enhance-ment of increase in APS of 20 in 2009/10 |  | LAA 2007 – 10 (Economy & Enterprise) Calderdale LAA Delivery Plan EE07b, p9 |
| CYPP AEW3: Indicator to measure education attainment relative to district average |  |  |  |  |  |  | LAA 2007 – 10 (Economy & Enterprise) Calderdale LAA Delivery Plan EE08, p11 |
| CYPP AEW3.1: In Ovenden Initiative neighbourhood management area (NMP) | TBC Dec 2007 | TBC Dec 2007 |  | TBC Dec 2007 | TBC Dec 2007 |  | LAA 2007 – 10 (Economy & Enterprise) Calderdale LAA Delivery Plan EE08, p11 |
| CYPP AEW3.2: In Mixenden Initiative neighbourhood management area (NE) | TBC Dec 2007 | TBC Dec 2007 | TBC Dec 2007 |  |  | TBC Dec 2007 | LAA 2007 – 10 (Economy & Enterprise) Calderdale LAA Delivery Plan EE08, p11 |
| CYPP AEW3.3: In Park Community Initiative neighbourhood management area (NE) | TBC Dec 2007 | TBC Dec 2007 | TBC Dec 2007 |  |  | TBC Dec 2007 | LAA 2007 – 10 (Economy & Enterprise) Calderdale LAA Delivery Plan EE08, p11 |
| CYPP AEW4: Percentage of 16-18 year olds not in education, employment or training |  |  |  |  |  |  | CYP Plan 2007 – 10 (Economy & Enterprise) Calderdale LAA Delivery Plan EE09, p12 |

| Measures | 2006/07 Actual | Targets |  |  |  |  | Linkages with other plans etc. |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 200708 | 2008/09 |  | 2009/10 |  |  |
| CYPP AEW4.1: In Calderdale | 8.7% | 8.5% | 8.1% |  | 7.6% |  | CYP Plan 2007 – 10 (Economy & Enterprise) Calderdale LAA Delivery Plan EE09, p12 |
| CYPP AEW4.2: In Ovenden Initiative neighbourhood management area (NMP) | TBC Sept 2007 | TBC Oct 2007 | TBC Oct 2007 |  | TBC Oct 2007 |  | CYP Plan 2007 – 10 (Economy & Enterprise) Calderdale LAA Delivery Plan EE09, p12 |
| CYPP AEW4.3: In Mixenden Initiative neighbourhood management area (NE) | TBC Sept 2007 | TBC Oct 2007 | TBC Oct 2007 |  | TBC Oct 2007 |  | CYP Plan 2007 – 10 (Economy & Enterprise) Calderdale LAA Delivery Plan EE09, p12 |
| CYPP AEW4.4: In Park Community Initiative neighbourhood management area (NE) | TBC Sept 2007 | TBC Oct 2007 | TBC Oct 2007 |  | TBC Oct 2007 |  | CYP Plan 2007 – 10 (Economy & Enterprise) Calderdale LAA Delivery Plan EE10, p13 |
| CYPP AEW5: Percentage of young people with learning difficulties/ disabilities aged over 16 who remain in full-time education, training or employment | 74.6% (TBC March 2007) | 83% | TBC March 2007 |  | TBC March 2007 |  | CYPS Plan 2006/09 LAA 2007 – 10 (Economy & Enterprise) |
| CYPP AEW6: Ratio of young people leaving care aged 16 or over engaged in full time education, training or employment to the total in the age group | 0.9 (TBC March 2007) | 0.9 |  | 0.9 |  | 0.9 | LAA 2007 – 10 (Economy & Enterprise) Futures Plan 2006/09 Corporate Plan 2006/09 CYPS Plan 2006/09 LACYP Strategy Calderdale LAA Delivery Plan EE11, p14 |

| Self- Assessment Score |  | Actions | Time Scales |  | Costs/Budgets |  |  | Officer Responsible |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | (CYPP AEW) Ensure that all young people with statements of SEN have a transition plan when the statement support ends. |  |  | April 2006 – March 2009 |  | £1.5K – CMBC base budget+ Connexions budget (£2.1 million in total) | Head of Family Support Services |  |
|  | (CYPP AEW6a) Increase accommodation available for care leavers. |  |  | April 2008 |  | Officer time £3k CMBC base budget | Head of Care Services |  |
|  | (CYPP AEW5a) Develop and implement a joint strategy with adult social services to support transition for young people and their families where ongoing support and care as an adult with learning difficulties or mental health difficulties or with disabilities |  |  | Transition protocol to be developed by April 2008 and implemented April 2008 – March 2010. |  | £7.5K CMBC base budget Transition co-ordinator post. | Head of Care Services |  |
|  | (CYPP AEW5b) Following the LSC review of post 16 provision for young people with learning difficulties and disabilities, develop and implement a strategy for increasing the range of local education and training provision for these young people. |  |  | September 2007 Strategy developed by December 2006 Consultation – January 2007 – April 2007 To be implemented September 2007 – March 2009 |  | £8K – CMBC base budget to develop strategy. Costs of implementation not yet known. £50K LSC grant to develop project proposal | Head of Family Support Services |  |

| Self- Assessment Score |  | Actions | Time Scales |  | Costs/Budgets |  |  | Officer Responsible |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | (CYPP AEW5c) Develop a ‘learner’ account post 16 for young people with complex needs in collaboration with schools, college and LSC |  |  | Learning Account project completed by September 2007. Development of local provision mapping Jan 2007 – March 2008 Implementation September 2007-March 2008 |  | This is a commissioned piece of work by LSC which includes officer secondment – approx £50K | Head of Family Support Services |  |
|  | (CYPP AEW) Develop and implement an annual strategic plan for learning and skills for young people 13-19 including information, advice and guidance, to focus on reducing the numbers of young people identified as NEET and to raise achievement |  |  | April 2007 – March 2008 |  | Pooled budget £85K schools and college LSC to be confirmed Standard Fund to be confirmed Connexions £20K | Head of Learning Services |  |

Glossary

| Acronym | Term | Acronym | Term |
| --- | --- | --- | --- |
| AEW | Achieving Economic Wellbeing | DFT | Department for Transport |
| AH | Affordable Housing | DH | Department of Health |
| APT | Action Planning Team | DP | Delivery Plan |
| ASB | Anti-Social Behaviour | DPPO | Designated Public Places Order |
| BH | Being Healthy (Indicator reference for CYPP) | DWP | Department for Work and Pensions |
| BLWY | Business Link West Yorkshire | DWP LPS | Department for Work and Pensions Local Pensions Service |
| BV | Best Value indicator reference | EA | Enjoying and Achieving (Indicator reference for CYPP) |
| CAB | Citizens Advice Bureau | EE | Economy and Enterprise |
| CAMHS | Children and Adolescent Mental Health Service | EV | Environment |
| CC | Calderdale College | GCE/ VCE | General Certificate in Education / Vocational Certificate in Education |
| CCF | Calderdale Community Forum | HA | Housing Association |
| CEO | Chief Executive Officer | HC | Healthier Communities |
| CHFT | Calderdale Hospital Foundation Trust | IB | Incapacity Benefit |
| CHT | Calderdale Hospital Foundation Trust | ICT | Information & Communication Technology |
| CMBC | Calderdale Metropolitan Borough Council | ISI | Information Sharing Index |
| CPCT | Calderdale Primary Care Trust | JAR | Joint Area Review |
| CVD | Cardio-Vascular Disease | JCP | Jobcentre Plus |
| CYP | Children and Young People | Kirklees MC | Kirklees Metropolitan Council |
| CYPP | Children and Young People's Plan indicator reference | LAA | Local Area Agreement |
| DAAT | Drug and Alcohol Action Team | LAC | Looked after children |
| Devt | Development | LACE | Looked After Children Education Service |
| DFES | Department for Education and Skills | LCHO | Low Cost Home Ownership |
| LEA | Local Education Authority | PPG | Pump-priming Grant |
| LPS | Local Pensions Service | PPO | Prolific and Priority Offender |
| LPSA | Local Public Service Agreement (former name for Reward Element target) | PRG | Performance Reward Grant |
| LSC | Learning and Skills Council | PSA | Public Service Agreement |
| LSP | Local Strategic Partnership | QA | Quality Assurance |
| (M) | Mandatory target | R&D | Regeneration and Development |
| MC | Metropolitan Council | WYLTP | West Yorkshire Local Transport Plan |
| MDT | Mandatory Drug Test | YOT | Youth Offending Team |
| MP | Making a Positive Contribution (Indicator reference for CYPP) | RE | Reward Element |
| MYCCI | Mid Yorkshire Chamber of Commerce | RE Target | Reward Element target (formerly called Local Public Service Agreement target) |
| NAHP | National Affordable Housing Programme | RSL | Registered Social Landlord |
| NE | Neighbourhood Element | SEN | Special Educational Needs |
| NEET | Not in Education, Employment or Education | SLA | Service Level Agreement |
| NMP | Neighbourhood Management Partnership | SS | Staying Safe (Indicator reference for CYPP) |
| NPT | National Probation Service | SSC | Safer and Stronger Communities |
| NTG | Narrowing the gap | SWYMHT | South West Yorkshire Mental Health Trust |
| Occ Health | Occupational Health | TBA | To be arranged |
| OCN | Open College Network | TBC | To be confirmed |
| OP | Older People | VCS | Voluntary and Community sectors |
| pa. | per annum | VSU | Victim Services Unit |
| PCT | Primary Care Trust | WCHx | West Central Halifax |
| PH2k | Pennine Housing 2000 Ltd |  |  |

Further information

To be confirmed