6

# Report to Scrutiny Panel

| Name of Scrutiny Panel | Adults, Health and Social Care |  |
| --- | --- | --- |
| Meeting Date | 16th March 2011 |  |
| Subject | Update on implementation of the action plan arising from the Serious Case Review commissioned by the Safeguarding Adults Board |  |
| Wards Affected | All |  |
| Report of | Head of Wellbeing and Social Care |  |
| Type of Item (please tick ) | Review existing policy |  |
|  | Development of new policy |  |
|  | Performance management (inc. financial) |  |
|  | Briefing (inc. potential areas for scrutiny) |  |
|  | Statutory consultation |  |
|  | Council request |  |
|  | Cabinet request |  |
|  | Member request for scrutiny (CCFA) |  |

Why is it coming here?

Appendix 1 shows the progress that has been made in implementation of the multi-agency action plan arising from a Serious Case Review. The Serious Case Review report and action plan were presented to this committee in August 2010 when members requested an update to be presented early in 2011. The independent SCR report was commissioned by the Safeguarding Adults Board following the death of HT – aged 82 - on 12th July 2009.

What are the key points?

- The action plan has been regularly reviewed by the Safeguarding Adults Board – including at its meeting on 1st March 2011 - The majority of actions have been implemented by the partner agencies. - SAB decided not to pursue the publication of an easy read version of the serious case review report as the resources to “translate” the document were not available at the time that the publication of an easy read version would have been appropriate. - The areas to be completed are summarised at the end of appendix 1 – page 21 onwards. Progress is underway for all actions and they are all due to be implemented by May 2011. - The key actions that remain to be completed concern training programmes and information to be published following the re drafting of the multi-agency safeguarding adults procedures in May. The procedures were reviewed in light of this SCR and other developments in practice. - The Safeguarding Adults Board will continue to monitor progress until the actions are complete.

Possible courses of action

- Safeguarding Adults Board to monitor the implementation of these actions

Contact Officer

Ruth Ingram Safeguarding Adults Manager ruth.ingram@calderdale.gov.uk Tel: 01422 393804

Should this report be exempt?

NO

| Reference |  | Jonathan Phillips |
| --- | --- | --- |
| Date | March 2011 | Director – Adult, Health and Social Care |

Key to RAG rating .Green = complete	Amber = on target for completion	Red not complete or information on progress not received

| Calderdale Safeguarding Adults Board \ SCR Action Plan |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SCR No | Recommendation |  | Response/Agreed action | Lead responsibility |  | Due date | Revised due date | Progress March 2011 |  | RAG |
| 6.1.1 | The multi agency guidance and procedures should be reviewed and amendments considered (as detailed in report) |  | Multi-agency safeguarding policy and procedures to be reviewed and re published | Safeguarding Manager |  | May 2010 | May 2011 | Draft procedures agreed Publication May 2011 |  | Green |
| 6.1.2 | Consideration should be given to contacting the CPS to seek their involvement and engagement in safeguarding, both as partner agency and as a contributor to multi agency guidelines and procedures |  | CPS to be invited to join SAB | Chair of SAB |  | May 2010 |  | Complete |  | Green |
| 6.1.3 | The SAB multi-agency training and development strategy and the content of training provided by each agency should be reviewed, to take account of lessons learnt in relation to both MARAC and Safeguarding |  | Multi-agency training strategy and training materials to be reviewed to ensure lessons learnt are incorporated | Safeguarding Development Officer and Training Task Group |  | July 2010 |  | Complete |  | Green |
| 6.14 | A simple information leaflet for members of the public should be developed which explains about Safeguarding and how people can access services. |  | Current leaflet to be reviewed in light of new procedures | Safeguarding Manager/AHSC Information officer |  |  | May 2011 |  |  | Amber |
| 6.15 | The SAB should work with all relevant stakeholders to make the process simple and easily understood for staff to “press the button” and get Agencies to come together and take action to protect vulnerable people. |  | Multi-agency safeguarding policy and procedures to be reviewed and re published | Safeguarding Manager/AHSC Information officer |  |  | May 2011 | Draft procedures agreed Publication May 2011 |  | Green |
|  |  |  | Web pages to be revised | Safeguarding Manager/AHSC Information officer |  |  | May 2011 | Draft Complete |  | Amber |
| 6.1.6 | Each Agency should produce an Action Plan to ensure that the recommendations made in this review are fully implemented, and the SAB should review these action plans every 6 months until it is satisfied that all recommendations have been introduced satisfactorily |  | SAB to receive and monitor agency action plans in response to this SCR every 6 months | Chair of SAB and Safeguarding Manager |  | July 2010 SAB |  | Ongoing |  | Green |
|  | Produce plain English version of SCR |  |  | CMBC Coms team |  |  | March 2011 | SAB agreed not to progress this |  | Red |
| West Yorkshire Police |  |  |  |  |  |  |  |  |  |  |
|  | Recommendation | Response/Agreed action |  |  | Lead responsibility | Due date | Revised due date |  | Progress March 2011 | RAG |
| 6.2.1 | The West Yorkshire Police (Calderdale Division) to ensure that systems are in place to ensure that all Domestic Abuse incidents and associated information and intelligence are appropriately notified to the Vulnerable Victim Unit. | All divisional Staff to ensure correct reporting procedures undertaken in relation to incidents involving Vulnerable Adults |  |  | Divisional Crime Manager | 31st March 2010 |  |  | . Ongoing | Green |
|  |  | Training provision for all front line Police officers within division to recognise incidents of abuse relating to Vulnerable and record accordingly |  |  | Police Training | 31st October 2010 | 31st March 2011 |  | Comprehensive Safeguarding training programme to be delivered. | Amber |
| 6.2.2 | The West Yorkshire Police (Calderdale Division) to ensure that consideration is made to referring all High risk Domestic Abuse incidents to MARAC and that systems are in place to audit all such referral and where decisions are made not to refer, the rationale is to be recorded on VIVID by a Supervisory Officer. | Supervisory structures within Safeguarding Unit to effectively manage, and record all responses to Vulnerable Victims. |  |  | Divisional Crime Manager | 30th April 2010 |  |  | Completed | Green |
|  |  | Appropriate Safeguarding referrals made to MARAC process. |  |  | MARAC Co-ordinator | 30th April 2010 |  |  | Completed | Green |

| 6.2.3 | The West Yorkshire Police (Calderdale Division) to ensure the risk assessments made in relation to Domestic Abuse incidents are accurate and that processes are in place to audit compliance with policy. | All Safeguarding Unit staff to ensure accurate risk assessments are in place in accordance with policy. Full audit to be undertaken within divisional Safeguarding Unit | Detective Supervisor, Divisional Safeguarding Unit | 31st May 2010 |  | Completed | Green |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 6.2.4 | That the DASH Risk Identification Checklist (RIC) replaces SPECCS as a risk assessment tool, and that this is introduced as soon as possible |  |  |  | 31st March 2011 | New data recording system to be introduced - Force NICHE Records Management system. | Amber |
| 6.2.5 | Training of Officers about multi agency procedures and especially about making written safeguarding referrals to ASC must be provided, and must be attended by Officers as identified through a training needs analysis | See 6.2.1 above ?? |  |  | 31st March 2011 | Comprehensive Safeguarding training programme to be delivered. | Amber |

| South West Yorkshire Partnership NHS Trust |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Recommendation | Response/Agreed action | Lead responsibility | Due date | Revised due date | Progress March 2011 | RAG |
| 6.3.1 | Managers must make sure that clinical staff are aware of, can have access to, and operate in accordance with MARAC and the multi agency safeguarding policy, procedures and guidance. Clinical staff have a professional responsibility to ensure they do likewise. | Safeguarding policy, procedure and guidance are available on the intranet. Staff attending training are made aware of the policy and how to access the document. Guidance relating to Domestic Abuse and MARAC procedure requires updating by the Trust MARAC Reps. | Specialist Advisor for Vulnerable Adults | End of April re DV policy update |  | Complete | Green |
| 6.3.2 | Managers in all clinical settings must ensure that clinical staff have access to appropriate MARAC and Safeguarding adults training. | The Trust has a rolling programme of training available in relation to Safeguarding Adults | General Managers |  |  | Complete | Green |
|  |  | A timetable of Briefing sessions is require in relation to MARAC briefings | Specialist Advisor for Vulnerable Adults | End of April for time table |  | Complete | Green |
| South West Yorkshire Partnership NHS Trust |  |  |  |  |  |  |  |
|  | Recommendation | Response/Agreed action | Lead responsibility | Due date | Revised due date | Progress March 2011 | RAG |
| 6.3.3 | Training delivered to staff should be reviewed to include the findings of this Review and to take account of lessons learnt. | This case is to be included in safeguarding adults training and MARAC briefing sessions. Power point presentation is to be updated based on these findings | Specialist Advisor for Vulnerable Adults | Action completed |  | Complete | Green |
| 6.3.4 | When staff are working with service users who may have been or who are being abused, they must review the risk assessment and also document any action they take. Where a person is considered to be at serious risk from domestic abuse, a MARAC risk assessment should be completed. | Audit of cases of action taken needs to be carried out in each service. | General Managers | End of April to Agree audit plan |  | Complete | Green |
|  |  | The Domestic Abuse policy need to be reviewed to include the MARAC risk assessment form, and the MARAC referral form | Specialist Advisor for Vulnerable Adults | April for Draft to be distributed to teams for comments |  | Complete | Green |
| 6.3.5 | Staff need to document clearly when they have discussed with a service user the potential for a referral to MARAC and/or ASC under the domestic abuse and safeguarding adults policies. | Audit of Team meetings /supervision records | General Managers | May for process to begin July completion |  | Complete | Green |
| South West Yorkshire Partnership NHS Trust |  |  |  |  |  |  |  |
|  | Recommendation | Response/Agreed action | Lead responsibility | Due date | Notes | Progress March 2011 | RAG |
|  | Where staff have concerns about the risk to service users they should seek supervision from their managers (as per Trust supervision policy), have a peer review or case discussion, and clearly log this in the service user’s records. | Audit of supervision records / team meetings | General Managers | May for process to be agreed / July for completion |  | Complete | Green |
| 6.3.6 | The Trust should conduct an audit to ensure that its supervision policy is appropriately applied where staff have concerns about the risk to service users, identify if staff have had a peer review or case discussion, and if practices adopted are clearly logged in the service user’s records |  |  |  |  | Complete | Green |

| Calderdale and Huddersfield NHS Foundation Trust |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Recommendation | Response/Agreed action |  | Lead responsibility | Due date | Revised due date | Progress March 2011 | RAG |
| 6.4.9 | The trust Safeguarding Adult Guidelines are due for review. The revised version should be more explicit in respect of the urgency of referral & the need for this to be made by telephone. (A written referral could be forwarded subsequently). | Revised Safeguarding Guidelines/Policy to be produced for CHFT, which is more explicit re timeliness of a telephone, followed up by a written referral. |  | Safeguarding Adults Lead | June 2010 |  |  | Green |
|  | Consideration should be given to one telephone referral line for all Safeguarding Adult referrals in Calderdale. | Gateway to Care Established |  | Calderdale Local Authority | In place – February 2010 |  | Complete | Green |
| 6.4.3 | Senior Nursing (Ward Sisters) from both the A&E Department & Medical Assessment Units to have all attended half day Safeguarding Adults Training within 3 months | Staff have commenced attending the half day training. All to have attended by due date. |  | Matron Nurse Consultant Emergency Care Sister - MAU Clinical Co-ordinator - A&E | June 2010 |  | Complete | Green |
| 6.4.1 | Consistent, reliable & robust Safeguarding Adult training attendance will be put in place across both the A&E Department & the Medical Assessment Unit in line with trust policy. | Systematised processes have been established to ensure a regular & necessary training attendance is prioritised & adhered to. |  | Matron Nurse Consultant Emergency Care Sister - MAU Clinical Co-ordinator – A&E | In place & ongoing |  | Ongoing | Green |
| 6.4.2 | Wider awareness raising around Safeguarding Adult Training requirements, availability & access across the organisation. | Revised Basic Safeguarding Presentation established – for introduction April 2010. Review of half day training content. Introduction of Kwango E-learning Safeguarding package to be introduced. Awareness raising via communications, insert into job descriptions, Elder Abuse/Safeguarding Awareness week in June, Leaflets onto payslips. Reinforce importance through trust management structures |  | Safeguarding Adults Lead & Trust Safeguarding Adults Board | Ongoing & by July 2010 | E learning hopefully available in autumn. Completed July 2010 | Complete | Green |
| 6.4.5 and 6.4.6 | Registered Nurses will conduct the initial Assessment & admission of patients on the Medical Assessment Unit. All entries by unqualified practitioners must be countersigned by a registered practitioner on all occasions. | These actions have been enforced immediately post local CHFT component of SCR investigation report. |  | Matron & Sister MAU | In place since January 2010 |  | Complete | Green |
| 6.4.7 | The recently developed Safeguarding Adults Leaflet developed in the A&E Department, will be shared with staff in the Medical Assessment Unit to help raise awareness, support them in their practice & to assist them in generating appropriate & timely safeguarding referrals. | Leaflet shared & available to staff. Staff aware. | Matron & Sister MAU |  | – in place since Jan 2010. |  | Complete | Green |
| 6.4.8 | Robust referral mechanisms to be established in the Medical Assessment Unit for patients requiring the services of the Crisis Intervention Mental Health Team. | Meeting to be set up with partners in SWYPFT | Matron & Sister MAU General Manager |  | . |  | Complete | Green |
| 6.4.4 | Clinical staff in both the A&E Department and the Medical Assessment Unit, need to demonstrate a much greater awareness of Safeguarding Adults, not just of patients themselves, but the impact of patients’ behaviour on others around them. | Improved attendance Safeguarding Training necessary. | Matron Nurse Consultant |  | Ongoing & developing. |  | Ongoing | Green |
|  |  | Learning from SCR once able to share fully A&E Dept on a programme with the NHS Institute designed to enhance the Patient Experience – will be seeking to mainstream Safeguarding as part of this work. Will be sharing with MAU | Emergency Care Sister - MAU Clinical Co-ordinator – A&E |  | Review in July 2010. | Will share more fully once public |  | Green |
| 6.4.10 | A safeguarding trigger question should be incorporated within the Falls Clinic and Inpatient Falls assessment documentation | A full assessment as to the cause of patient falls is undertaken & safeguarding is a consideration although there is not a specific trigger question within the assessment |  |  |  |  |  | Green |

| NHS Calderdale (PCT) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Recommendation | Response/Agreed action |  | Lead responsibility | Due date | Revised due date | Progress March 2011 | RAG |
| 6.5.2 | To critically review and audit the uptake of Safeguarding Adult Training to reinforce the importance of rigorous risk assessment | To disseminate the Calderdale Multi Agency Policy Procedure and Guidance to all GP practices |  | Adult safeguarding –lead professional | Mar 2010 |  | Completed | Green |
|  |  | Increase awareness within the GP population and all provider staff through dissemination of information through the existing Link , GP communication system |  | Adult safeguarding –lead professional | Mar 2010 |  | Completed | Green |
|  |  | Assess the feasibility of delivering training via the PEN Pal’s ( GP protected learning scheme) |  | Adult safeguarding –lead professional | July 2010 | October 2010. |  | Green |
|  |  | Audit the existing system to monitor the uptake of training |  | Adult safeguarding –lead professional | Apr 2010 |  | Complete | Green |
|  |  | Assess the feasibility with the Medical director of developing the GP appraisal and PDR process to incorporate |  | Adult safeguarding –lead professional | June 2010 |  | . Completed | Green |
|  |  | Audit systems and processes are in place to facilitate compliance in attending |  | Head of patient Safety and Quality | Jan 2010 |  | Completed | Green |
|  |  | Develop a communication plan to ensure the learning from this serious case review is included in mandatory adult safeguarding training |  | Adult Safeguarding lead professional | Apr 2010 |  | Completed | Green |
|  |  | As part of the annual review of multi agency training ensure issues raised in this IMR are included and responded to |  | Adult Safeguarding lead professional | Apr 2010 |  | Completed. | Green |
| 6.5.3 | Critically review the district nurse record keeping template to ensure the assessment planning implementation and evaluation of ongoing patient care is explicit | To establish and review recording processes to strengthen clarity around minimum standards of baseline and ongoing assessments |  | Head of Patient Safety and Quality | Jan 2010 |  | Completed | Green |
|  |  | Review and strengthen the annual record keeping audit to define the expected outcomes in the baseline assessment |  | Head of Patient Safety and Quality | Jan 2010 |  | Completed | Green |
|  |  | To assess the feasibility of establishing ongoing peer review audit of district nursing records |  | Head of Patient Safety and Quality | Jan 2010 |  | Completed | Green |
|  |  | To audit escalation processes |  | Head of Patient Safety and Quality | Jan 2010 |  | Ongoing Rolling records audit programme | Green |
| 6.5.1 | NHS Calderdale Local Safeguarding Policy is approved, disseminated and implemented across the organisation | Policy to be received and approved by the Clinical Executive (QA) |  | Adult Safeguarding lead professional | Jan 2010 |  | Completed | Green |
|  |  | Policy to be received and reviewed by the Patient safety group |  | Adult Safeguarding Professional Lead | Apr 2010 |  | Completed | Green |
|  |  | Policy to be received and approved by the Provider Services patient safety and safeguarding group |  | Head of Patient Safety and Quality | Mar 2010 |  | Completed | Green |
|  |  | Disseminate policy throughout the provider arm, including publication on the intranet. |  | Head of Patient Safety and Quality | Mar 2010 |  | Completed. | Green |
|  |  | Policy to be disseminated to all providers and independent contractors |  | Adult Safeguarding lead professional | Mar 2010 |  | Completed. | Green |
| 6.5.4 | Review the feasibility of developing a Model of safeguarding supervision which takes into account professional accountability and enables scrutiny of professional decision. | Task and finish group will be formed to address this recommendation which will include scoping, proposal and approval mechanism. Task and Finish Group met in June 2010. Proposal to take forward a mode of supervision to be presented to the Quality & Safety Group | Adult Safeguarding lead professional |  | Apr 2010 | . |  | Green |
|  |  | Consideration will be given to developing a delegation framework to ensure there is a clear line of accountability for delegated work District Nursing Service Guidelines to be developed during 2010/11 as part of the Provider Patient Safety Development Plan which will include lines of accountability | Adult Safeguarding lead professional |  | Apr 2010 |  |  | Green |
|  | Clinical Supervision is embedded across Provider Services | Clinical Supervision Guidelines to be disseminated to all staff within Provider Services, including publication on the intranet |  | Head of Quality and Patient Safety | January 2010 | Clinical Supervision guidelines have been ratified by the Quality and Safety Group. | Completed | Green |
|  |  | Compliance with clinical supervision sessions to be audited Updated guidelines now available on the PCT Intranet for staff to access All staff currently receiving a personal clinical supervision pack Compliance with clinical supervision included into clinical audit programme for 2010/11 |  | Head of Quality and Patient Safety | March 2011 |  |  | Green |
|  | Provide personalised feedback to individuals within the team involved in the SCR | Feedback to be individuals involved with the case, including record keeping. |  | Head of Quality and Patient Safety | End March 2010 |  | Completed | Green |

| Adult Health and Social Care |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Recommendation | Response/Agreed action | Lead responsibility | Due date | Revised due date | Progress March 2011 | RAG |
| 6.6.1 | An audit of safeguarding referrals received by ASC should be undertaken to establish the extent to which ASC staff are working in accordance with MARAC and the multi agency Safeguarding policy, procedures and guidance. | Audit to be carried out of most recent 100 completed safeguarding referrals across all adult groups. Audit to cover issues raised by SCR. | Safeguarding Manager; Relevant Operations Managers | Late April 2010 |  | Complete | Green |
|  |  | More in depth audit to be carried out of sample of cases from each team. | Relevant Operations Managers | Late April 2010 |  | Complete To be repeated by April 2011-see CQC action plan | Green |
| 6.6.2 | An audit of referrals should take particular account of the role of Team Leaders who have a key role to play in supervising staff and in the effective implementation of MARAC and multi agency safeguarding guidance and procedures. This audit should help to shape any staff training and development that is required. | In depth audit to examine how team leaders/managers use supervision to ensure effective implementation of MARAC and safeguarding procedures. | Relevant Operations Managers | Late April 2010 |  | Complete As a result new supervision protocol/IT screen to be implement-ed in April 2011. | Green |
|  |  | Consideration to be given to additional training and development needs of team leaders/managers in relation to safeguarding | Training task group/WFDU/Safeguarding team | By June 2010 | May 2011 | Being reviewed in line with revised procedures National competency framework being used to assess training needs Training plan agreed for 2011-12 Module to be developed by end May | Amber |
| 6.6.3 | Future training should take account of the lessons learnt from this Review and in particular of the need for staff to recognise their safeguarding role alongside that of providing support and services to vulnerable adults. | All social workers are receiving a full day’s training on new safeguarding screens and changes to the safeguarding procedures resulting from the SCR. | Safeguarding Manager; Development Officer, Safeguarding | April 2010 |  | Complete | Green |
|  |  | The Safeguarding Adults Training and Development Strategy module for safeguarding assessors to be reviewed and redesigned in the light of the SCR. | Training task group/WFDU/ Safeguarding Team | By June 2010 | May 2011 | Being reviewed in line with revised procedures National competency framework being used to assess training needs Training plan agreed for 2011-12 Module to be developed by end May | Amber |
| 6.6.3 | Consideration should be given to the need for risk assessment training. | Adequacy of current arrangements for developing competency in risk assessments to be reviewed. | Workforce Development Manager and Operations Managers, Wellbeing & Social Care | By June 2010 | Feb 2011 | Completed Action agreed to train key staff as part of 6.6.2 above and wider staff through new pathways framework. | Green |
| 6.6.4 | Consideration should be given to requiring in all safeguarding cases where a referral is accepted, that the nominated safeguarding assessor has at least one initial person- to - person contact with the potential vulnerable person. This contact might take place alongside a colleague from another Agency, provided this would not be detrimental to their relationship with the service user. | Safeguarding procedures to be revised to embed this requirement into safeguarding process and to clearly record situations where this cannot be done. | Safeguarding Manager | By June 2010 | Dec 2010 | Draft procedures agreed Publication May 2011 | Green |
| 6.6.5 | ASC should ensure that Team Managers understand their responsibility to follow multi agency safeguarding procedures, and that Team Managers are clear about the reason why a case is opened or closed, with the distinction between safeguarding and assessment/support made apparent | Discuss in management meetings |  |  |  | Complete | Green |
|  |  | Deliver one day training to all team managers and practitioners | Safeguarding manager |  |  | Complete | Green |
|  | Where safeguarding referrals remain as open cases, consideration must always be given to having a planning meeting, and where a decision is made not to have such a meeting, the reasons for this should be recorded. | Procedures to be revised to make clear to safeguarding assessors and their managers under what circumstances a planning meeting is required and to ensure that there is a clear record of decisions not to hold one. | Safeguarding Manager | By June 2010 | Dec 2010 | Being included in new draft procedures Publication May 2011 | Green |
| 6.6.6 | All staff should be reminded of the importance of noting and recording discussions with managers about safeguarding issues whether they take place inside or outside of formal settings such as supervision or planned case meetings. | Adult care management procedures to be revised, making it a requirement that there is a written record of case discussions relating to safeguarding issues, as part of the client record. | Relevant Operations Managers, Wellbeing & Social Care | By June 2010 |  | Complete | Green |
| 6.6.7 | Administration at the hospital social work team must be reminded of the importance of bringing to the attention of the Team Manager any and all communications received relating to safeguarding issues. | Team manager to be tasked with ensuring administrative systems are robust and that safeguarding concerns are reported immediately to the Team Manager or person deputising. | Chief Operations Manager, OP&PD; Hospital Team Manager | April 2010 |  | Complete | Green |
| 6.6.8 | A manager from ASC should be designated to attend regularly the monthly meetings of MARAC. | Discussions to take place in Wellbeing and Social Care to nominate a suitable staff member to represent ASC at MARAC meetings. | Head of Wellbeing & Social Care | April 2010 |  | Complete | Green |

| Summary of outstanding actions |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Safeguarding Adults Board |  |  |  |  |  |  |  |
|  | Recommendation | Response/Agreed action | Lead responsibility | Due date | Revised due date | Progress March 2011 |  |
| 6.14 | A simple information leaflet for members of the public should be developed which explains about Safeguarding and how people can access services. |  |  |  | May 2011 |  | Amber |
| 6.15 | The SAB should work with all relevant stakeholders to make the process simple and easily understood for staff to “press the button” and get Agencies to come together and take action to protect vulnerable people. | Web pages to be revised |  |  | March 2011 |  | Amber |
| 6.1.6 | Each Agency should produce an Action Plan to ensure that the recommendations made in this review are fully implemented, and the SAB should review these action plans every 6 months until it is satisfied that all recommendations have been introduced satisfactorily | SAB to receive and monitor agency action plans in response to this SCR every 6 months | Chair of SAB and Safeguarding Manager | July 2010 SAB |  | Ongoing | Amber |
|  | Produce plain English version of SCR |  | CMBC Coms team | Dec 2010 | March 2011 | SAB agreed not to progress | Red |
| West Yorkshire Police |  |  |  |  |  |  |  |
| 6.2.1 | The West Yorkshire Police (Calderdale Division) to ensure that systems are in place to ensure that all Domestic Abuse incidents and associated information and intelligence are appropriately notified to the Vulnerable Victim Unit. | Training provision for all front line Police officers within division to recognise incidents of abuse relating to Vulnerable and record accordingly | Police Training | 31st October 2010 | 31st March 2011 | Comprehensive Safeguarding training programme to be delivered. | Amber |
| 6.2.4 | That the DASH Risk Identification Checklist (RIC) replaces SPECCS as a risk assessment tool, and that this is introduced as soon as possible |  |  |  | 31st March 2011 | New data recording system to be introduced - Force NICHE Records Management system. | Amber |
| 6.2.5 | Training of Officers about multi agency procedures and especially about making written safeguarding referrals to ASC must be provided, and must be attended by Officers as identified through a training needs analysis | See 6.2.1 above ?? |  |  | 31st March 2011 | Comprehensive Safeguarding training programme to be delivered. | Amber |
| Adult Health and Social Care |  |  |  |  |  |  |  |
|  | Recommendation | Response/Agreed action | Lead responsibility | Due date | Revised due date | Progress March 2011 |  |
| 6.6.2 | An audit of referrals should take particular account of the role of Team Leaders who have a key role to play in supervising staff and in the effective implementation of MARAC and multi agency safeguarding guidance and procedures. This audit should help to shape any staff training and development that is required. | Consideration to be given to additional training and development needs of team leaders/managers in relation to safeguarding | Training task group/WFDU/Safeguarding team | By June 2010 | May 2011 | Being reviewed in line with revised procedures National competency framework being used to assess training needs Training plan agreed for 2011-12 Modules to be developed by end May | Amber |
| 6.6.3 | Future training should take account of the lessons learnt from this Review and in particular of the need for staff to recognise their safeguarding role alongside that of providing support and services to vulnerable adults. | The Safeguarding Adults Training and Development Strategy module for safeguarding assessors to be reviewed and redesigned in the light of the SCR. To be revised in line with new competency framework | Training task group | By June 2010 | May 2011 | Being reviewed in line with revised procedures National competency framework being used to assess training needs Training plan agreed for 2011-12 Modules to be developed by end May | Amber |