Calderdale Health and Wellbeing Board

Date: 26 July 2011
Subject: Local Healthwatch Task & Finish Group – Update
1. Purpose of the report
1.1. To provide the Board with an update on the progress made by the Local HealthWatch transition task and finish group, which met for the first time on 12th July 2011. 

2. Progress Update 
Progress has been made on the following key issues:
2.1. Engaging Widely with Stakeholders

A flyer/ information sheet is being produced, and will be available before the end of July. This will give a plain English overview of the proposals for Local Healthwatch in Calderdale, and invite people to get involved further. In particular, it will invite people to a stakeholder’s event to be held on 21st September 2011. 

The event will have speakers talking about involvement good practice, workshops to get people’s views on local barriers/ aspirations for Local HealthWatch (LHW) and a drop in event for people to find out more. 

The group has also decided to invite representatives from older people’s involvement structures to join this work, to ensure that this important client group is represented. 

2.2. Investigating Different Delivery Models

Work to develop detailed proposals is ongoing. It will be informed by the Stakeholder’s event in September, but in the meantime, we will get examples from other local authorities for comparison and continue to link into other areas through a Regional Commissioners’ Group. This will help to develop an idea of the resources needed. 

The Task & Finish Group will also look at how LHW will work with other involvement structures for young people, and how the transition for complaints advocacy services will work from 2013 onwards. 

2.3. Report to the Shadow Health And Wellbeing Board

As well as the delivery model above, a key part of this report will be to set the timescale for commissioning. 

Calderdale Council’s Procurement Manager is helping to put together a timescale for the process, including exploring different options for procuring the services needed. This timescale, along with the comparison information on different delivery models, will be considered at the next meeting of the Task & Finish Group on 1st September 2011.
This group is on schedule to deliver a report to the Shadow Health & Wellbeing Board in October 2011. 


For further information about this report, please contact: 

Sarah Manfredi

Community Engagement Manager, Calderdale MBC

Sarah.manfredi@calderdale.gov.uk
01422 393271/ 0754 066 9488

Agenda Item 8








