11

# CALDERDALE MBC

# WARDS AFFECTED:     ALL

# AUDIT COMMITTEE –  17th March 2014

# RISK MANAGEMENT 2013-14 ANNUAL REPORT

REPORT OF HEAD OF FINANCE

- ISSUE

1.1	To provide Members of the Audit Committee with an annual review of the management of risk within the Council for 2013-2014.

- NEED FOR A DECISION

  - To note the work of the Corporate Risk Management Support Group (CRMSG) in managing risk during 2013-14, and;

  - To comment on and approve the February 2014 update of the Corporate Risk Management Strategy and Corporate Risk Register.

3.	RECOMMENDATION

  - Members approve the updated Corporate Risk Management Strategy and Corporate Risk Register.

  - Members note the work carried out by the Corporate Risk Management Support Group in managing risk within the Council.

  - That a half yearly progress report be presented to the 3rd November 2014 Audit Committee meeting.

4.	BACKGROUND

  - The purpose of this report is to update Members of the Audit Committee on risk management within the Council over the last year.

  - Local Authorities are required to have in place sound systems of internal control which include arrangements for managing risk. To provide this effectively the Council has a Corporate Risk Management Strategy incorporating a Risk Management Framework. The Risk Management Framework outlines the processes in place for identifying, assessing, and controlling risks associated with achievement of the Council’s objectives and the delivery of its services and is one of the key elements in place with regard to the Council’s overall systems of internal control and corporate governance.  The aim of the Framework is to balance the level of risk faced by the Council with the appropriate resources necessary to control the risk, and then to monitor those controls to ensure that the residual risk is manageable by the Council.

4.3	In order to achieve the objectives of the Corporate Risk Management Strategy and the Risk Management Framework and to ensure that risk management is fully embedded throughout the Council, the CRMSG is in place. The group consists of the Acting Assistant Head of Finance, Risk Manager, Directorate Risk Champions, Internal Audit, the Principal Health and Safety Advisor and the Emergency Planning Advisor. The fundamental role of this group is to ensure implementation of the Corporate Risk Management Strategy, to share best practice, to offer advice and assistance throughout all aspects of Council business with regard to risk and to advise on potential future risk.

- CORPORATE RISK MANAGEMENT STRATEGY

  - The Corporate Risk Management Strategy forms the foundation for Risk Management within the Council and is used to ensure risk management is aligned with the Councils corporate priorities. It also contributes towards the Councils strong systems of internal control and corporate governance procedures which are reflected in the Council’s Annual Governance Statement.

  - The Corporate Risk Management Strategy was formally reviewed in February 2014 and there have been some revisions to the review processes and reporting of risk. The updated Corporate Risk Management Strategy is attached in Appendix A of this report for Members information.

6.	CORPORATE RISKS

6.1	Decisions taken by Central Government with regard to reductions in Local Authority resources continue to put pressure on Councils to deliver existing services with reduced resources. Calderdale is no exception and has had to change the way that it can deliver services in line with public expectation. This has required Members to continue to consider significant budget reductions as part of the budget proposals for 2014 – 2017. The financing decisions taken by central government continue to have significant risk implications for how the Council provides its services and have a significant influence not just on the Corporate Risk Register but on the Directorate, Programme and Project risk registers which feed into the Corporate Register.

6.2	The Corporate Register is divided into two parts A and B.

Part A identifies those risks which are likely to affect the delivery of the Councils services in the current economic climate and these are reviewed and reported to Members.

Part B contains those risks which need to be retained within the corporate risk register but which are unlikely to change unless the controls are reduced or removed. The revised and amended corporate risk register is attached at Appendix B.

Corporate risks can be escalated from part B to part A if it is considered that the level of likelihood or impact of the risk has increased and equally risks can be moved from part A to Part B if the level of risk has reduced to the point where it is no longer a key risk.

6.3	The following paragraphs set out the views of Directors who are designated corporate lead officers for corporate risks, the Council’s Corporate Leadership Team (CLT) and CRMSG on whether there is a need to increase or decrease the priority of certain risks within the Corporate Risk Register.

6.4	In November 2013 the Assistant Head of Finance contacted all Directors as the corporate risk owners, asking them to:

1. Individually and comprehensively review each of the risks within the corporate risk register for which they were responsible.

2. Consider whether there might be any new or emerging Corporate Risks which might affect the Council that were not already on the Corporate Risk Register.

3. Consider, review and update their Directorate Risk Registers.

6.5	Following the review by Directors of the risks within the Corporate Risk Register for which they have responsibility, with the exception of CR044 ‘Services that are provided to schools becoming academies’, no Director felt the need to either increase or reduce the level of risk for any of the corporate risks within the Corporate Risk register.

The Director of Communities identified a new risk for inclusion within the Corporate Risk Register and this is CR045 Delivery of the Tour De France and this is included within the revised Corporate Register attached in Appendix B.

The CRMSG also considered the Corporate Risk Register as part of the group’s review of the Directorate and Corporate Risk Registers.

Corporate Leadership Team considered the report at their meeting on the 25th February 2014 and are in agreement with the report and the proposed amendments to the Corporate register outlined below.

6.6	The proposed amendments to the Corporate Risk Register are as follows

6.6.1	CR044 Services that are provided to schools becoming academies - currently High Risk.

The Director of Children and Young Peoples  who has responsibility for this risk has as part of their review, proposed that the risk be amended to Medium on the basis of the controls detailed in that risk and that the predicted impact of the risk has reduced. The CRMSG and CLT support the view that the risk be amended to Medium.

6.6.2.	CR045 Delivery of the Tour de France

Calderdale is one of only a few Councils through which the Tour de France will travel on the 6th of July 2014 and as such is responsible for the logistics of delivering the Tour De France stage, managing and delivering spectator expectations and also ensuring that the people who live in the areas through which the cyclists will pass are not unduly affected. There is a specific Tour de France risk register being produced however as the impacts of the Tour de France are across the Council it is considered appropriate that there should be a risk included in the Corporate Risk Register. The CRMSG and CLT support the view that the risk be included for this review period.

6.7	All Directors were asked to ensure that for the Corporate Risks for which they have lead responsibility that there was a link into the appropriate section of the Councils priority outcomes ‘Building Ambition for Calderdale’ and this has been completed.

6.8. 	All Directors as corporate risk owners have been reminded to keep the corporate risks under continuous review and this will be reported to Members in the November progress report on Risk Management to the Audit Committee.

7.	DIRECTORATE RISK REGISTERS

7.1	Directorate Risk registers are continuously reviewed by Directorate Risk Champions, with the revised registers being presented to Directorate Management/Leadership Teams for approval. Once DMT’s/DLT’s have agreed the updated directorate risk register, the register will be circulated in the form of a Member briefing note to Scrutiny panels.

7.2 	For Member information, at the current time Directorate Risk Register progress is as follows;

- AHSC – Currently under review.

- Chief Execs – review process completed and reported.

- CYPS –  review completed and reported to Scrutiny.

- Communities – reported to Scrutiny on 13 November 2013.

- Economy and Environment – review reported to Scrutiny on 3rd February  2014.

- Public Health – register completed and finalised.

7.3	Directorate risk champions were asked to carry out a full review of their directorate risk registers as part of the peer review of directorate risks which was carried out in February 2014. Individual directorate risks were compared across all directorate risk registers. In addition those risks included within the Corporate Risk Register were considered and where common areas were identified it was determined whether those risks should individually remain the responsibility of the Directorate or whether the risk should be escalated to the Corporate Register. The peer review has resulted in amendments to several of the risks within directorate registers but no directorate risks have been escalated to the Corporate Risk Register for 2013-2014.

8.	RISK REGISTER REVIEW PROCESS

8.1	As part of its work the CRMSG continually seeks to improve the management and reporting of risk. At the peer group review due to the number of new risk champions which now form part of the group there was a discussion on the linking between the different levels of risk register and the critical points at which a project risk or directorate risks can start the escalation process onto the corporate risk register.

8.2	As a result of these discussions it was agreed that the existing levels of risk registers provided a robust system for the management of risk. It is felt however that the existing review and reporting process for risk should be refined to ensure that there is a comprehensive overview and challenge of the review process and that the different types of risk register are more closely linked. It is therefore proposed that in the future:-

8.2.1	All project risks will be reviewed as part of the project process and if it is considered that a project risk warrants escalation onto a directorate register then the project lead will discuss the risk with the directorate risk champion and if it is appropriate take the risk to the next available directorate management team for approval.

8.2.2	All directorate risk registers will be challenged by the Risk Manager and the directorate risk champion. The purpose of the challenge is to include the consideration of the inclusion of any project risks, whether the current risk priorities are appropriate  and whether any of the risks are sufficiently high that they should be considered for inclusion on the corporate risk register.  Any suggested revisions will be taken to the directorate management team for agreement.

8.2.3	There is an element of continual review of the corporate risk register, however as a result of the challenge from the Risk Manager any potential revisions or inclusion of risks from the directorate risk register will be discussed with the lead for that corporate risk and reported to Corporate Leadership Team for their comment and agreement.

8.2.4  All changes to corporate risk priorities and any inclusions of risks escalated from the directorate risk registers will be reported to Members of the Audit Committee for comment and approval. This will ensure that where necessary Members of the Audit Committee see the changes to the Corporate Register on a more frequent basis than the current annual reporting of the formal review of the register.

9. 	WORK OF THE CORPORATE RISK MANAGEMENT SUPPORT GROUP

9.1.	During the last year the CRMSG have met on 4 occasions and has been very pro-active. Minutes of meetings are posted on the Council’s intranet.

9.2. 	Issues covered throughout 2013 - 2014 have included discussions and actions with regard to the following;

- Directorate Risk Champions role in Project and Programme risk.

- Directorate Risk Champions role in Partnership arrangements.

- Directorate Risk Champions role in Budget Savings.

- Directorate Risk Champions responsibility with regard to co-ordinating the update of their Directorate Risk Register.

- Receiving reports from the Council’s Principal Health and Safety Advisor.

- Receiving reports from the Council’s Business Continuity Officer.

- Reviewing the main findings from Risk Management Directorate Audits carried out by Internal Audit in order to share best practice throughout the group and therefore all Directorates of the Council.

- Organise training to Council staff on risk management awareness.

- The continuous review of risks faced by the Council.

- The full peer review of the Corporate and Directorate risks.

- The review of the group’s terms of reference to ensure they reflect the group’s roles and function with regard to the management of risk.

- To develop the use of Action Plans for each corporate and directorate risk. The aim being that actions when completed will become additional controls.

- Provide update reports to the Audit Committee twice a year.

10.	EMBEDDING RISK IN THE COUNCILS CORPORATE PROCESSES

10.1	Risk Management continues to form part of the Council’s Key Business processes including:-

- Business planning

- Forward planning and resource allocation

- Development of policies and strategies

- Performance management

- Programme and project management

11.	TERMS OF REFERENCE

11.1	At the November 2013 meeting of the CRMSG the groups Terms of Reference were reviewed and a copy is attached to this report in Appendix C for information.

12.	RISK CHAMPIONS

12.1	Since the last annual review there have been a number of changes to the officers who fulfil the role of directorate risk champions. A list of the current risk champions and the directorates they represent is as follows for Members information:

Adults Health and Social Care	Iain Baines

Communities				Andrew Pitts

Chief Executives			Pete Smith

Children and Young Peoples	Anne Craven

Economy and Environment	Pat Smith

Public Health				Chris Cartwright

13.	RISK TRAINING

13.1	The Director of Economy and Environment has the responsibility for delivering the Corporate Asset and Facilities Management (CAFM) and the Town Centre Office Strategy (TCOS) programmes both of which contain a significant number of projects all aimed at delivering the programme outcomes. To ensure that risk was identified and recorded in a consistent manner training courses were delivered to all those staff involved in the projects to ensure that they were aware of their responsibilities for the management of risk and that all the projects used a common approach to the calculating and recording of risks to allow easy comparisons across the various project risk registers.

##### 14.	CONCLUSION

14.1	Risk management continues to be a key part of the Councils assurance and governance framework informing and supporting the Councils Annual Governance Statement. The Council continues to manage the changing risk environment working both within the Council and with other Local Authorities as appropriate to keep at the forefront of Risk Management.

14.2	Corporate and Directorate risks continue to be identified, assessed, monitored and reported to Members, Corporate Leadership Team  and Directorate Management Teams throughout the year as appropriate.

25th February 2014

FOR FURTHER INFORMATION ON THIS REPORT CONTACT:

Lisa Hinchliffe - Acting Assistant Head of Finance		Telephone 01422-393562

(Internal Audit, Risk Management, 		Email: Lisa.Hinchliffe@calderdale.gov.uk

and Insurance)

DOCUMENTS USED IN THE PREPARATION OF THE REPORT:

Risk Management Strategy

Corporate Risk Register

Directorate Risk Registers

Audit reports

Minutes of the Risk Management Group meetings

DOCUMENTS ARE AVAILABLE FOR INSPECTION AT:

Princess Buildings, Halifax

Appendix A

Calderdale Metropolitan Borough Council

Risk Management Strategy

2013 - 2014

1.	INTRODUCTION

1.1	Corporate Governance and Risk Management

The Council is committed to effective corporate governance arrangements and recognises that all aspects of risks to service delivery must be managed. In developing its corporate governance framework the Council has accepted the need for effective risk management and systems of internal control.  As part of this process the Council has developed a risk management strategy and framework for managing the key risks which the Council faces in an increasingly difficult economic environment.

1.2	The Council’s Approach to Risk Management

Risk refers to the uncertainty that surrounds future events and outcomes.  One definition of risk is: - ‘The possibility that an action or event will adversely or beneficially affect an organisation’s ability to achieve its objectives’.

The Council manages risk in a considered and controlled manner. The risk management strategy is designed to support the achievement of the Council’s aims and objectives in all areas of service delivery.

The Council will not tolerate risk avoidance and it is Council policy to encourage managers to identify, understand and manage risk and to learn how to work with risks to deliver greater benefits.

In turn managers within the Council must: understand the risks they face, their causes, how to control them, and their cost. They will manage the Council’s exposure to these risks within existing resources and within existing budgets.

1.3	Tangible or Non Tangible risk

Risks can be both tangible (e.g. threats to the Council’s assets) and intangible (e.g. risks to the Council’s reputation).  Risks may be inherent within the activities of the Council, or they may originate from the environment within which the Council operates.  The common feature of risks however, is their potential to reduce the effectiveness of the Council’s activities and/or to increase its costs. Around 80% of risks cannot be insured against or transferred and therefore require overt risk management measures. The management of risk is therefore integral to achieving the Council’s objectives.

1.4	Risk identification

The purpose of risk management is to identify those risks which may prevent the Council and its partners from achieving the Councils vision, its key work objectives, and its direction of travel and then putting procedures in place to minimise or manage that risk. Risk management is a corporate and systematic process for identifying, evaluating, addressing, and monitoring risks in a cost-effective way and ensuring staff have the necessary and appropriate skills to identify and assess the potential for risks to arise.

1.5	Risk negative / risk positive

Risk is not just negative where unmanaged risks prevent the council from achieving its objectives but can also be positive where well managed risks will allow the Council to exceed its objectives. Positive use of risk management allows the Council to undertake activities that have a higher level of risk but deliver a greater benefit. Where risks are identified, understood, and well managed, then the residual risk is reduced.

2.	RISK MANAGEMENT STATEMENT

In recognising the benefits to be derived from effective risk management, it is the Council’s policy that it is fully committed to the management of risks including adopting best practices in the identification, evaluation and control of risks in order to:

- Integrate risk management into the culture of the Council;

- Manage risk in accordance with best practice;

- Eliminate  or reduce risks to an acceptable level;

- Anticipate and respond to changing social, environmental and legislative requirements;

- Prevent injury and damage

- Raise awareness of the need for risk management.

By adopting this risk management statement the Council recognises that risk management is a key function in achieving its ambition and corporate priorities.  Complying with the Council’s policy will be achieved by:

- Establishing clear roles, responsibilities and reporting lines within the Council for risk management;

- Providing opportunities for shared learning on risk management across the Council;

- Establishing a mechanism for identifying and prioritising risk areas;

- Reinforcing the importance of effective risk management as part of the everyday work of employees;

- Incorporating risk management considerations into reviews of services;

- Incorporating risk management into the business plans of services; and

- Quality assuring the risk management arrangements of the Council’s programmes and projects on an ongoing basis.

These policy statements form part of the Council’s framework of corporate governance and internal control and together with the risk management framework they:-

- Explain the Council’s underlying approach to risk management,

- Document the roles and responsibilities of Elected Members, Corporate Leadship Team, the Corporate Risk Management Support Group, Directorate Management Teams, Service Managers and officers;

- Outline key aspects of the risk management process.

3.	ROLES AND RESPONSIBILITIES

- Elected Members have ultimate responsibility for risk management as risks can prevent the achievement of the Council’s objectives. In the context of risk management Members will exercise leadership; consider and adopt current and future risk management policies and strategies; and support and monitor the risk management process.

- Overall responsibility rests with the Chief Executive although the development and ongoing operation of risk management is delegated to the Assistant Head of Finance (Internal Audit, Risk Management, and Insurance)

- The Assistant Head of Finance oversees the detailed implementation of risk management processes throughout the Council, and with the Risk Manager maintains, reviews and reports on the Corporate Risk register.

- The Assistant Head of Finance with the Risk Manager will provide support, guidance, and advice on all risk management matters including the training of Members and officers.

- Directorate Risk Champions are responsible for the identification, assessment and management of those risks that occur within their respective directorates. This will be through the individual and peer group review of risks, the monitoring, review and reporting of the risk register, the assessment of new risks within the directorate,   and regular briefings to Directorate management teams ,

- A Corporate Risk Management Support Group (CRMSG) has been established with a membership which includes the Assistant Head of Finance, Risk Manager, Directorate Risk Champions, and representation from Business Continuity and Health and Safety. The Group implements the Risk Management processes of the Council within Directorates. The group is crucial to the implementation of a successful risk management programme through its role of facilitating, enabling and embedding all aspects of risk management, and being the focal point for all aspects of risk management including best practice.

- Service managers are accountable for the implementation and maintenance of sound risk management within their areas of responsibility, in line with Council policy and procedures.

- All council staff are required to create an environment where managing risk is accepted as the individual responsibility of each member of Council staff.

4.	RISK MANAGEMENT

The objective of risk management is to ensure that the assessment of risk becomes securely embedded in all the Council’s processes at all levels and that risks associated with alternative options are routinely considered as part of the decision making process. Appropriate guidance and training will be made available through the CRMSG.

5.	RISK MANAGEMENT FRAMEWORK

5.1	Objectives of the Framework

The framework outlines the process for identifying, assessing, and controlling risks associated with the achievement of the Council’s objectives.  It is a key element of the Council’s overall structure of internal control and corporate governance.  The aim of the framework is to balance the level of risk faced by the Council with the cost and effort necessary to control the risk, and to maintain controls so that the remaining level of exposure is acceptable to the Council.

The Council has identified the following stages in its risk management approach:

Recognition

Establishing that within the Council there are tangible and intangible risks and what those risks are.

Identification, assessment, evaluation

Identifying the risks to the delivery of the Council’s services through the evaluation and assessment of those services and highlighting where risks may occur and their potential for disruption to service delivery.

It is not practical to list all the risks facing the Council. Therefore a systematic assessment of all the identified risks allows those which are considered to be significant to be highlighted for inclusion on the Councils Corporate and/or Directorate Risk Registers for monitoring and mitigating actions.

Analysis and establish current capabilities

Risk evaluation, including prioritisation of risks by scoring the likelihood and impact of those risks to the Council, establishing the current controls which are in place to mitigate identified risks, re-evaluation of risk prioritisation with the controls in place, and linking risks to the Corporate and Directorate plans.

Developing action plans/implementation

Action planning to ensure residual risk is managed to an acceptable level and ensuring that where appropriate actions to further reduce the risks are put in place and included within action plans which are both implemented and time limited.

Measuring, monitoring, review, and reporting

This covers the frequent monitoring and regular reporting of all levels of risk exposure, including the managing of remedial actions, and the reviewing of the risk environment to ensure that the framework remains up to date.

5.2	Risk Assessment

5.2.1  	Recognition, Identification, assessment, evaluation

In order for the Council to focus on the key risks and establish action plans to mitigate risks all risks were assessed as part of the initial process for identifying significant risks for inclusion in the risk registers.

Subsequent to this all new risks must also be assessed and ranked in terms of their probability of occurrence, timing, and estimated impact on objectives to establish whether they also present sufficient risk to the Council to be included within Directorate risk registers or if the level of risk requires it on the Corporate Risk Register.

5.2.2.	Analysis and establish current capabilities

Following identification of any  significant risks which would affect the Council, the risks are scored by the Directorate Risk Champions in conjunction with the Assistant Head of Finance and the Risk Manager to establish the level of risk which would exist should there be no controls

Two factors are used to calculate the risk

    - The impact of the risk i.e. should the risk occur what is the effect on the Council. Impacts can be financial, operational, or reputational.

    - The likelihood of the risk occurring i.e. how frequently the risk may occur in a given period of time.

The impact and likelihood of each risk is assigned a score of High (3), Medium (2) or Low (1) according to the chances of its occurrence with no controls in place. This establishes the maximum chances of the risk occurring i.e. the gross risk:

| Likelihood |  | High | 3 | Likely to occur each year; |
| --- | --- | --- | --- | --- |
|  |  | Medium | 2 | Likely to occur in a 5 year time period; |
|  |  | Low | 1 | Unlikely to occur in a 5 year period; |
| Impact | Financial | High | 3 | Financial impact likely to exceed £2.5m; |
|  |  | Medium | 2 | Financial impact between £0.5m and £2.5m; |
|  |  | Low | 1 | Financial impact less than £0.5m. |
|  | Reputational | High | 3 | Adverse national media coverage |
|  |  | Medium | 2 | Adverse regional coverage |
|  |  | Low | 1 | Adverse local media coverage |
|  | Operational | High | 3 | Failure to provide statutory duties; |
|  |  | Medium | 2 | Significant disruption to provision of service |
|  |  | Low | 1 | Minor/short term disruption to services |

5.2.3	Controls

The current controls, if any, which are in place to manage the identified risks are then evaluated for their ability to mitigate the risk and then risk re-assessed for its impact and likelihood with the controls in place.  Assessment should take account of the degree of control over each risk, the cost/income impact and opportunities presented by risks.  The impact on other areas of Council activities should also be considered. This establishes the residual or nett risk.

5.2.4.	Developing action plans/implementation

If following the risk assessment process it is considered that the exposure to individual risks continues to remain unacceptable then actions to manage each risk should be agreed and recorded against each risk in the appropriate risk register to ensure that the risk is kept under active review, and each action has a responsible officer to ensure necessary work is carried out. Where actions are time limited then a target date for the mitigating action is to be included.

Depending on the likelihood and impact of the risk, and the adequacy of existing controls, other control strategies could include:

- Modify the risk – changing operations so that the anticipated event cannot occur;

- Accept the risk – and be prepared to manage the consequences;

- Reduce/eliminate the risk – changing operations so that the likelihood is reduced or the impact is minimised;

- Transfer the risk – by arranging for another party to take over the risk, usually contractually, or through insurance;

- Ignore the risk – where it is assessed to have minimal impact and likelihood of occurring; and

- Manage the risk – mitigate the risk by putting in place appropriate internal controls to better manage the outcome.

5.2.5.	 Measuring, monitoring, review, and reporting

Monitoring of risks, controls and actions should be undertaken continuously by the nominated lead officers for the risk assisted by the Risk Manager and Directorate Risk Champions to ensure that planned actions are having the desired effects and to assess whether changes are needed.

The process, of ensuring effective risk management is in place, is monitored by the Assistant Head of Finance (Internal Audit, Insurance and Risk Management) and the Risk Manager and then reported to the Corporate Risk Management Support Group who in turn report to the Corporate Leadership Team and the Audit Committee twice a year.

#### Directorate risk register monitoring reports are presented to Members of the appropriate Scrutiny panel in the form of a briefing note on an appropriate timescale agreed with the individual Scrutiny panels.

#### The Corporate risk register is reported to the Audit Committee on an annual cycle with a six monthly update reporting any changes over the previous six months.

#### The Head of Finance will include a Head of Internal Audit’s opinion within the Annual Governance Statement on the strength of systems of control and governance arrangements each year. The Annual Governance Statement will accompany the Council’s published statement of accounts.

5.2.6	Review of the framework for Risk Management

The Risk Management Framework is reviewed regularly by the Risk Manager and the CRMSG to ensure its direction and pace is consistent with developments, any changes in objectives and activities, and the results of monitoring carried out.

5.2.7	Implementing Risk Management Arrangements

The CRMSG is responsible for leading the overall implementation process.

6.	RISK MANAGEMENT AS PART OF THE SYSTEMS OF INTERNAL CONTROL

The Councils systems of internal control incorporate a number of risk management elements that form part of the risk framework and facilitate effective and efficient operations, enabling the Council to respond to a variety of operational, financial, and commercial risks. These elements include:

- Corporate Risk Register. This facilitates the identification, assessment and ongoing monitoring of risks significant to the Council.  The document is reviewed continually by the Assistant Head of Finance and the Risk Manager with emerging risks included as required and formally reported every three months to the Corporate Leadership Team and Audit Committee.

- Directorate Risk Registers. Directorate Risk Champions ensure that significant risks in their Directorate areas are identified, assessed and monitored.  The register is formally reviewed every three months and reported to the Directorate Management Team prior to it being reported to the appropriate Scrutiny Panel. Emerging risks are included as necessary and improvement action plans and risk indicators are monitored as necessary by Directorates and the Risk Management Group.

- Project, programme, performance and partnership registers. As part of the continual process to improve risk management all projects, programmes, performance targets and partnerships are to review the need for a risk register outlining the potential risks faced by that programme, project, etc when being set up. Where a register is considered necessary then the register will be reported to the appropriate board or monitoring group on a regular basis commensurate with the time span of the project, programme, partnership or performance target.

- Audit Committee. Audit Committee receives an annual report on risk management, the progress made, the risk challenges facing the Council and amendments to the Corporate Risk register and Corporate Risk Strategy. There is also a 6 monthly update report between the annual reports. The Audit Committee is therefore well-placed to consider the effectiveness of the internal control systems, including the Council’s system for the management of risk.

- Quality Assurance Internal Audit is an important element of the internal control process.  Apart from its normal programme of work, Internal Audit is responsible for the reviewing the effectiveness of the internal control systems within the Council for its projects and programmes. External Audit provides feedback to the Council on the operation of the internal financial controls reviewed as part of their annual audit.

Risk Management Corporate Support Group

Audit Committee

Significant   Corporate     Risks drives Audit activity

Significant Directorate

risks

Operational activity

Corporate partnerships, IT systems, Council portfolio of   programmes

Significant  partnerships,

Council & Directorate projects, programmes and performance targets

Significant Operational risks

CABINE

Service Managers

Directorate Risk Champions

T, AUDIT COMMITTEE

Programme, partnership , project and performance risks monitored , reviewed and managed by appropriate officers and officer groups and reported regularly to the lead directorate management team. High risks to be considered for inclusion in the Directorate risk register

Programme risk feeds into the process

Programme risks and risk registers monitored by programme board

Corporate risk register Part A

Reviewed and reported risks

Corporate risk register Part B

Reviewed only risks

Reviewed as part of a continual dynamic process and reported to the Audit Committee every 6 months with interim updates as required and appropriate

Five Directorate Risk registers containing risks appropriate to each directorate and risks brought forward from project, performance, partnership and project registers.

Reviewed quarterly by Directorate DMTs and reported to Scrutiny Panels

High risks within Directorate registers which have cross council implications or actions considered for inclusion in the Corporate Risk register

The Corporate Risk Management Support Group through its Risk Champions has overall responsibility for risk management and the peer review, management and implementation of actions to achieve the management of risk,

Reporting reviews of risk registers to the appropriate scrutiny panel through briefing reports

Actions from Scrutiny Panel feeds back into the appropriate registers

Reported reviews of corporate risk to the Audit Committee.

Actions from Audit Committee feed back into the corporate register via the Corporate Risk Group

Projects risks and project risk registers monitored by project board

Partnership risks and significant partnership registers monitored by

appropriate partnership board

Performance management risks monitored by performance management officers

Appendix B

Corporate Risk Register

Parts A & B

Version 22

March 2014

| ##### Risk Map of Corporate risks (NET) |  |  |  |  |
| --- | --- | --- | --- | --- |
| ##### PART A |  |  |  |  |
| IMPACT> | 3 | CR031, | CR009, CR010, CR016. CR034, CR037 | CR007, CR015, CR040, CR042, CR043, |
|  | 2 |  | CR041, CR045 | CR021, CR044 |
|  | 1 |  |  |  |
|  |  | 1 | 2 | 3 |
| ##### LIKELIHOOD > |  |  |  |  |

| Risks in severity order | Risk No | Gross risk | Net risk | Priority |
| --- | --- | --- | --- | --- |
| Available resources inadequate to meet corporate priorities | CR 007 | 9 | 9 | HIGH |
| Local recession | CR 015 | 6 | 9 | HIGH |
| Failure to deliver projects effectively | CR040 | 9 | 9 | HIGH |
| Building infrastructure management | CR 042 | 9 | 9 | HIGH |
| Severe weather | CR 043 | 9 | 9 | HIGH |
| Services provided to schools becoming academies | CR 044 | 9 | 6 | MEDIUM |
| Inability to recruit and retain key staff | CR 010 | 9 | 6 | MEDIUM |
| Increasing energy costs / supply restrictions | CR 034 | 9 | 6 | MEDIUM |
| Failure of a Partnership | CR 037 | 9 | 6 | MEDIUM |
| Failure to appreciate demographic change | CR 021 | 6 | 6 | MEDIUM |
| Loss of Major supplier or contractor | CR 009 | 6 | 6 | MEDIUM |
| Failure to deliver people’s expectations | CR 041 | 6 | 6 | MEDIUM |
| Negative/counterproductive press/media publicity | CR 016 | 6 | 6 | MEDIUM |
| Delivery of the Tour de France | CR045 | 6 | 4 | MEDIUM |
| Not implementing change required to drive performance improvement | CR 031 | 6 | 3 | LOW |

| ##### Risk Map of Corporate risks (NET) |  |  |  |  |
| --- | --- | --- | --- | --- |
| ##### PART B |  |  |  |  |
| IMPACT> | 3 | CR 029 | CR 011 CR 012 CR 014 CR 030, CR 035 |  |
|  | 2 |  | CR 039 |  |
|  | 1 |  |  | CR 025 |
|  |  | 1 | 2 | 3 |
| ##### LIKELIHOOD > |  |  |  |  |

| Risks in severity order | Risk No | Gross risk | Net risk | Priority |
| --- | --- | --- | --- | --- |
| Civil Disorder | CR 011 | 9 | 6 | MEDIUM |
| Crime and Disorder | CR 012 | 9 | 6 | MEDIUM |
| Failure to meet needs of diverse communities | CR 014 | 9 | 6 | MEDIUM |
| Corporate manslaughter | CR 030 | 9 | 6 | MEDIUM |
| Information security | CR 035 | 9 | 6 | MEDIUM |
| Planning for major peace time disaster | CR 039 | 6 | 4 | MEDIUM |
| Litigation | CR 025 | 9 | 3 | LOW |
| Contamination and Pollution | CR 029 | 9 | 3 | LOW |

Corporate Risk Register

Part A

| Risk | Available resources inadequate to meet corporate priorities | CR 007 |
| --- | --- | --- |
| ## Created | April 2003 |  |
| ## Priority | # HIGH |  |
| Reporting | # Audit committee |  |
| ## Service | Chief Executives Office |  |
| Lead Officer | Head of Finance |  |
| Head of Service | Head of Finance |  |
| ### Links to Performance Framework | Building Ambition for Calderdale - Efficiency |  |
| Trigger | Changes in government funding leading to shortfall Comprehensive spending review Budget decisions Inability to attract external funding Reduction in saleable assets Insufficient capacity to deliver priorities Inability to recruit and retain key staff Recession leading to reduced income from planning applications and other activities Changes in welfare benefits system leading to increased benefit and support aid claims |  |
| Consequence | Failure to deliver services – statutory and other Inadequate pace of modernisation Excessive workloads Intervention Poor inspections Stakeholder concerns Staff turnover and low staff morale Unable to deliver projects and programmes Failure to deliver budget council savings |  |
| ### Likelihood | 3 |  |
| Impact | 3 |  |
| Gross Risk Score | 9 |  |
| Controls in Place | Balanced budget Medium term financial strategy Budget Review Groups Budget consultation process Service Plans Budget Priorities Scrutiny External Agencies Audit Recruitment and retention policy / Personnel Policies Human Resources Strategy Exit interviews |  |
| ### Likelihood | 3 |  |
| Impact | 3 |  |
| Net Risk Score | 9 |  |
| Actions to reduce risk and increase controls | Three year financial strategy ensures, in setting annual budget, resources clearly allocated to priorities. |  |
| Date reviewed | January 2014 |  |
| Date revised | March 2013 (Audit Committee) |  |
| Date removed |  |  |
| Reason for removal |  |  |

| Risk | ### Loss of a major partner, supplier or contractor | ### CR 009 |
| --- | --- | --- |
| ## Created | April 2003 |  |
| ## Priority | ### MEDIUM |  |
| Reporting | # Audit committee |  |
| ## Service | Chief Executives Office |  |
| Lead Officer | Head of Democratic & Partnership Services |  |
| Head of Service | Chief Executive |  |
| ### Links to Performance Framework | Building Ambition for Calderdale - Resilience |  |
| Trigger | Major supplier or contractor ceases to trade due to its financial circumstances or change in Government policy Major supplier or contractor ceases to deal with the Council due to a change in its service delivery policy |  |
| ### Consequence | Core service cannot be delivered Additional cost of finding an alternative provider Customer dissatisfaction Adverse publicity and impact on reputation Financial loss to the Council through process costs, loss of revenue or grant aid. Legal disputes Insurance claims |  |
| ### Likelihood | 2 |  |
| Impact | 3 |  |
| Gross Risk Score | 6 |  |
| Controls in Place | Approved list of contractors Procurement Policy and Strategy Constitution Contract Procedure Rules (Amended December 2010) Contract monitoring arrangements Scrutiny function of Members Bonds Application of contract procedure and contract monitoring arrangements Reporting to Members, SMT and DMT’s to maintain awareness Regular monitoring of existing partner, supplier or contractor to ensure still financially viable. Robust selection procedures |  |
| ### Likelihood | 2 |  |
| Impact | 3 |  |
| Net Risk Score | 6 |  |
| Actions to reduce risk and increase controls | Sustainable Procurement strategy being developed to encourage local small business and social enterprises to supply the council |  |
| Date reviewed | January 2014 |  |
| Date revised | January 2013 |  |
| Reasons for revision | Change of lead Service |  |
| Date removed |  |  |
| Reason for removal |  |  |

| Risk | #### Inability to recruit and retain key staff | #### CR 010 |
| --- | --- | --- |
| ## Created | April 2003 |  |
| ## Priority | ### MEDIUM |  |
| Reporting | # Audit committee |  |
| ## Service | All |  |
| Lead Officer | Head of Human Resources |  |
| Head of Service | Director of Communities |  |
| ### Links to Performance Framework | Building Ambition for Calderdale - Resilience |  |
| Trigger | Higher salaries offered by other organisations for equivalent work Inability to recruit suitable staff and continual re-advertising of key posts Lack of training or development opportunities Poor staff work life balance Uncertainty within transformation Council not seen as a good employer |  |
| Consequence | Failure to deliver services and meet requirements Failure to deliver the Council’s Vision Low staff morale leading to increased staff absences Poor audit inspection reports and assessments Possibility of intervention Council not seen as the employer of choice Low numbers and poor quality of applicants for council posts |  |
| ### Likelihood | 3 |  |
| Impact | 3 |  |
| Gross Risk Score | 9 |  |
| Controls in Place | Exit interviews Reviews of pay structures and pay awards Staff performance development plans (PDPs) Monitoring of application rates Monitoring of leavers Human resources strategy Personnel Policies Succession planning Workforce strategy |  |
| ### Likelihood | 2 |  |
| Impact | 3 |  |
| Net Risk Score | 6 |  |
| Actions to reduce risk and increase controls | Undertake staff surveys and address concerns raised |  |
| Date reviewed | January 2014 |  |
| Date revised | January 2014 |  |
| Reasons for revision | Change in Head of Service |  |
| Date removed |  |  |
| Reason for removal |  |  |

| Risk | Impacts arising from a local or national recession | ## CR 015 |
| --- | --- | --- |
| ## Created | April 2003 |  |
| ## Priority | # HIGH |  |
| Reporting | # Audit committee |  |
| ## Service | All |  |
| Lead Officer | Head of Housing, Environment and Renewal |  |
| Head of Service | Director - Economy and Environment |  |
| ### Links to Performance Framework | Building Ambition for Calderdale - Growth |  |
| Trigger | Closure of major employer Public Sector jobs cuts Reduction of public sector support infrastructure e.g. Business Link, Yorkshire Forward National economic problems i.e. recession |  |
| Consequence | High unemployment Increased costs to the council through benefit claims Council Tax/NNDR debts increased Free School Meals increase Increased demands on the Council and Voluntary Agency services Increased Crime levels and possible Civil Disorder Reduced income to the Council Increased insurance claims Increase in Fraud Demand for no Council Tax increase and even a reduction Reduced Central Government funding |  |
| Likelihood | 3 |  |
| Impact | 3 |  |
| Gross Risk Score | 9 |  |
| Controls in Place | Economy and Enterprise Strategy Leeds City Region Local Enterprise Partnership Support Fund and grants available to local businesses/ support from ETF for projects Work with partners to develop networks of support for businesses. |  |
| ### Likelihood | 3 |  |
| Impact | 3 |  |
| Net Risk Score | 9 |  |
| Actions to reduce risk and increase controls | Strategic review of economic strategy More effective methods of working to allow increased number of claims to be dealt with by same number of staff. Grant aid available for businesses which are in difficulty. Partnership response to welfare reform Economic Task Force activity |  |
| Date reviewed | January 2014 |  |
| Date revised | January 2013 |  |
| Reasons for revision | Updated actions |  |
| Date removed |  |  |
| Reason for removal |  |  |

| Risk | Negative/counterproductive press/media publicity | CR016 |
| --- | --- | --- |
| ## Created | April 2003 |  |
| ## Priority | # Medium |  |
| Reporting | # Audit committee |  |
| ## Service | Communities |  |
| Lead Officer | Head of Customer Services |  |
| Head of Service Links to Performance Framework | Director – Communities Building Ambition for Calderdale - Efficiency |  |
| Trigger | Negative article/s in local and national newspaper reports Negative reports broadcast on local and national TV/radio |  |
| Consequence | Loss of reputation with peers, public, partners and regulatory bodies False and inaccurate information reported and being unchallenged Loss of confidence in the Council by the public, peers, partners and regulatory bodies Loss of funding from partners/external bodies Council becomes a less attractive employer in the employment market place ‘Council bashing’ becomes an accepted practice leading to continual erosion of reputation and decrease in public satisfaction survey score |  |
| Likelihood | 3 |  |
| Impact | 2 |  |
| Gross Risk Score | 6 |  |
| Controls in Place | Corporate Communications Service Plan Media protocols Effective Media evaluation and planning Centralised Communications Team for advice, guidance and media support Freedom of Information, Data Protection Equality and Diversity Policy Corporate Communications Service Plan Corporate complaints database |  |
| Likelihood | 3 |  |
| Impact | 2 |  |
| Net Risk Score | 6 |  |
| Strategies to reduce risk and increase controls | Forward Plan |  |
| Date reviewed | January 2014 |  |
| Date revised | February 2013 |  |
| Reasons for revision |  |  |
| Date removed |  |  |
| Reason for removal |  |  |

| Risk | ### Failure to appreciate or plan for demographic change | ### CR 021 |
| --- | --- | --- |
| ## Created | April 2003 |  |
| ## Priority | # MEDIUM |  |
| Reporting | # Audit committee |  |
| ## Service | Chief Executives Office |  |
| Lead Officer | Chief Executive |  |
| Head of Service | Chief Executive |  |
| ### Links to Performance Framework | Building Ambition for Calderdale - Growth |  |
| Trigger | Education results Mismatch between housing demand and provision. Mismatch between employment demand and provision. Service provision does not meet public needs Change in age profile of population Closure of significant employer Migration between authorities Migration between areas within the authority |  |
| Consequence | RSG/FSS Funding Impact on Services Budget issues and need for realignment Employment rates Housing availability Poor performance, reputation loss and potentially intervention. |  |
| ### Likelihood | 2 |  |
| Impact | 3 |  |
| Gross Risk Score | 6 |  |
| Controls in Place | Corporate Planning framework and Corporate Priorities Provision of schools and school places Budget and Medium Term Financial Strategy Regeneration strategy Service Plans Health and Inequalities Action Plan Reporting of reviewed risk registers to CLT and DMT to increase awareness |  |
| ### Likelihood | 3 |  |
| Impact | 2 |  |
| Net Risk Score | 6 |  |
| Actions to reduce risk and increase controls | Schools and other capital programmes Economic Regeneration Strategy |  |
| Date reviewed | January 2014 |  |
| Date revised | January 2013 |  |
| Reasons for revision |  |  |
| Date removed |  |  |
| Reason for removal |  |  |

| Risk | Not implementing change required to drive performance improvement | CR031 |
| --- | --- | --- |
| ## Created | # April 2003 |  |
| ## Priority | # LOW |  |
| Reporting | # Audit committee |  |
| ## Service | Chief Executive’s Office |  |
| Lead Officer | Head of Business Change and Performance Management |  |
| Head of Service Links to Performance Framework | Director of Communities Ambition for Calderdale - Sustainability |  |
| Trigger | Failure to meet Key Performance Targets Lack of understanding of key performance issues and Benchmark statistics Failure to plan adequately in order to improve performance Failure to monitor progress of improvement plans and impacts on performance indicators Failure to evidence improvement Failure to implement Lean & Demand Management improvements Low uptake in terms of Lean & Demand Management Accreditation |  |
| Consequence | Failure to deliver the Council’s Corporate Ambitions Failure to meet Efficiency Targets and Budget Saving requirements Failure to make most effective use of resources Impact on Customer Satisfaction levels Poor audit/inspection outcomes Loss of reputation with peers, partners and the public |  |
| Likelihood | 2 |  |
| Impact | 3 |  |
| Gross Risk Score | 6 |  |
| Controls in Place | Monitoring of improvement via the MAD Performance System, Chief Executive 1:1s and quarterly SMT meetings Strengthening of the improvement support role via the implementation of Admin Review recommendations (expected April 2012) Shared performance management framework for strategic partnerships implemented LEAN Process Improvement training for all colleagues ‘Making a Difference’ collection of evidence system Lean Accreditation to Level 2 included in Director and Head of Service job descriptions |  |
| Likelihood | 1 |  |
| Impact | 3 |  |
| Net Risk Score | 3 |  |
| Strategies to reduce risk and increase controls | Business Improvement Plan Revised Corporate Performance Management Framework |  |
| Date reviewed | January 2014 |  |
| Date revised | November 2013 |  |
| Reasons for revision | Reflect strengthening of performance reporting to CLT and Cabinet plus implementation of Demand Management initiative |  |
| Date removed |  |  |
| Reason for removal |  |  |

| Risk | Increasing energy costs/ restrictions of supply | CR 034 |
| --- | --- | --- |
| ## Date created | May 2006 |  |
| ## Priority | # Medium |  |
| Reporting | # Audit committee |  |
| ## Service | Economy and Environment |  |
| Lead Officer | Lead for CAFM |  |
| Head of Service | Director - Economy and Environment |  |
| ### Links to Performance Framework | Ambition for Calderdale - Sustainability |  |
| Trigger | Significant rise in energy costs either in gas or fuel oils /petrol Reduction in energy supply due to sanctions, strike action or global supply instability. Reduction in energy monitoring leading to unrestricted energy use |  |
| Consequence | Uncontrolled overspend on energy budgets with consequent impact on budgets Temporary closure of facilities with high energy requirement leading to a consequent impact on service provision. Reduction in the provision of services which are reliant on the use of vehicles or powered machinery. Impact on the elderly and those with low income leading to additional calls on Council budgets and Council services to assist those at risk Fuel crisis requiring implementation of the Councils fuel crisis action plan with consequent impact on service provision |  |
| ### Likelihood | 3 |  |
| Impact | 3 |  |
| Gross Risk Score | 9 |  |
| Controls in Place | Business Continuity Officer in post Business Continuity in place as part of Civil Contingencies Business Continuity recovery group in place Increased provision within the Medium Term Financial Strategy Corporate Procurement Unit established to review energy cost and procurement Business Continuity and Business Recovery plans to be produced for all services Energy provided through YPO Framework Service agreement – the most secure way to purchase energy Energy costs to increase 4.1% electric and 1.2% gas in 2014/15. Increases in prices will be offset by reduced energy consumption |  |
| ### Likelihood | 3 |  |
| Impact | 2 |  |
| Net Risk Score | 6 |  |
| Actions to reduce risk and increase controls | Awareness raising of fuel saving measures through energy conservation service Develop Sustainable Procurement Strategy |  |
| Date reviewed | January 2014 |  |
| Date revised | January 2014 |  |
| Reasons for revision | Updated controls |  |
| Date removed |  |  |
| Reason for removal |  |  |

| Risk | Failure of a Partnership | #### CR 037 |
| --- | --- | --- |
| ## Date created | 8th September 2007 |  |
| ## Priority | # MEDIUM |  |
| Reporting | # Audit committee |  |
| ## Service | All |  |
| Lead Officer | Head of Democratic & Partnership Services , |  |
| Head of Service | Chief Executive |  |
| ### Links to Performance Framework | Building Ambition for Calderdale - Resilience |  |
| Trigger | A partner encounters financial difficulties and is unable to continue within the partnership Political change at local or national level. Under achievement of reward or mandatory performance targets. Loss of a key officer from within the partnership and / or board Data quality management and data system incompatibility Not having an exit strategy is in place for the partnership Lack of a central partnership register outlining expectations of the partnership Differing needs/agendas of the partners Inadequate monitoring systems Failure to understand the legal and financial liabilities |  |
| Consequence | Increased costs to the Council. of continuing to provide service without partner Failure to achieve performance targets Failure of Partnership Litigation Duplication / omission of activity |  |
| ### Likelihood | 3 |  |
| Impact | 3 |  |
| Gross Risk Score | 9 |  |
| Controls in Place | Establish significant partnership register Risk management of partnerships Risk assessment of performance targets Nominated Lead officers for themes Appropriate risk training Health and Wellbeing Board |  |
| ### Likelihood | 2 |  |
| Impact | 3 |  |
| Net Risk Score | 6 |  |
| Actions to reduce risk and increase controls | Joint risk registers Ownership of risk by partnership boards Effective review and reporting process |  |
| Date Reviewed | January 2014 |  |
| Date revised | February 2011 |  |
| Reasons for revision |  |  |
| Date removed |  |  |
| Reason for removal |  |  |

| Risk | Failure to deliver projects effectively | CR040 |
| --- | --- | --- |
| ## Date created | September 2008 |  |
| ## Priority | # High |  |
| Reporting | # Audit committee |  |
| ## Service | Chief Executives Office |  |
| Lead Officer | Head of Business Change and Performance Management |  |
| Head of Service | Director of Communities |  |
| ### Links to Performance Framework | Building Ambition for Calderdale - Efficiency |  |
| Trigger | Increasing number of projects and insufficient resources to deliver those projects leads to project failure and inability to continue to deliver existing council services effectively and efficiently. Projects not effectively budgeted or resourced Poor communication and a lack of leadership Lack of coordination between overlapping projects Unclear / unrealistic expectations and deadlines and a lack of / poor forward planning Financial Limitations and a lack of Project Management Methodology |  |
| Consequence | Failure to deliver projects on time and to budget Major project overruns leading to significant loss of reputation. Increased project costs lead to budget reductions for other services Insufficient staff to complete projects and deliver current service leads to service failure or project delay Inadequate existing service delivery |  |
| ### Likelihood | 3 |  |
| Impact | 3 |  |
| Gross Risk Score | 9 |  |
| Controls in Place | Calderdale Way Approach to Project management Procurement Gateway Process Council’s decision making process Council’s Scrutiny process Monitoring of delivery plan progress via the Performance Management System, Chief Executive 1:1s Quarterly CLT and Cabinet meetings. Mandatory use of the Councils project management systems Regular and effective project reviews and reporting of projects and issues surrounding those projects to project boards and DMT / CMT Continuous risk assessment of the project process and programme. Ownership of the project process at project board and Senior Officer level Clear objectives and outcomes. Effective and adequate resourcing of projects Implementation of PMIS Monitoring of delivery plans via the Performance Management System Procurement Gateway Process |  |
| ### Likelihood | 3 |  |
| Impact | 3 |  |
| Net Risk Score | 9 |  |
| Actions to reduce risk and increase controls |  |  |
| Date reviewed | January 2014 |  |
| Date revised | January 2014 |  |
| Reasons for revision | Reflect growing demand for project related support and strengthening of performance reporting to CLT and Cabinet |  |
| Date removed |  |  |
| Reason for removal |  |  |

| Risk | Failure to deliver people’s expectations | CR041 |
| --- | --- | --- |
| ## Date created | September 2008 |  |
| ## Priority | # Medium |  |
| Reporting | # Audit committee |  |
| ## Service | Chief Executives Office |  |
| Lead Officer | Chief Executive |  |
| Head of Service | Chief Executive |  |
| ### Links to Performance Framework | Building Ambition for Calderdale - Ambition |  |
| Trigger | Failure to deliver the expectations of the people of Calderdale Insufficient evidence of understanding customer needs Targets to ‘stretch’ achievement or ‘narrow the gap’ not achieved Changes to agreed delivery plans impacting upon performance |  |
| Consequence | Loss of reputation leading to significant loss of funding Negative impact on partnership working |  |
| ### Likelihood | 2 |  |
| Impact | 3 |  |
| Gross Risk Score | 6 |  |
| Controls in Place | Calderdale Improvement Programme Communications Strategy New corporate performance management framework Regular updates / monitoring of delivery plans Performance monitoring process Consultation with stakeholders |  |
| ### Likelihood | 3 |  |
| Impact | 2 |  |
| Net Risk Score | 6 |  |
| Actions to reduce risk and increase controls | Assessment of customer understanding across Partners |  |
| Date reviewed | January 2014 |  |
| Date revised | February 2012 |  |
| Reasons for revision | Inclusion of additional control re communications strategy |  |
| Date removed |  |  |
| Reason for removal |  |  |

| Risk | Building infrastructure management | CR 042 |
| --- | --- | --- |
| ## Date created | April 2009 |  |
| Priority | HIGH |  |
| Reporting | # Audit committee |  |
| ## Service | Economy and Environment |  |
| Lead Officer | Lead for CAFM |  |
| Head of Service | Director - Economy and Environment |  |
| ### Links to Performance Framework | Ambition for Calderdale - Sustainability |  |
| Trigger | Essential repair and maintenance not being carried out through a lack of clarity over responsibility and funding. Inadequate maintenance where a service or directorates has insufficient budget for maintenance. A lack of co-ordination leading to inaction on repairs. Inadequate leasing arrangements leaving the responsibility for building repair and maintenance with the Council. Lack of decision and /or funding for the demolition, sale, or restoration of an unused building leads to the structure becoming unsound. Loss of building due to malicious fire setting Loss of building due to non arrival of a fire appliance due to the changes in the fire service structure |  |
| Consequence | Complete or partial collapse/loss of a building Injury or even loss of life to members of the public and/or CMBC staff. Insurance claims. Loss of workplace or service provision. Loss of community provision. Loss of building, equipment, furniture, assets. Damage to surrounding areas. Need to invoke business continuity plan. Reputational damage |  |
| ### Likelihood | 3 |  |
| Impact | 3 |  |
| Gross Risk Score | 9 |  |
| Controls in Place | Capital bids for budgets to repair and renovate buildings. Programme of increased Health and Safety Assurance work developed for schools and corporate buildings Reports to Cabinet. Additional funding for critical structural repairs Disposal of surplus buildings Reduction in the councils building portfolio through disposal programmes |  |
| ### Likelihood | 3 |  |
| Impact | 3 |  |
| Net Risk Score | 9 |  |
| Actions to reduce risk and increase controls | Asset management plan and review of Asset Management controls including centralisation of control of assets Centralised budgets Increased role of Members Capital Programme working Party to engage Member support for decisions relating to building assets . Close monitoring of the changes to the fire service provision in Calderdale |  |
| Date reviewed | January 2014 |  |
| Date revised | January 2013 |  |
| Reasons for revision | Annual review |  |
| Date removed |  |  |
| Reason for removal |  |  |

| Risk | Severe Weather | CR 043 |
| --- | --- | --- |
| ## Date created | February 2012 |  |
| ## Priority | # High |  |
| Reporting | # Audit committee |  |
| ## Service | Communities |  |
| Lead Officer | Head of Neighbourhoods |  |
| Head of Service | Director - Economy and Environment |  |
| ### Links to Performance Framework | Ambition for Calderdale - Resilience |  |
| Trigger | High winds Severe and prolonged periods of cold weather Heavy snowfall Heavy rainfall leading to severe flooding of low lying areas Budget reductions for snow clearing and gritting |  |
| Consequence | Council fails to respond due to inadequate plans in place leading to injury, death, homelessness, and disruption to services. Failure of a significant part of the councils service Major injury or loss of life from cold and icy conditions particularly among the elderly Damage to industrial infrastructure from flooding Homelessness due to flood damage Increased claims on the Council for damage and injury to staff and the public Increase in the number of houses and businesses unable to get property insurance Property values reduced due to flooding blight |  |
| ### Likelihood | 3 |  |
| Impact | 3 |  |
| Gross Risk Score | 9 |  |
| Controls in Place | Corporate Emergency incident plan in place Specific Emergency Plans and Arrangements in place Business continuity plans in place Business impact analysis completed Salt stocks maintained at a more than adequate level for the duration of the winter period Insurance Policies Action plans to be tested to ensure that they link with the emergency services Constant review, updating and reporting of Emergency plans to make sure that information is current and usable. |  |
| ### Likelihood | 3 |  |
| Impact | 3 |  |
| Net Risk Score | 9 |  |
| Actions to reduce risk and increase controls | Training key staff for emergencies, Plans in place for dealing with severe weather New partnership - Calderdale flood recovery programme |  |
| Date reviewed | January2014 |  |
| Date revised | March 2013 (Audit Committee) |  |
| Reasons for revision |  |  |
| Date removed |  |  |
| Reason for removal |  |  |

| Risk | Services that are provided to schools becoming academies. | CR 044 |
| --- | --- | --- |
| ## Created | June 2012 |  |
| ## Priority | # MEDIUM |  |
| Reporting | # Audit committee |  |
| ## Service | All |  |
| Lead Officer | Director of Children and Young People’s Services |  |
| Head of Service | Head of Learning Services |  |
| ### Links to Performance Framework | Building Ambition for Calderdale – Efficiency; Delivering efficiency and effectiveness in public services |  |
| Trigger | DfE agenda for increased number of academies Academies choose to buy services from other providers More freedoms and autonomy for academies External providers market their services to academies Real terms reductions in school and Local Authority funding Insufficient capacity to deliver services to schools, (knowledge and experience.) Inability to recruit and retain key staff to provide services to schools |  |
| Consequence | Loss of income to meet the MTFS forecast School/academy needs not met as services are not available Local Authority services become unsustainable Support and challenge from Local Authority is diminished for key support services Specialist knowledge not available to provide services to academies Excessive workloads for fewer staff |  |
| ### Likelihood | 3 |  |
| Impact | 3 |  |
| Gross Risk Score | 9 |  |
| Controls in Place | Services to Schools Action Plan Directories of Services for both schools and academies Services to Schools Strategic Board in place Account Manager in place Medium Term Financial Strategy Annual school feedback survey Close financial monitoring Service Plans CYPS Scrutiny panel |  |
| ### Likelihood | 3 |  |
| Impact | 2 |  |
| Net Risk Score | 6 |  |
| Actions to reduce risk and increase controls | Continue to promote Calderdale’s services (market place events, briefings, cluster working for school business managers), continue to monitor school feedback, and continue to develop service management skills (including financial management). |  |
| Date reviewed | November 2013 |  |
| Date revised | January 2014 |  |
| Date removed |  |  |
| Reason for removal |  |  |

| Risk | Delivery of the Tour de France | ## CR 045 |
| --- | --- | --- |
| ## Created | January 2014 |  |
| ## Priority | # MEDIUM |  |
| Reporting | # Audit committee |  |
| ## Service | All |  |
| Lead Officer | Head of Neighbourhoods |  |
| Head of Service | Director – Communities and Business Change |  |
| ### Links to Performance Framework | Cabinet priorities / Calderdale Ambition – Maintaining delivery of priority local services and Tackling inequalities in health and wellbeing. |  |
| Trigger | Regional management – impacting on communication TDF Budget allocation Staff retention Infrastructure |  |
| Consequence | Capacity to deliver services - event Overspending on budget Reduction in knowledge base Unable to cope with increase in crowds to the area |  |
| Likelihood | 2 |  |
| Impact | 3 |  |
| Gross Risk Score | 6 |  |
| Controls in Place | Relevant officers on appropriate regional groups Strategic Board in place to receive information and monitor Share point for communications and document to assist backfill Traffic management and transportations plans underpinned by effective communications |  |
| ### Likelihood | 2 |  |
| Impact | 2 |  |
| Net Risk Score | 4 |  |
| Actions to reduce risk and increase controls | As in controls in addition a more detailed TDF specific risk assessment compiled across the region with local implications added. |  |
| Date reviewed | January 2014 |  |
| Date revised | January 2014 |  |
| Reasons for revision | Changes to controls and actions |  |
| Date removed |  |  |
| Reason for removal |  |  |

Corporate Risk Register

PART B

| Risk | #### Civil Disorder | #### CR 011 |  |  |
| --- | --- | --- | --- | --- |
| ### Created | April 2003 |  |  |  |
| ## Priority | # MEDIUM |  |  |  |
| Reporting | # Audit committee |  |  |  |
| ## Service | Neighbourhoods |  |  |  |
| Lead Officer | Head of Neighbourhoods |  |  |  |
| Head of Service | Director - Communities |  |  |  |
| ### Links to Performance | Cabinet priorities / Calderdale Ambition – Maintaining delivery of priority local services |  |  |  |
| Trigger | Major street disturbances in Calderdale or other areas Disaffected communities New powers and/or legislation National or local criminal activities External factors e.g. War, Political/religious extremism Rumour spreading / perception of inequality of service Prominent Calendar Dates of Events (Previous disturbances etc). Local and national election results |  |  |  |
| Consequence | ‘Copy cat’ disturbances on streets Reduction of services, Already over stretched services work further extended Property/ vehicle damage, Costs of restoration Insurance claims and consequent increase in insurance premiums Non insured losses Potential rise in crime levels Breakdown of established partnerships Loss of reputation Potential resident migration Potential rise in Council Taxes/financial pressures on Council and partners Safety risk to council staff and members of the public working in these areas Loss of business investment Loss of life and injury |  |  |  |
| ### Likelihood | 2 |  |  |  |
| Impact | 3 |  |  |  |
| Gross Risk Score | 6 |  |  |  |
| ### Controls in Place | Feedback to Police by Community Cohesion staff and Community wardens Calderdale MBC Major Incident Plan / Business Continuity plan Calderdale MBC Health & Safety Policy, arrangements and training Guidance for responding to acts of civil unrest Working with other Authorities to share best practice and tension levels Monthly Community Impact Assessment meetings – frequency of meetings increased during periods of heightened tensions/bi-monthly Silver meetings Silver and Gold structures established and in place Weekly tension reports shared with CIAG partners Community Cohesion, PREVENT and equality policies and initiatives Reporting of reviewed risk register to DMT, CMT and Cabinet to increase awareness Matching history to current intelligence Effective partnership working particularly at neighbourhood level |  |  |  |
| ### Likelihood | 2 |  |  |  |
| Impact | 3 |  |  |  |
| Net Risk Score | 6 |  |  |  |
| Actions to reduce risk and increase controls | Extend community partnerships and intelligence gathering ‘Myth busting’ through corporate centre to communities Implement Safer Communities Strategy Development of ‘Resourceful Communities’ programme |  |  |  |
| Date reviewed | January 2014 |  |  |  |
| Date revised | February 2014 |  |  |  |
| Reasons for revision | Change of Directorate name and additional controls. |  |  |  |
| Date removed |  |  |  |  |
| Reason for removal |  |  |  |  |
| Risk | ### Crime and Disorder |  | ### CR 012 |  |
| ## Created | April 2003 |  |  |  |
| ## Priority | # MEDIUM |  |  |  |
| Reporting | # Audit committee |  |  |  |
| ## Service | All |  |  |  |
| Lead Officer | Head of Neighbourhoods |  |  |  |
| Head of Service | Director - Communities |  |  |  |
| ### Links to Performance Framework | Cabinet priorities/Calderdale Ambition – Fairness Maintaining delivery of priority local services and tackling inequalities in health and wellbeing. |  |  |  |
| ### Trigger | Burglary Violent Crime Vehicle and Road Crime Hate Crime Alcohol related Crime Domestic Violence Repeat Victimisation Vandalism Child Sexual Exploitation |  |  |  |
| Consequence | Death or Serious Injury # Cost of crime through insurance claims, loss of revenue, and rebuilding costs Reduced Investment Loss of Business Confidence Anti Social Behaviour (ASB)and criminal damage Truancy Fear of crime Increased fear of crime amongst vulnerable groups, e.g. the elderly or housebound Adverse publicity and reputational damage Perception of ‘No go’ areas Targeting of specific communities |  |  |  |
| ### Likelihood | 3 |  |  |  |
| Impact | 3 |  |  |  |
| Gross Risk Score | 9 |  |  |  |
| Controls in Place | Safer Communities Strategy Enhanced Educational Opportunities Enhanced Recreational Opportunities Surveillance (CCTV) Designing out of crime or potential crime areas ### Anti Social Behaviour Orders Calderdale Major Incident Plan Town Centre wardens, Licensing laws and managing/monitoring of night clubs and binge drinking Effective partnership working through Community Safety Partnership Implementation of 24 hour Anti Social Behaviour Audit Trail (ASBAT) report Reporting of reviewed risk registers to Service Management Teams and Corporate Management Team to increase awareness CCTV strategy Regular neighbourhood Safer, Cleaner, Greener meetings Regular Vulnerability Location Panel meetings using ASBAT |  |  |  |
| ### Likelihood | 2 |  |  |  |
| Impact | 3 |  |  |  |
| Net Risk Score | 6 |  |  |  |
| Actions to reduce risk and increase controls | Calderdale MBC Car Parks to be in line with Association of Chief Police Officers (ACPO) Safer Parking scheme #### Calderdale MBC to promote using Secure by Design in designing out crime in Calderdale Focus on ASB, violent crime, and alcohol |  |  |  |
| Date reviewed | January 2013 |  |  |  |
| Date revised | February 2013 |  |  |  |
| Reasons for revision | Change to Directorate name and additional controls and actions |  |  |  |
| Reason for removal |  |  |  |  |

| Risk | Failure to meet needs of diverse communities | ## CR 014 |
| --- | --- | --- |
| ## Created | April 2003 |  |
| ## Priority | # MEDIUM |  |
| Reporting | # Audit committee |  |
| ## Service | All |  |
| Lead Officer | Head of Neighbourhoods |  |
| Head of Service | Director - Communities |  |
| ### Links to Performance Framework | Cabinet priorities/Calderdale Ambition -Maintaining delivery of priority local services and tackling inequalities in health and wellbeing. |  |
| Trigger | Lack of appropriate facilities Increased demands on services Newer communities presenting in Calderdale Low take up of services by certain groups. . Failure to understand relevant community needs Deprivation and health inequality index Reduction in dedicated staff and budgets Heightened tensions in areas and/ or periods of unrest |  |
| Consequence | Low levels of educational attainment Poor health Pressure on Public Services Lack of community confidence in public service delivery Disaffected communities Reputational damage to the Council Legal challenge Civil Disorder Political and religious extremism Gap in health and affluence between communities |  |
| Likelihood | 3 |  |
| Impact | 3 |  |
| Gross Risk Score | 9 |  |
| Controls in Place | Consultation/ Community Engagement Aligned budgets Community Cohesion, PREVENT and equality policies and initiatives Equality Impact Assessments Effective partnerships Reporting of reviewed risk registers to DMT and Corporate Management Team to increase awareness |  |
| ### Likelihood | 2 |  |
| Impact | 3 |  |
| Net Risk Score | 6 |  |
| Actions to reduce risk and increase controls | Neighbourhood teams identify and articulate community needs to service providers |  |
| Date reviewed | January 2014 |  |
| Date revised | February2013 |  |
| Reasons for revision | Changes to controls and actions |  |
| Date removed |  |  |
| Reason for removal |  |  |

| Risk | Litigation | CR 025 |
| --- | --- | --- |
| ## Created | April 2003 |  |
| ## Priority | # LOW |  |
| Reporting | # Audit committee |  |
| ## Service | Chief Executives Office |  |
| Lead Officer | Head of Democratic & Partnership Services |  |
| Head of Service | Chief Executive |  |
| ### Links to Performance Framework | Building ambition for Calderdale - Efficiency |  |
| Trigger | Poor decision and/or advice Increased claims awareness Funding Poor Management Lack of Monitoring Challenge under EU law |  |
| Consequence | Reputation Fines and Costs Effects on Budgets Additional workload Staff Turnover |  |
| Likelihood | 3 |  |
| Impact | 3 |  |
| Gross Risk Score | 9 |  |
| Controls in Place | Council Constitution Financial Procedure Rules and Controls Policies and Procedures (Health & Safety etc.) Positive Industrial Relations Insurance Provision Audit and Inspection Training of Staff |  |
| Likelihood | 3 |  |
| Impact | 1 |  |
| Net Risk Score | 3 |  |
| Actions to reduce risk and increase controls | Raise staff awareness of what actions are likely to result in litigation |  |
| Date reviewed | January 2014 |  |
| Date revised | February 2012 |  |
| Reasons for revision |  |  |
| Date removed |  |  |
| Reason for removal |  |  |

| Risk | Contamination and Pollution | CR 029 |
| --- | --- | --- |
| ## Created | April 2003 |  |
| ## Priority | # LOW |  |
| Reporting | # Audit committee |  |
| ## Service | All |  |
| Lead Officer | Head of Housing , Environment and Renewal |  |
| Head of Service | Director – Economy and Environment |  |
| ### Links to Performance Framework | Ambition for Calderdale - Sustainability |  |
| Trigger | Air quality hazard Water quality hazard Public Health hazard Noise pollution Asbestos contamination Waste Management problems |  |
| Consequence | Major health risks Increased staff sickness and absence Calderdale is seen as a less attractive place to live, work or visit Adverse publicity Fines Insurance claims Reputational impact |  |
| ### Likelihood | 3 |  |
| Impact | 3 |  |
| Gross Risk Score | 9 |  |
| Controls in Place | Monitoring of Environmental Health standards Enforcement of Environmental Health legislation Asset Management Plan Asbestos Removal Plan Reporting of reviewed risk registers to DMT and Corporate Management Team to increase awareness ### Annual review of Corporate Plans |  |
| ### Likelihood | 1 |  |
| Impact | 3 |  |
| Net Risk Score | 3 |  |
| Actions to reduce risk and increase controls | Staff training and development in Environmental Heath legislation |  |
| Date reviewed | January 2014 |  |
| Date revised | January 2013 |  |
| Reasons for revision |  |  |
| Date removed |  |  |
| Reason for removal |  |  |

| Risk | Corporate Manslaughter | CR 030 |
| --- | --- | --- |
| ## Date created | August 2005 |  |
| ## Priority | ### MEDIUM |  |
| Reporting | # Audit committee |  |
| ## Service | Chief Executives Office |  |
| Lead Officer | Principal Health and Safety Adviser |  |
| Head of Service | Director of Communities |  |
| ### Links to Performance Framework | Building Ambition for Calderdale - Sustainablility |  |
| Trigger | Serious injury or death of one or more CMBC employees or members of the public |  |
| Consequence | Health and Safety Executive investigation Police investigation (potential murder investigation) Loss of reputation Court case Significant fines Imprisonment of named senior managers / staff Increased insurance premiums |  |
| ### Likelihood | 3 |  |
| Impact | 3 |  |
| Gross Risk Score | 9 |  |
| Controls in Place | Health and Safety section in place to manage Health and Safety risk Health and Safety co-ordinators within each service Briefing sessions across Council Annual Health and Safety audits In depth Health and Safety training and refresher courses Awareness raising of risk Health and Safety advisers site inspections Reporting on ‘near misses’ to Health and Safety Section Enforcement of Construction (Design and Management) Regulations Frequent monitoring of CMBC managed construction sites. |  |
| ### Likelihood | 2 |  |
| Impact | 3 |  |
| Net Risk Score | 6 |  |
| Actions to reduce risk and increase controls | Continued awareness training |  |
| Date reviewed | January 2013 |  |
| Date revised | January 2014 |  |
| Reasons for revision | Change in Head of Service responsibility |  |
| Date removed |  |  |
| Reason for removal |  |  |

| Risk | Information Security (Failure to secure information) |  | #### CR035 |  |
| --- | --- | --- | --- | --- |
| ## Date created | June 2006 |  |  |  |
| ## Priority | # medium |  |  |  |
| Reporting | # Audit committee |  |  |  |
| ## Service | Chief Executive |  |  |  |
| Lead Officer | Corporate Information Manager |  |  |  |
| Head of Service | Democratic and Partnership Services |  |  |  |
| ### Links to Performance Framework | Building Ambition for Calderdale - Fairness |  |  |  |
| Trigger | Information has been stolen, lost, altered without authorisation, misused or cannot be accessed or data integrity has been compromised. Accidental or deliberate release of information to unauthorised persons by any means e.g. phone conversation, paper documents and electronic means. Loss or theft of mobile computing devices e.g. laptop, personal data assistant. Loss or theft of storage media e.g. paper, CD, USB stick and floppy disk. Accidental or deliberate damage to Council networks/systems e.g. virus infection, denial of service attack, environmental hazard. Unauthorised access to networks/systems e.g. hacking, malicious code infection. Accidental or deliberate deletion or destruction of records. |  |  |  |
| Consequence | Inappropriate service delivered. Litigation. Loss of service. Breach of confidentiality Financial loss. Loss of user confidence and damage to Council’s reputation Failure to meet legislative obligations Decision Notice issued to the Council by the Information Commissioner County Court judgement against the Council for breach of Data Protection Act. Damages awarded as a result of individuals or organisations suing the Council |  |  |  |
| ### Likelihood | 3 |  |  |  |
| Impact | 3 |  |  |  |
| Gross Risk Score | 9 |  |  |  |
| Controls in Place | Information Governance Board ICT Control Environment. Anti-virus measures. Filtering of Internet & Email activity. Encryption of mobile devices Usage policies e.g. Policy on Internet and E-Mail Usage, ICT Code of Practice, Mobile Device Usage & Security Policy Guidance on legislation e.g. Data Protection, Freedom of Information Acts. Backup procedures. Disaster recovery plans, Equipment Inventory. Risk Management procedures Monitoring & intrusion detection. Code of Conduct for Council Employees (Disclosure of Information 2.2 – 2.6) Disciplinary procedures |  |  |  |
| ### Likelihood | 2 |  |  |  |
| Impact | 3 |  |  |  |
| Net Risk Score | 6 |  |  |  |
| Actions to reduce risk and increase controls | Information Security Policy incorporating BS7799 best practice. Information Management Policy and Action Plan Security awareness training Review of usage policies. Software inventory Test restoration of systems from backups. |  |  |  |
| Date reviewed | January 2013 |  |  |  |
| Date revised | November 2011 |  |  |  |
| Reasons for revision |  |  |  |  |
| Date removed |  |  |  |  |
| Risk |  | Planning for major peace time disaster | CR 039 |  |
| ## Date created |  | September 2008 |  |  |
| ## Priority |  | # Medium |  |  |
| Reporting |  | # Audit committee |  |  |
| ## Service |  | Communities |  |  |
| Lead Officer |  | Head of Neighbourhoods |  |  |
| Head of Service |  | Director - Communities |  |  |
| ### Links to Performance Framework |  | Ambition for Calderdale - Resilience |  |  |
| Trigger |  | Significant emergency requiring invoking the councils emergency plan Failure of a significant part of the councils service Pandemic |  |  |
| Consequence |  | Council fails to respond due to inadequate plans in place leading to injury, death, homelessness, and disruption to services. Major loss of life due to inability to respond effectively Widespread contamination and pollution Loss of reputation |  |  |
| ### Likelihood |  | 2 |  |  |
| Impact |  | 3 |  |  |
| Gross Risk Score |  | 6 |  |  |
| Controls in Place |  | Corporate Emergency incident plan in place Specific Emergency Plans and Arrangements in place Business continuity plans in place Business impact analysis completed Plans in place for dealing with a pandemic in all services Plans test run both in real time and desktop situations Constant review, updating and reporting of Emergency and plans to make sure that information is current and usable. Regular EP and BC updates taken to DMT’s for awareness. |  |  |
| ### Likelihood |  | 2 |  |  |
| Impact |  | 2 |  |  |
| Net Risk Score |  | 4 |  |  |
| Actions to reduce risk and increase controls |  | Training key staff for emergencies, Roll out training programmes to senior officers Improved out of hours resilience amongst senior staff |  |  |
| Date reviewed |  | January 2014 |  |  |
| Date revised |  | February 2013 |  |  |
| Reasons for revision |  | Change to actions. |  |  |
| Date removed |  |  |  |  |
| Reason for removal |  |  |  |  |

Register history

| Risk | Risk No | Date Amended | Amendment |
| --- | --- | --- | --- |
| Version 3 |  |  |  |
| Adoption of priorities that do not meet national or local needs | ###### CR 004 | November 04 | Risk removed from register |
| Failure of major system, IT , communication | ##### CR 002 | November 04 | Risk removed from register |
| Breach of IT security | ##### CR 001 | November 04 | Risk removed from register |
| Obsolete technology | ##### CR 003 | November 04 | Risk removed from register |
| Demographic change | ##### CR 005 | November 04 | Risk removed from register |
| Poor decision making process, e.g. too slow or concentrated on too few individuals | CR 006 | November 04 | Risk removed from register |
| Failure of major information technology and communication system | ###### CR 026 | November 04 | New risk included on register |
| ##### Version 4 |  |  |  |
| All risks | All | February 05 | All risks have the word strategies changed to actions to match the terminology in the OIP and CP |
| All risks | All | February 05 | All risks issued with unique reference number |
| ##### Version 5 |  |  |  |
| All risks | All | February 05 | All risks have review date included |
| Version 6 |  |  |  |
| Failure to implement children act |  | August 05 | Link to new Children and Young Peoples register |
| Corporate Manslaughter | CR 030 | August 05 | New risk included on register |
| Failure to achieve Performance targets | CR 031 | August 05 | New risk included on register |
| Failure of Building structure | CR 032 | August 05 | New risk included on register |
| Flu pandemic | CR 033 | August 05 | New risk included on register |
| ###### Version 7 |  |  |  |
| Business Continuity | CR008 | November 05 | Risk amended due to continuing work on business continuity |
| Flu Pandemic | CR033 | November 05 | Risk amended due to continuing work on business continuity |
| Poor decision making process | CR006 | December 05 | Risk reinstated on recommendation of Cabinet 05.12.05 |
| ###### Version 8 |  |  |  |
| Increasing energy costs or energy supply restrictions | CR034 | May 06 | New risk included in response to rising fuel costs |
| Failure to implement Children’s Bill | CR 028 | May 06 | Children and Young Peoples Directorate in place with its own risk register |
| Information Security | CR035 | #### July 06 | New risk included |
| Version 9 |  |  |  |
| Data quality | CR036 | December 07 | New risk included |
| Partnerships | CR037 | September 07 | New risk included |
| Version 10 |  |  |  |
| Access to Services inspection | CR038 | May 08 | New risk included |
| Negative/counter productive press/media publicity | CR016 | August 08 | Risk amended by lead service |
| Not implementing change required to drive performance improvement | CR031 | August 08 | Risk amended by lead service |
| Version 11 |  |  |  |
| Poor decision making process | CR 006 | September 08 | Risk removed from register |
| Change in Political Control | CR 020 | September 08 | Risk removed from register |
| Inadequate response to legislation, regulations and guidance | CR 022 | September 08 | Risk removed from register |
| Inappropriate member or officer conduct | CR 027 | September 08 | Risk removed from register |
| Low Levels of educational achievement | CR 024 | September 08 | Risk removed from register |
| Fraud | CR 017 | September 08 | Risk removed from register |
| Breakdown of Prudent Financial Management | CR 023 | September 08 | Risk removed from register |
| Failure of significant IT and communication system | CR 026 | September 08 | Risk removed from register |
| Inadequate pace of innovation and modernisation | CR 013 | September 08 | Risk removed from register |
| Civil Disorder | CR 011 | September 08 | Risk moved from Corporate Risk register part ‘A’ to part ‘B’ |
| Crime and Disorder | CR 012 | September 08 | Risk moved from Corporate Risk register part ‘A’ to part ‘B’ |
| Failure to meet needs of diverse communities | CR 014 | September 08 | Risk moved from Corporate Risk register part ‘A’ to part ‘B’ |
| Freedom of Information | CR 018 | September 08 | Risk moved from Corporate Risk register part ‘A’ to part ‘B’ |
| Corporate manslaughter | CR 030 | September 08 | Risk moved from Corporate Risk register part ‘A’ to part ‘B’ |
| Failure of Building structure e.g. Northgate | CR 032 | September 08 | Risk moved from Corporate Risk register part ‘A’ to part ‘B’ |
| Information security | CR 035 | September 08 | Risk moved from Corporate Risk register part ‘A’ to part ‘B’ |
| Litigation | CR 025 | September 08 | Risk moved from Corporate Risk register part ‘A’ to part ‘B’ |
| Contamination and Pollution | CR 029 | September 08 | Risk moved from Corporate Risk register part ‘A’ to part ‘B’ |
| Business Continuity | CR 008 | September 08 | Risk deleted and built into CR039 |
| Pandemic | CR 033 | September 08 | Risk deleted and built into CR039 |
| Consequence of major peace time disaster | CR 019 | September 08 | Risk deleted and built into CR039 |
| Planning for major peace time disaster | CR 039 | September 08 | New risk containing CR008, CR019, CR033 |
| Project risk and failure to deliver projects | CR 040 | September 08 | New risk included |
| Deliver people’s expectations | CR 041 | September 08 | New risk included |
| Demographic change and the failure to appreciate and plan for demographic change | CR 021 | October 08 | Risk moved to medium following HBOS takeover |
| Version 12 |  |  |  |
| Access to services inspection | CR038 | August 09 | Inspection completed |
| Building infrastructure management | CR042 | August 09 | New risk |
| Version 13 |  |  |  |
| All risks | All risks | December 09 | Risks revised to bring into line with new Directorates |
| Version 14 |  |  |  |
| All Risks | All Risks | January 10 | Risks reviewed by lead officers for annual review |
| Version 15 |  |  |  |
| Negative/counterproductive press/media | CR016 | February 10 | Risk medium Change of directorate |
| Not implementing change required to drive performance improvement. | CR011 | February 10 | Risk reduced from medium to low |
| Version 16 |  |  |  |
| All Risks reviewed | All Risks | November December 2010 | Risks reviewed by directors/ lead officers for annual review |
| Planning for a major peace time disaster | CR 009 | November2010 | Move CR039 to part B. Strong risk management within business continuity and emergency planning |
| Failure of building structure | CR 032 CR 042 | August 2010 | CR032 merged with CR042 as similar risks |
| Not implementing change required to drive performance improvement. | CR011 | August 2010 | Low likelihood and effective controls |
| Freedom of Information | CR 018 | September 10 | Risk removed from Corporate Risk register as for 3 years the risk has remained well controlled ’ |
| Version 17 |  |  |  |
| Impacts arising from a local recession | CR015 | March 2011 | Risk increased to High Audit committee 21.03.2011 |
| Failure to deliver projects effectively | CR040 | March 2011 | Risk increased to High Audit committee 21.03.2011 |
| Version 18 |  |  |  |
| All Risks reviewed | All Risks | November 2011 | Risks reviewed by directors/ lead officers for annual review |
| All Risks reviewed | All Risks | January 2012 | Risks reviewed by risk champions as part of the peer review |
| Severe weather | CR043 | February 2012 | New weather risk created and split from CR039 |
| Version 19 |  |  |  |
| Failure to deliver projects effectively | CR040 | March 2012 | Risk increased from medium to high, Audit committee K78 |
| Building infrastructure management | CR 042 | March 2012 | Risk increased from medium to high, Audit committee K78 |
| Services provided to schools becoming academies | CR 044 | June 2012 | New risk included Audit Committee 25.06.2012 |
| Version 20 |  |  |  |
| All Risks | All Risks | November 2012 | Actions reviewed for eligibility and whether they are actions or controls |
| All risks | All risks | January 2013 | All risks reviewed |
| Version 21 |  |  |  |
| Available resources inadequate to meet corporate priorities | CR007 |  | Failure to achieve budget council savings included in consequences |
| Severe weather | CR043 |  | Moved from part B to part A |
| Version 22 |  |  |  |
| All risks reviewed | All Risks | January 2014 | Risks reviewed by directors/ lead officers for annual review |
| All risks reviewed | All Risks | January 2014 | Risks reviewed by risk champions as part of the peer review |
| Tour de France | CR045 | January 2014 | New Risk included |

Appendix C

Risk Management Corporate Support Group

Terms of Reference

Purpose of the Group

- To support the Council in the continuous development of the management of risk.

- To maintain clear roles, responsibilities and reporting lines throughout the Council for all aspects of risk management;

- Provide opportunities for shared learning and increased staff awareness for risk management throughout the Council;

- To embed the importance of effective risk management through increased staff awareness of risk as part of their everyday work.

- Monitor the effectiveness of the embedding process for risk management throughout the Council on a continuous basis.

- Ensure that the Councils Corporate Risk Management Strategy, Corporate and Directorate Risk registers are current and effective through regular and continuous reviews.

- To work with the Council’s Member Risk Champion to ensure that elected Members are kept up to date with the latest developments in risk management.

##### Membership of the Group

- The group will be chaired by the Assistant Head of Finance and consist of the following:

- Assistant Head of Finance (Internal Audit, Risk Management, and Insurance)

- Risk Management Assistant

- Directorate Risk Champions

- Public Health Service Risk Champion

- Business Continuity representative

- Health and Safety representative

- Internal Audit representative

## Directorate Risk Champions are nominated by the appropriate Director.

## Specialists/Advisers (other officers or external experts) can be invited to attend meetings to facilitate the work of the group.

##### Role and Responsibilities of; -

##### The Group

- Ensure that there is a shared awareness and understanding of the nature and extent of risks the Council faces by promoting good risk management throughout the Council.

- Embed Risk Management into the culture of the Council with the aim of promoting Risk Management within: -

  - Building Ambition for Calderdale

  - Programmes and Projects

  - Performance Management

  - Partnership Workings

  - Budget Reduction Processes

  - Procurement

  - Service Plans

  - Service reviews

3. 	To eliminate or reduce operational and strategic risks to an acceptable level, as detailed within Corporate and Directorate risk registers by raising awareness of the need for risk management.

4. 	To promote the managing of risk in accordance with best practice.

5.  Anticipate and respond to changing social, environmental and legislative requirements;

6.  Monitor and improve the effectiveness of risk management throughout the Council.

7.  Carry out peer reviews of all Directorate risk registers in order to identify any cross cutting risks which might need escalating to the corporate risk register.

8.  To submit annual and half yearly update reports to Corporate Leadership Team (CLT) and the Audit Committee outlining the development and implementation of new initiatives in risk management across the council.

9.	To consider internal audit reports on Corporate and Directorate risk management to identify areas of best practice and cross directorate issues to be rectified.

- Assistant Head of Finance

1.  To update on an annual basis the Calderdale Code of Corporate Governance with regard to Risk Management.

2.  To prepare, publish and keep up to date the Risk Management Strategy and Framework.

3.   To be responsible for co-ordinating completion and update of the Corporate Risk Register and for reporting the register to CLT and the Audit Committee.

4. To roll out the Corporate Risk Management Strategy and Framework to Directorate Risk Champions for further embedding throughout the Council.

5	To monitor that Directorate risk management arrangements in place comply with the Corporate Risk Management Strategy and to report the arrangements in place to the group.

## 6. To complete the Risk Management Corporate Assurance Statement and report his  assessment back to the group.

7.  The Assistant Head of Finance on behalf of the group will submit an annual report and a six monthly update report to CLT and the Audit Committee to advise them of proposed changes which have occurred within the Corporate Risk Register and Corporate Risk Management Strategy, and to update Members of the current state of Risk Management including development and implementation of new initiatives in risk management across the council.

## To submit internal audit reports on corporate risk management to the group.

- Directorate Risk Champions

## To be responsible for monitoring, developing, promoting and embedding risk management as set out within the Council’s Corporate Risk Management Strategy and Framework across their directorates.

## To attend Risk Management Corporate Support Group meetings, but if unavailable, to send a substitute if they are unable to attend.

## To provide risk management awareness training throughout their Directorate.

## To complete the Annual Directorate Assurance Statement for risk management on behalf of their directorate.

## To monitor risk management arrangements throughout their Directorate to ensure compliance with the Corporate Risk Management Strategy and Framework.

## To be responsible for co-ordinating the completion and update of their Directorate risk register and for reporting the register to their scrutiny panel in accordance with the Corporate Risk Management Strategy.

## To submit minutes of the group’s meetings to their DMT’s.

## Directorate Risk Champions will ensure that any agreed action that relates to their Directorate is carried out and that proper and appropriate responses are made.

## 9.    To submit all internal audit risk management directorate reports to the group.

## Frequency of Meetings

## Meetings will take place every three months unless otherwise required and the dates of the meetings are to be established at the start of each year

## The agenda for each meeting will be set by the Assistant Head of Finance.

## Agenda and supporting papers will be distributed at least five working days in advance of each meeting.

## Governance of the Group

## Minutes of meetings will be taken, approved at the next meeting of the group and published on the Intranet.

- Minutes of meetings will be circulated to members of the group and to the Council’s Member Risk Champion within 2 weeks of a corporate group meeting taking place.

## The Corporate Risk Management Strategy and reports issued by the group relating to risk management will be published on the Intranet.

## The Corporate Risk Register will be published on the Intranet.

## Directorate Risk Registers will be published on the intranet.

- The results of Internal Audit reports on Corporate and Directorate control of risk management will be presented to the group. Internal Audit reports and findings will be circulated by the corporate manager and directorate officers.

##### Training

###### Risk management awareness training will be carried out through in house services and through external advisors.

##### Targets and performance

- The group’s performance will be evaluated against the submission of reports to Scrutiny Panels, CLT  and the Audit Committee.

Budget

## There is no budget available to support the group.

## Updated November 2013.

## Approved by the Corporate Risk Management Support Group 19th November 2013