
Calderdale Safeguarding Children Board Business Plan 2014 - 2015
[image: image2.png]@%, Calderdale
(o\ Safeguarding
Children Board




Calderdale Safeguarding Children Board Business Plan - May 2014 to April 2015



[image: image1.png]@%, Calderdale
(o\ Safeguarding
Children Board





Version Control
	4.12.14
	Amended Business Plan(JC) to be next updates on 25th January 2015 as Version 12
	V11

	21.1.15
	Amended Business Plan )JC) to be next updated on 18th February 2015 as Version 13
	V12

	
	
	

	
	
	


	1
	The Calderdale Safeguarding Children Board has assurance that children receive the right help at the right time and are clear about how this impacts on safeguarding

	No
	Objective
	Action
	Timescale
	Reporting
	Outcome
	Status, evidence & sign off/follow up

	1.1
	The CSCB has a clear understanding of early help arrangements
	Write the journey of establishing the early help strategy in Calderdale.  Storyboard 
	August 2014
	Jeff Rafter
	Early Intervention Report produced to CSCB August 2014 for baseline. Storyboard to show journey of change.
	Complete  

	1.2
	Examine use of thresholds in achieving integrated delivery of Early Help LINK TO SIIP 1.9
	Performance Management data showing referrals to Early Intervention Panels 
	September 14
	PM sg
	PM data to demonstrate how agencies use EIPs. 
	Complete

	1.3
	
	Soft audit – Professional forums to seek views, barriers, good practice around Early Help
	Dec 14

March 15

May 15
	EH&P
	Triangulation of performance management and reports from Early Help sector
	Some slippage on timescales by three weeks:  First events booked for January 2015 (27th and 30th).  

	1.4
	
	Review and refresh Signatures of Risk/Continuum of Need. Task Group set up for October 2014
	December 2014
	EH&P
	Revised version for consultation published in Oct14 & finalised in Dec14
	Signatures of need Done.  Continuum of Need done and being formatted in January 2015. 

	1.5
	
	Launch awareness raising campaign for Thresholds document after revision and agreed formats
	December 2014

March 2015
	Comms and Engagement 

Learning & Improvement
	Front line pracs & members of public understand & implement thresholds and is evidenced through PMQA
	Signatures of Risk document launched on website and through Multi Agency Training.  

Changed timescale of promotion due to decision to relaunch both during Safeguarding Week (March 2015)

	1.6
	
	Feed results of use of thresholds to Business Group to act upon
	January 2014
	Business Group
	BG identify resources needed to improve or promote thresholds docs 
	

	1.7
	CSCB to seek assurance that Early Help strategies and practice in Calderdale are effective
	Agree and amend Early Help Strategy including agreeing the MA early help indicators to be monitored by CSCB
	October 2014
	EH&P + CYPPE, CYPS, CSCB
	Vision & framework for early help agreed by strategic partnership & implemented by partner agencies
	Completed and agreed at December 2014 CSCB
On Website January 2015.  

Further launch through Safeguarding Week.  

	1.8


	
	Examine impact of Single Assessment on referral numbers to EIPs (from CAF)
	December 2014
	EH&P, PM Group
	Has introduction of a single assessment impacted on No. of referrals to EIP & MAST?  
	Nov 2014 update:  Target for completed SAs was not met although some fluctuation accounted for through summer holiday period.  Qtr 3 to be examined in Jan 2015.  PM still monitoring and Audit set up to evidence impact.  

	1.9
	
	MA Audit group audit Tier 5 cases: identify missed early help  opportunities & where early help been successful & share areas of good practice 
	February 2015
	EH&P, MA Audit
	Learning from this practice will feed into the Learning and Improvement sub group and the MA training programme.  
	Audit planned for January to March 2015.  

	1.10
	
	MA audit group receive joint adult/child protocol report to establish how effective it is in increasing professionals’ understanding & increasing number of referrals across both 
	January 2015

After October 14 Board response
	EH&P / Principal Social Worker 
	Evidence that awareness raising and launch of joint protocol has affected referrals to Early Help & Safeguarding from both Adult & Children’s Services
	Received December 2014.  Further work to be done RE raising awareness in Adult Services.  Planned through SAB / CSCB and IB.  Joint Adult / Child Safeguarding Week planned March 2015

	1.11
	Improve organisations ability to respond to the needs of children & young people who require early help providing a robust framework for the delivery of a high quality early help offer.
	Multi-agency chronology to be promoted and audited by CSCB LINK TO SIIP 1.1.2  Task and Finish Group: October 2014
	November 2014
	EH&P

C&E

MA Audit
	CSCB is assured that a more comprehensive and multi-agency risk assessment is completed T&F set up
	EH&P pilot underway – to be reviewed end of January 2015

	1.12
	
	Learning and Improvement: Direct training from Section 11 results with monitoring of agencies compliance.

 Learning and Improvement Sub-group to analyse attendance against referral data
	March 2015
	EH&P and L&I sg
	MAT directly reflects issues & needs from Section 11 audit. Analysis provides CSCB with management oversight of partner engagement.  Attendance trends inform CSCB of those engaging with the early help agenda or not.  
	Report for Section 11 to go to Board February 2015.  Learning from this and Board Member responses to feed into 2015-2016 Learning and Improvement Programme.  

	1.13
	Identification of vulnerable groups and how we ensure effective support and communication is delivered at those groups and individuals
	Focussed piece of work to:

Identify isolated and vulnerable

-Assess current position

-Promote early help through professionals

-Raise awareness of early help through media campaign
	March 2015
	EH&P
	Increased levels of self-referrals from children and young people
	

	1.14
	
	-Public Audit

-NSPCC data

-Referrals to MAST.  Are there any wrong doors?

-If parents don’t give consent, could audit to see why.
	March 2015
	EH&P
	Increased levels of self-referrals from children and young people
	


	2
	Assure the Calderdale Safeguarding Children Board of the effectiveness of the identification and safeguarding of the most vulnerable children in Calderdale

	No
	Objective
	Action
	Timescale
	Reporting
	Outcome
	Status 

	2.1
	CSCB assured Children Looked After (CLA) living in Calderdale and living out of the authority are safe. LINK TO SIIP 4.1.2 
	PM group to reflect vulnerabilities of CLA and care leavers
	August 2014
	PM group to Business Group
	CSCB to be assured it has a clear approach to ensure the Board addresses CLA and care leavers across all its functions and governance relationships
	Complete 

	2.2
	
	MA Audit programme to reflect vulnerability of CLA & care leavers
	August 2014
	MA Audit 
	
	Complete



	2.3


	
	Rolling Report to the Board every 6 months.   
	October 2014
	JC to the Board
	
	Complete

	2.4
	To develop a key area of practice for and on behalf of the CSCB and ensure the effectiveness of its strategic arrangements and operational delivery. At present the key areas of practice are:

Child Sexual Exploitation,

Children Missing from Home and Trafficked Children
	Identify area of key practice through Performance Management Quality Assurance to identify areas of practice which need to improve.
	June 2014
	Business Group
	The Board can assure itself an embedded approach based on a learning culture.  
	Complete

	2.5
	
	Produce publicly available, MA strategies which detail present position, local joint working arrangements & future direction for each area
	September 2014
	Proactive and Responsive sub group
	The partnership and public are clear about the delivery of services and requirements for future working.  
	Complete.  Further revision of CSE Strategy done in December 2014 and will be relaunched in February 2015.  
Current Position Paper presented to August Board with Strategy and updated further in January 2015.  

	2.6
	
	Ensure strategy is clear and working with regard to prevention of CSE through professionals, parents and young people’s feedback.
	November 2014
	P&R through qualitative feedback & performance management 
	The Board is reassured that joint working is helping to prevent the presence of CSE in Calderdale.  
	MA Action Plan developed through Proactive and Responsive Sub Group focussing on: Prevent, engage, inform, identify, support disrupt and prosecute.  Linked with Gold, Silver Bronze Groups.  

	2.7
	
	Through audit, measure whether support to individuals, families and communities is having positive outcomes
	December 2014
	Proactive and Responsive scrutinise work of the MA Audit Group
	The Board is reassured that joint working arrangements for CSE for c&yp are effective.  
	CSE Audit completed in Summer 2014.  Findings positive.  

Impact report written and published for CSE practice and impact 2010 – 2014 in December 2014.  

Second Historical Audit commenced December 2014 to April 2015.  

Further review of CSE Team planned for March 2015.  

Further scrutiny from Independent Chair planned for Spring 2015.  
CSE Action Plan details further work with individuals, families and communities.

	2.8
	
	Provide support and advice to community engagement partnerships and proactively plan to ease community tensions.
	Ongoing & as need arises proactivly 
	P&R sg / C&E sg
	The Board has a Public presence and is open to scrutiny. 
	See Action Plan for full community engagement.
Police and LSCB trained Hoteliers RE CSE.  

Taxi driver training due to be compulsory upon renewal of licence. 

Further community engagement planned for Operation Harehill.  

	2.9
	
	Continuously review strategies and plans and improve / maintain local joint working arrangements
	June 2014 and ongoing
	P&R sg / CSCB
	The Board can be assured that the partnership is reviewing practice and improving from National / Local Learning.
	Complete – see strategy and review in December 2014 and January 2015.  See P&R sub group meeting notes challenging partner and accountability

	2.10
	Professionals are knowledgeable about the impact of neglect and emotional abuse on children and are able to intervene to support children
	Review the work done by the Neglect Task and Finish Group
	November 2014
	Business Group
	The Board can assure itself of the true position of joint working arrangements for Neglect & Emotional Abuse.
	Business Group assigned audit of Neglect cases to MA Audit Group.  Timescale November 2014 not met, planned for March 2015.  BG risk assessed position and has advertised for PMQA role to support CSCB.  

	2.11
	
	Reflect on the feedback from the SCR regarding the neglect toolkit and feed this into updated version
	December 2014
	SCR Sub group
	Children’s life chances are improved by provision of effective services to support positive parenting and overcome the effects of neglect.  
	Timescale pushed back to after March 2015 after PMQA role appointed.  

	2.12
	
	Audit cases of neglect & include in PM data set to establish true position of effects of Neglect 
	March 2015
	Multi Agency Audit Group
	
	

	2.13
	Board to assure itself that Domestic Abuse involving children strategies are working across agencies
	Seek assurance through reporting that Domestic Abuse strategies in Calderdale are making a difference to families and children through effective joint working through PMQA
	December 2014
	Business Group
	Clear governance arrangements are in pCLAe which report on the true position of Domestic Abuse and it’s impact on children – this is fed into the Business Group who highlight areas of concern to the Board and sub group work plans
	PM indicator 1.4 reports A&E cause for concern from DV and follow up from HVs / School Nurses: 100% reported and followed up and now automatically referred to IEPs for consideration.  
Transformation Funding now funds post and hosts governance structure for DA which will feed into Board through Board Member representatives (Designated Nurse and DCS).  

	3
	Robust Performance Management and Quality Assurance demonstrates effective Safeguarding

	No
	Objective
	Action
	Timescale
	Reporting
	Outcome
	Status, evidence & sign off/follow up

	3.1
	To ensure the board has effective performance management systems in pCLAe to support effective challenge and ask relevant questions
	To review and assess work undertaken on the performance manage systems to date
	Performance sub group meeting on 20.5.14
	Performance Management sub group
	The CSCB will be assured that the performance management framework is effective and is directed by the Performance Management and Quality Assurance Framework.  The Board is assured of the true position of Calderdale in relation to how effective joint working arrangements are.  
	Complete see minutes, CSCB minutes and reports.  

	3.2
	
	To ensure the current dataset is fully populated and contains sufficient analysis to be “fit for purpose”
	For LSCB meeting on  5th June


	CSCB
	
	Complete see minutes, CSCB minutes and reports.  

	3.3
	To ensure a multi-agency dataset of safeguarding activities an outcomes is collated and regularly evaluated to assist the board in defining strengths and areas for improvement of safeguarding services in Calderdale  
	To review developments in Calderdale and nationally and make proposals for a more outcome focussed safeguarding dataset with a strong multi-agency focus
	August Board
	PM sub group
	
	Complete see minutes, CSCB minutes and reports.  

	3.4
	
	To implement a strengthened performance management dataset and provide analysis of this for the Board’s consideration
	Bi-monthly
	CSCB
	
	Complete see minutes, CSCB minutes and reports.  

	3.4a
	
	All sub group Chairs to escalate PM requests to Business Manager
	Monthly
	Business Manager
	All sub groups identify data requirements which are captured in dataset
	Complete see minutes, CSCB minutes and reports.  

	3.5
	Establish a rigorous Quality Assurance Framework which complements and supports single agency audit  LINK TO SIIP 7.2
	Establish a multi-agency task and finish group to drive forward multi agency audit
	End of June 2014
	Business Group
	6 weekly meetings established
	Complete and Multi Agency Audit Group now even standing Sub Group

	3.6
	
	Provide evidence to the CSCB to enable the Board to scrutinise, challenge and assure itself
	Bi monthly
	MA Audit Group
	Increased awareness at the CSCB.  Evidence of reports
	Reports from MAAG to Board bi-monthly complete.  See examples in December 2014 Board Meeting Minutes
Further development to be done with more in depth reports at CSCB meetings.  

	3.7
	
	Develop a robust and regular programme of multi-agency audits
	October 2014
	MA Audit Group
	Programme for short, medium and long term audit planning
	Programme Complete and updated monthly at MAAG

	3.8
	Ensure multi agency audits feed into the PMQA to provide triangulated analysis measuring quality of provision, areas for improvement and dissemination of learning
	Ensure lessons learned from SCRs and external scrutiny are fed into the QA audit framework.  
	When need arises
	Business Group
	Programme includes audits directly responding to learning
	See LIF and SCR Framework.  

See SCR Action Plans.  
Impact Monitoring sheet will record impact from learning

	3.9
	
	Evaluate audits to verify learning and actions
	Bi monthly
	MA Audit Group
	Evaluation and reports show learning has been acted upon
	Multi Agency Audit Group now established.  Processes complete for requesting, undertaking and reporting on audits.  Evidence now needs to show Audits making a difference.  

	3.10
	Regular reporting with emerging themes and trends to CSCB and any external scrutiny
	Analyse trends and themes identified through audit
	6 weekly
	Business Group
	Analysis and reports available for scrutinising
	Multi Agency Audit Group now established.  Processes complete for requesting, undertaking and reporting on audits.  Evidence now needs to show Audits making a difference.  

	3.11
	
	Report to Business Group and CSCB
	Bi Monthly
	 MA Audit Group
	Reports available
	Multi Agency Audit Group now established.  Processes complete for requesting, undertaking and reporting on audits.  Evidence now needs to show Audits making a difference.  

	3.12
	
	Feed trends and themes into PMQA Framework
	Bi monthly
	Business Group
	Thematic reports available
	PMQA Framework Adopted December 2014.  

	3.13
	
	Report on corrective actions, improvement of practice and progress to CSCB
	Bi monthly
	Business Group
	Evidence of actions completed
	Follow up reporting, and evidence of impact spreadsheet to be implemented in Audit and evidenced to CSCB


Sections 3.6 to 3.13 at risk of not being accomplished within proposed timescales due to non-engagement from partner agencies and capacity of Board Business Manager and Secretariat.  Business Proposal to be presented to October Board with Options paper to mitigate risks.  Update Jan 2015:  October 2014 Board Challenged attendance at Multi Agency Audit meetings which have since been fully attended.  Board agreed to recruit PMQA role to support Business Manager.  Since attendance at MA Audit Group has increased, further reporting has shown evidence of impact from Audits and Action plans completed.  
	4
	The Calderdale Safeguarding Children Board drives Safeguarding and Practice Improvement for children and young people

	No
	Objective
	Action
	Timescale
	Reporting
	Outcome
	Status, evidence & sign off/follow up

	4.1
	The establishments of a learning culture in the context of single and multi agency organisational and professional accountability.  LINK TO SIIP 5.2.3
	Map current process for managing case review
	October 2014
	Case Review sub group
	Fit for purpose Case Review Framework.  
	SCR Framework completed.  Due to be officially signed off at January 2015 Board.  

	4.2
	
	Identify within framework an options paper and action plan re future use of systems methodology and identify and clarify commissioning and QA role of Independent Chair.  
	December 2014
	Case Review sg Business Group and CSCB
	Established Case Review Framework which forms part of the Learning Improvement Framework
	Done.  February 2015 to be agreed.  

	4.3
	All Board Members and an increasing number of Schools, Voluntary, Private and Community Sector Organisations complete self-assessments (Section 11) to establish the position of Safeguarding in Calderdale organisations
	Commission and launch an annual self assessment programme (Section 11) to build a comprehensive self assessment across all provision, in order to support and shape joint working at all points in the ‘child’s journey’.  
	June 2014
	Business Group 
	The Board is assured that member services for children are meeting their commitments in respect of safeguarding.  The Board can also identify areas where improvement and support are required.  
	Completed.  100% of Board Members completed and returned Audits.  100% of Commissioned Services also completed.  6-% of Schools.  First year of 3 year plan successfully underway.  Report completed November 2014.  Scrutiny, analysis and recommendations to go to Board in February 2015

	4.4
	
	Analyse Section 11 results for:  Safeguarding Concerns, good practice to share and triangulation against other evidence (practitioner feedback, children’s views and PM reports)
	October 2014
	Business Group
	Section 11 results feed into Annual Report with actions around training, policy and procedure review, commun’n to front line practitioners and setting a standard for quality around safeguarding practice.  
	Report Completed in November 2014.  Further analysis reported to October Board as a Risk with proposal for additional PMQA role which was accepted.  In December 2014, Multi Agency Analysis meeting held – results to go to January 2015 Board.  

	4.4a
	
	Produce action plan for 2015 / 2016
	October 2014
	Business Group
	
	Timescale slipped.  Due to go to Board February 2015.  See Section 11 paper

	4.5
	The learning improvement framework (LIF) will be the vehicle for the identification of learning & development, policy development and practice review
	A robust learning improvement framework will be developed.

Providing a robust system of identifying learning, delivering learning opportunities, evaluation and evaluating impact.  LINK TO SIIP 5.2.1
	October 2014
	Learning &Improvement

 Group

CSCB business group

CSCB
	The LIF will provide a system of review delivery and evaluation. 
	Timescale slipped.  LIF reviewed and accepted by Board December 2014.  See LIF.  


	4.6
	The CSCB has a programme of learning and development reflecting the priorities of the CSCB. 

 
	The CSCB will deliver a comprehensive and responsive programme of learning and development opportunities 
	April 2014 


	L &I Group

Business group

CSCB
	A programme of high quality learning and development will be delivered reflecting both in principle and practice the priorities of the CSCB.  
	See L&I programme

	4.7
	
	CSCB to include prevalence of SMART planning from multi-agency audits.  LINK TO SIIP 1.2.2
	September 2014
	Learning and Improvement sub group
	Publicised training opportunities.

Analysis via audit reports.
	See L&I programme and evaluation reports

	4.8
	The effectiveness and impact of multi agency training will be understood by the CSCB LINK TO SIIP 7.3
	1. A performance report will be provided to the Learning & Improvement Group 
	August 2014
	Learning &Improvement Group

Business group

CSCB
	The CSCB will be assured that the learning and development activities of the CSCB is impacting on the professionals and agencies ability to safeguard children
	Complete

	
	
	
	
	
	
	

	4.9
	Multi agency learning and development opportunities will positively change the attitudes & behaviours of staff towards interagency working  to safeguard children  
	1. The LSCB Learning and Improvement group will review and consider the multi agency training against the agreed benchmarks. 
	July 2014
	Learning &Improvement 

business group


	All multi agency training will be benchmarked against identified standards.
	Report considered and accepted by Board in August 2014.  Benchmarks written to be reviewed and targets set for 2015-2016 in February and April 2015.  

	4.10
	
	2. A system of evaluation will be developed to ensure that that multi agency training is having the required impact to safeguard children in Calderdale.
	July 2014

 And bi monthly
	Learning &Improvement Group

CSCB business group

CSCB
	The impact of training will be understood it will provide assurance to the CSCB that children are safer as a result of staff attending multi agency training.
	Much work done to evaluate impact of training and reported to Board quarterly.   Charging Policy agreed in December 2014 and enforced from January 2015.  Letter to each Board member detailing attendance from every agency supported challenge to partners of their participation in MA Training.  Further evaluative work done immediately after and 3 monthly follow ups for attendees.  Quality Assurance programme planned.  


4.4 at risk due to capacity of Board Manager / need for deep analysis.  To be included in Business Proposal for 2nd October Board.  Update December 2014: Multi agency meeting completed deeper analysis and report to February 2015
4.10 risk due to cancellation of training.  Report on risks, mitigations RE cancellation of training to be written by AW and presented to 2.10.14 Board.  Update December 2014:  Report to Board resulted in agreed charging policy and agreed challenge to partners through letters examining attendance.  
	5
	Clear priorities are set and core business processes are strengthened which establish effective joint working arrangements for safeguarding children and young people

	No
	Objective
	Action
	Timescale
	Reporting
	Outcome
	Status, evidence & sign off/follow up

	5.1
	Review and set clear  core business processes 
	12 month rolling programme of scrutiny reports which reflect current strategy and objectives: 
	October 2014
	CSCB through the Business Group


	This will enable the Board to develop evidence, monitor, measure and challenge services for children and drive improvement. 
	Completed.  See list of Rolling Reports

	5.1a
	
	Induction Programme written to be delivered to new members and existing as needed
	October 2014
	Business Group
	Any member can meet with any Chair to have sub group work explained etc
	Timescale Slipped.  Induction pack consists of Business Plan, Constitution, Board Member Agreement, Sub Group Terms of Reference, Annual Report and Recent Newsletters.  
Buddy Board Members set up.  

	5.2
	Cohesive working arrangements between CSCB, Scrutiny Panel, Improvement Board and Partner Agencies
	Protocol agreed between Boards and links continued to reduce duplication and plug gaps.  LINK TO SIIP 2.1 & 2.2
	June 2014
	CSCB
	Effective co working of the boards will be the ultimate measure in the sustained improvement and via inspection. 
	Protocol Agreed.  Workplan agreed for HWBB, CYPPE, CSCB, Scrutiny, CCG, IB.  

	5.3
	Complete actions within Improvement Board’s Single Integrated Imp’t Plan (SIIP)
	Identify SIIP actions within each sub group work plan and reflect in Business Plan.
	June 2014
	Business Group
	Improvement driven forward by the LSCB, the Business Group and he subgroups.  
	Complete

	5.4
	
	Set timescales for each SIIP action to be completed
	July 2014
	Business Group
	Local Authority and CSCB prepared for external reviews
	Complete

	5.5
	Voice of child: Continue the drive through audit and supervision,

Multiagency and joint working practice to reflect focus on the child’s journey. LINK TO SIIP 1.6
	Recognise, celebrate and showcase good practice. Thematic audit on case files and evidence of group events providing platform for young people. 

Multiagency case audits reveal focus of evidence of the child’s journey. 
	July 2014
	Communication and Engagement sub group

MA Audit 
	Voice of the child is established for all core processes for the LSCB and influences the direction taken and decisions made by the LSCB.  
	Only had single agency input so far, more required. 

Young Advisors have completed a questionnaire and the results should be available soon. 

Full programme for Young Advisors agreed by December Board.  Further Voice of the Child examples given at Board Meetings.   

	5.6
	Ofsted Preparation LINK TO SIIP 7.1, &.1.1, 
	Identify risks and mitigate through Ofsted Task and Finish Group - Update Risk Register
	September 2014 
	Business Group
	LSCB Ofsted ready with documented evidence 
	Business Group highlighted risks through ‘Board Capacity Paper’ after risk assessing Business Plan (Version 11).  

	5.7
	Publish Annual Report in September 2014
	Use Annual Report to help establish long and short term improvements
	September 2014
	RB / JC
	Annual Report delivered on time
	Published in October 2015.  


	5.8
	Ensure Calderdale has robust policies and procedures which are up to date, relevant and in line with local, national guidance, current legislation and local need.
	Review existing local and internal policies, procedures, protocols and best practice guidance against

-  Ofsted and CSCB self-assessment/development plan and Business/Improvement plan

-  Learning identified in SCR 
	Timescales to be agreed but to reflect urgency of situation
	Learning and Improvement sub group
	Policies are robust and reflect local learning.  
	Revision begun after SCR Child K.  Consortium meetings bimonthly addressing each policy.  Task and Finish Groups for Information Sharing Agreement and further work RE Neglect done.  CAF identified as needing updating; replaced by Single Assessment.  

	5.9
	
	Ensure they are WT13 and West Yorkshire Consortium compliant
	At every Consortium meeting
	JC and Learning and Improvement sub group
	Confident in procedures
	Always done in conjunction with West Yorkshire Consortium and Tri-X

	5.10
	
	Identify in context of improvement/business plan and Ofsted readiness priorities 
	October 2014
	Learning and Improvement sub group
	Annual plan of policies and procedures to be reviewed according to priorities set by SIIP, Business Plan and Ofsted
	Timescale slipped.  However L&I sg now have MA task and finish group set up from December 2015 focussing on pols and procs

	5.11
	
	Consult and engage partners in process and revision
	October 2014
	Learning & Improvement sg
	
	See above 

	5.12
	
	Identify and agree clear methodology and implementation/support implementation
	November 2014
	Learning and Improvement sg & Comms and Engagement sg
	Policies are clear, accessible and understood by all front line workers across all partner agencies
	Review is underway and changes have been made to policies on website

	5.13
	CSCB to develop effective communication with the Calderdale community and professionals who work with children and young people
	Development of the marketing strategy including responding to emerging needs.


	October 2014
	Comms & Engagement Sub group
	Organisations, professionals and general public receive the right information at the right time.
	Behind schedule. Marketing Strategy next meeting is scheduled for 24/11/14

Marketing Strategy due for completion January 2014

	5.14
	
	Overseeing the effectiveness of the CSCB website to ensure clarity and consistency of messages presented.


	October 2014
	Comms & Engagement sub group 
	LSCB is effective at communicating key safeguarding knowledge and information, and the website is a public and transparent ‘window to the Board’.  
	Website has been significantly updated
Bi Monthly Newsletters produced

	5.15
	
	Use of the website to increase understanding by the Board of the issues of and successes from the work force.  
	March 2015
	Comms & Engagement sub group
	To triangulate understanding of how effective or not joint working is in Calderdale.  
	Proactive and Reactive Website responds to IC, Business Manager and Sub Group Leads / Horizon scanning.  E.g. FGM.  Radicalisation

	5.16
	
	Provide regular updates to multi agency partnerships to disseminate Board business, learning and current safeguarding news.   


	Bi monthly
	Comms & Engagement sub group
	Calderdale workforce more aware of Board business and is well informed about up to date local guidance, policy and procedure around safeguarding. 
	Bi monthly newsletters being sent out, not sure how widely disseminated. Early Years bulletins always include website links. Essential Knowledge Briefings will be put on website.


5.5 – no identified risks of not listening to children, but not yet evidence at Board.  Put on at standing agenda item at C&E group.  Update: Done – first time Board received papers in October 2014
CSCB Business Plan Version 12 – 21.1.15







 2

[image: image1.png][image: image2.png]