ITEM

# Report to Scrutiny Panel

| Name of Scrutiny Panel | Economy and Environment |  |
| --- | --- | --- |
| Meeting Date | 15 December 2010 |  |
| Subject | REVENUE BUDGET MONITORING 2010/11 |  |
| Wards Affected | ALL |  |
| Report of | Group Director Economy and Environment |  |
| Type of Item (please tick ) | Review existing policy |  |
|  | Development of new policy |  |
|  | Performance management (inc. financial) |  |
|  | Briefing (inc. potential areas for scrutiny) |  |
|  | Statutory consultation |  |
|  | Council request |  |
|  | Cabinet request |  |
|  | Member request for scrutiny (CCFA) |  |

Why is it coming here?

To report: - The second cycle overall service controlled revenue budget monitoring position for 2010/11; - The forecast Service Controlled Budget variances of the Directorate and underlying issues - The implications for future years

What are the key points?

This report is primarily for information. No decisions are required.

Possible courses of action

It is recommended that Members consider the report and identify any areas they would like to consider for further scrutiny in a future report

Contact Officer

A Kent Telephone: 01422 392108

Should this report be exempt?

No

- Background

  - This report provides information on-

    - results to end of September 2010

    - the service managers current forecast of outturn compared to the service controlled budget for 2010/11

    - the reasons for significant forecast budget variances and underlying issues.

    - the issues affecting the Directorate budget in future years

- Main issues for Scrutiny

Current Financial Year

2.1 This report presents the results of the second overall monitoring review of revenue expenditure and income compared to budget in 2010/2011 which is summarised as follows (excluding Transport Services), prior to the movement on reserves -

|  | Net Expenditure to September |  | Remaining Budget | Current Approved Budget | Current Forecast Outturn for Year | Forecast Budget Variance (f-e) |
| --- | --- | --- | --- | --- | --- | --- |
|  | % of Budget | £000 | £000 | £000 | £000 | £000 |
| (a) | (b) | (c) | (d) | (e) | (f) | (g) |
| Overall Directorate Position | 40 | 11170 | 17338 | 28508 | 29015 | 507 |

2.2 The Summary shows the net expenditure on the Councils financial ledger at end of September 2010 and therefore reflects the timing of payments and income to that date. However the service manager forecast for the year is based on the financial ledger position at that time, together with known/planned commitments and forecast income levels for the remainder of the financial year.

2.3 The forecast net budget variance is expected to be offset from reserves and other adjustments as outlined in paragraph 2.21 below.

Business Planning Units/Budget Monitoring Arrangements

2.4 The Directorate service controlled revenue budget is allocated to a number of Business Planning Units.

2.5 Each Business Planning Unit comprises one or more Cost Centres. Each Cost Centre has a dedicated budget for expenditure (and income as appropriate) and a cost centre manager responsible for monitoring and managing the budget in accordance with service requirements and for providing a forecast outturn for the year.

2.6 Cost centre managers and Heads of Service have access to monthly statements showing the budget, income and expenditure, commitments and remaining budget and are required to review/update the forecast for the year each month. This process enables Managers to rapidly identify relevant budget control issues and to take action/ reallocate budgets to offset forecast under/overspendings.

2.7 Many items of income and expenditure within the Directorate’s services do not follow a straight-line pattern or even spend/receipt during the year. For example, winter service costs are mainly incurred during the winter season, property rates are normally charged at the beginning of the year, some income is charged for in advance or arrears etc.

2.8 The forecast outturn compared to current approved net budget for each Business Planning Unit (excluding Transport Services) is shown in the following table prior to the use of reserves and other adjustments -.

| Business Planning Unit | Net Expenditure to September |  | Remaining Budget | Current Approved Budget | Forecast for Year | Variance (f-e) |
| --- | --- | --- | --- | --- | --- | --- |
|  | % of Budget | £000 | £000 | £000 | £000 | £000 |
| (a) | (b) | (c) | (d) | (e) | (f) | (g) |
| Regeneration | 28 | 482 | 1266 | 1748 | 1692 | -56 |
| Design & Maintenance | 74 | 1113 | 399 | 1512 | 1631 | 119 |
| Planning | 61 | 1204 | 762 | 1966 | 2553 | 587 |
| Director | 16 | 105 | 558 | 663 | 499 | -164 |
| Highways & Projects | 32 | 2851 | 6041 | 8892 | 8880 | -12 |
| Markets | 44 | -246 | -315 | -561 | -484 | 77 |
| Networks & Other Engineering | 35 | 461 | 870 | 1331 | 1306 | -25 |
| Parking Services | 42 | -590 | -801 | -1391 | -1340 | 51 |
| Housing | 64 | 739 | 410 | 1149 | 1360 | 211 |
| Environment | 38 | 5051 | 8148 | 13199 | 12918 | -281 |
| Total | 40 | 11170 | 17338 | 28508 | 29015 | 507 |

2.9 The percentages shown of net expenditure to September are based on the current approved budget. This shows that this group of Directorate services have spent, net of income received, at end September, 40 % of the current approved budget.

2.10 Appendix A provides further information concerning forecast variances to budgets below the Business Planning Unit level.

2.11. The current forecasts of outturn exceed the current budget by £507k prior to further forecast movements on reserves and other adjustments for particular service areas.

2.12 The forecast variance for the Regeneration Service is mainly from savings in staff costs

2.13 The forecast shown for Design and Maintenance reflects a potential shortfall in fee incomes and a shift in workloads towards compliance work. The service continues to examine options to reduce this forecast budget variance, the outcome to be reflected in the next budget monitoring report submitted to this Panel.

2.14 The forecast budget variance on the Planning Service mainly comprises 4 elements

- The Development Management service is forecasting a variance to budget of £336k for the current year, the result of a shortfall of income. The remainder of the Housing and Planning Delivery Grant 2009/10 is held in reserve to meet the forecast outturn shortfall in full. The Conservation service is forecast to overspend by £4k

- The Building Control Service is forecasting a variance to budget of £42k for the current year, again mainly the result of a shortfall of income. The Building Control trading account reserve of £24k will be used to offset  part of the forecast shortfall

- Within Development Strategy the net forecast variance to budget of £213k comprises

  - The forecast for the Local Development Framework £271k which would be funded by a specific reserve.

  - The Energy Management and Spatial Planning forecast net under-spending to budget of £58k, mainly the result of additional income from fuel rebates

2.15 A contingency budget for 2010/11, mainly comprising one off budget savings brought forward from 2009/10 but also new savings for 2010/11 is held to help the Directorate meet forecast budget variances/pressures for the current year. Any balance not required for this purpose will be either carried forward to 2011/12  or used to fund spend to save/other required initiatives.

2.16 The forecast under-spend on Highway Maintenance staffing costs is to offset work on land drainage within the Projects service

2.17 The forecast budget variance on the Markets Service reflects continued difficult trading conditions.

2.18 Key issues included in the forecast overspend on the Housing Service include the net cost of the Strategic Housing Market Assessment, the cost of maintaining land, costs of the Doorways service and staffing costs. Service Managers continue to devise options for reducing/containing such costs within the budget

2.19 The forecast under-spending to budget on the Environment Service is mainly on the Waste Service being the result of improving rates of recycling and reduced waste going into Landfill. The forecast surplus at year end of £270k will be placed into a reserve to be used in later years to meet the expected increasing cost per tonne of Landfill Tax.

2.20 The Parking Services budget is to be adjusted for the closure of the Broad Street Car Park by £140k and will be reflected in the next budget monitoring report submitted to this Panel

2.21 Once the various transfers to and from reserves and other adjustments are taken into account, the forecast variance shown in 2.8 above is eliminated-as follows

|  | £000 |
| --- | --- |
| Forecast Variance to Directorate Budget | 507 |
| Transfer Environment-Waste Service forecast under-spend to Reserves | 270 |
| Forecast Transfers from Reserves: |  |
| Development Management | -336 |
| Building Control | -24 |
| Strategic Resources | -6 |
| Local Development Framework | -271 |
| Compensation for Closure of Broad St Car Park | -140 |
| Net Forecast Variance to Directorate Budget after movements on Reserves | Nil |

2.22 The forecast position of the Transport Service is shown in Appendix 2. The figures shown combine both service and centrally controlled budgets. The service is currently forecasting to remain within its total budget for the current financial year.

2.23 The Directorate Management Team has examined for all its services, the progress of income and expenditure against the 2010/11 budget, the latest service managers forecast of outturn compared to budget and have taken into consideration the impact of the items above.

2.24 The Directorate Management Team is taking action to contain budget pressures and at this stage believes that the outturn for 2010/11 will be broadly within total resources available.

2011/12 & Future Years

2.25 The Directorate is forecast to use and exhaust a number of reserves in 2010/11 to offset budget shortfalls in that year. However, the shortfalls can be expected to recur in 2011/12 (and future years) as follows.

2.26. With regard to the Development Management service, the Government has announced the termination of the Housing and Planning Delivery Grant regime with effect from 2010/11. The remainder of the 2009/10 Grant received by the Council is expected to be used in meeting the forecast budget shortfall in 2010/11. Planning Fees are currently determined by Central Government and were last reviewed with effect from 1st April 2008. Unless there is a significant upturn in the economy (and therefore planning applications), and/or substantive review of fees by Government and/or a replacement grant regime introduced, the current year forecast variance of c£340k can be expected to recur in 2011/12 onwards. This issue will need to be considered by Members as part of the process to prepare the 2011/12 budget.

2.27 The Building Control service is also significantly dependent on income from fees and the service is not immune to the current economic conditions. Unless there is a significant upturn in the economy and increased building control fee and partnership fee incomes as a result, a similar forecast variance to budget as identified for the current year of c£40k may recur in 2011/12. This issue will also need to be considered by Members as part of the process to prepare the 2011/12 budget.

2.28 The forecast level of spend in 2010/11 on the Local Development Framework (LDF) will, if achieved, exhaust the reserve balance. Central Government are reviewing all requirements for public spending and may vary the provisions of the LDF but until a new scheme is introduced the Council will need to continue with the LDF preparation and updating. The level of required spending on LDF, or a replacement scheme, in 2011/12 and future years will also need to be considered by Members as part of the process to prepare the 2011/12 budget.

2.29 The Directorate service controlled revenue budget in the future years has already been reduced to reflect savings arising from the programme to transform service provision. These savings, taken at Budget Council 2010, amount to £200k in 2011/12 rising to £1.1m per annum from 2012/13 onwards. A framework of separate projects to determine the detailed means of achieving these savings has been put into place. The individual project leads have provided a current position statement, including the forecast date to conclude the review/detail the source of the savings, as set out in Appendix 3.

- Consultation

Not applicable

- Further action and timescales

The Directorate will continue to monitor its budget on a monthly basis and take action to manage additional pressures that may arise.

- Options appraisal

The Directorate Management Team review options on a regular basis to contain identified budget problems within the budget resources available.

- Conclusions

The Directorate Management Team receives relevant and timely information on the revenue budget monitoring position.

- Appendices

Appendix 1 provides more detailed information below the Business Planning Unit level

Appendix 2 provides details of the budget/forecast of the Transport Services account

Appendix 3 provides details of the progress in securing the transformation of services budget savings agreed at Budget Council 2010 for the future years

- Background documents

Report of the Finance Manager to Directorate Management Team and decisions thereon

Analysis and information provided by the Assistant Head of Finance, other Finance Staff, cost centre managers and Heads of Service.

- Documents available for inspection at

Directorate Finance Office 3rd Floor Northgate House Northgate, Halifax

Appendix 1

Financial Summary below the Business Planning Unit level £000

(Excluding Transport Services –see Appendix 2)

| Business Planning Unit (BPU) | Detail Group | Net Budget | Net Forecast Outturn | Variance |
| --- | --- | --- | --- | --- |
| Regeneration | Head of Regeneration | 139 | 136 | -3 |
|  | Business & Economy | 925 | 957 | 32 |
|  | Major Projects | 138 | 136 | -2 |
|  | Land & Property | 546 | 463 | -83 |
|  | BPU Total | 1748 | 1692 | -56 |
| Design and Maint. | Corporate Maintenance | 1164 | 1164 | 0 |
|  | Design and Maintenance | 348 | 467 | 119 |
|  | BPU Total | 1512 | 1631 | 119 |
| Planning | Head of Planning | 129 | 125 | -4 |
|  | Development Management/Conservation | 291 | 631 | 340 |
|  | Building Control | 163 | 205 | 42 |
|  | Development Strategy | 698 | 911 | 213 |
|  | Directorate Support | 685 | 681 | -4 |
|  | BPU Total | 1966 | 2553 | 587 |
| Director |  | 250 | 253 | 3 |
| Contingency |  | 413 | 246 | -167 |
|  | BPU Total | 663 | 499 | -164 |
| Highways & Projects | Highway Maintenance | 902 | 804 | -98 |
|  | Highways Works | 6773 | 6773 | 0 |
|  | 3rd Party Insurances | 652 | 652 | 0 |
|  | Depots | 67 | 74 | 7 |
|  | Projects & Land Drainage | 331 | 416 | 85 |
|  | Management/Other | 167 | 161 | -6 |
|  | BPU Total | 8892 | 8880 | -12 |
| Markets | Markets BPU Total | -561 | -484 | 77 |
| Networks &Other Eng. | Head of Highways & Eng | 109 | 106 | -3 |
|  | Networks Manager and Staff | 127 | 113 | -14 |
|  | Road Safety | 476 | 462 | -14 |
|  | Rights of Way | 255 | 255 | 0 |
|  | Traffic | 152 | 188 | 36 |
|  | Highways Dev. Control | 170 | 139 | -31 |
|  | Transportation | 42 | 43 | 1 |
|  | BPU Total | 1331 | 1306 | -25 |
| Parking Services | Parking Support | 1066 | 1057 | -9 |
|  | On Street/Off Street | -2457 | -2397 | 60 |
|  | BPU Total | -1391 | -1340 | 51 |
| Housing | Housing Access | 471 | 614 | 143 |
|  | Private Sector Housing | 396 | 434 | 38 |
|  | Housing General | 282 | 312 | 30 |
|  | BPU Total | 1149 | 1360 | 211 |
| Environment | Environmental Protection | 1264 | 1253 | -11 |
|  | Waste Services | 11935 | 11665 | -270 |
|  | BPU Total | 13199 | 12918 | -281 |
| Directorate Total | Prior to forecast use of reserves | 28508 | 29015 | 507 |

Appendix 2

Transport Services

Revenue Budget 2010/11 Monitoring – September 2010 (Cycle 2)

Transport Account	              Workshop Account                  Combined Account

|  | Budget 2010/11 | Forecast 2010/11 | Variance 2010/11 | Budget 2010/11 | Forecast 2010/11 | Variance 2010/11 | Budget 2010/11 | Forecast 2010/11 | Variance 2010/11 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Employees | 1,867 | 1,868 | 1 | 383 | 353 | (30) | 2,250 | 2,221 | (29) |
| Premises | 201 | 193 | (8) | 0 | 1 | 1 | 201 | 194 | (7) |
| Transport | 1,785 | 1,842 | 57 | 165 | 159 | (6) | 1,950 | 2,001 | 51 |
| Supplies & Services | 102 | 61 | (41) | 14 | 17 | 3 | 116 | 78 | (38) |
| Support Services | 283 | 283 | 0 | 0 | 0 | 0 | 283 | 283 | 0 |
| Capital | 182 | 182 | 0 | 0 | 0 | 0 | 182 | 182 | 0 |
| Expenditure | 4,420 | 4,429 | 9 | 562 | 530 | (32) | 4,982 | 4,959 | (23) |
| Income | (4,495) | (4,504) | (9) | (626) | (594) | 32 | (5,121) | (5,098) | 23 |
| Surplus()/Deficit | (75) | (75) | 0 | (64) | (64) | 0 | (139) | (139) | 0 |

Appendix C

Economy and Environment Scrutiny Panel   24th November 2010

Revenue Budget Monitoring Report Cycle 2

Progress report on Transformation Budget Savings agreed at Budget Council 2010

| Savings option (as described in the formal Council Budget document) | Required Budget Saving for 2011/12 £000 | Required Budget Saving from 2012/13 onwards £000 | Name of Project Lead | Current Position | Target date for final report to DMT |
| --- | --- | --- | --- | --- | --- |
| Projects, Land & Property, Design and Maintenance |  | 500 | Ian Gray | The FM review work is concluding the feasibility work with a concluding report and action plan being produced on the 9th November 2010. | March 2012 |
| Administration Review | 100 | 100 | Geoff Willerton | First phase high level outcomes reported to DMT, with indicative savings. Issues of principle to be resolved. Second phase, relating to specific posts, to be completed by mid-November. | 17th November 2010 |
| Markets Services | 100 | 100 | David Moore | Savings identified so far are at 70% of target. Work is also ongoing to clarify budget targets. Next phase is to consult with Members and then begin work to bring savings identified to fruition. Further work is also needed to identify a further £30k of savings. | December 2010 |
| Housing & Environment |  | 200 | Mark Thompson | Savings contributions have been identified through an innovative re-tendering of the Council’s waste disposal contracts. A saving of £165 k per annum is estimated if recycling rates are sustained. A broader review is underway with respect to other services with a number of savings options being prepared. A potential saving on child play support workers for temporary accommodation has been identified. | February 2011 |
| Highways Design and Maintenance |  | 200 | D Tee | A report was presented to Cabinet Procurement Working Party on 7 October 2010 detailing the current position with the Highways Term Maintenance Contract. A report from consultants is expected shortly on the opportunities for improving the contract and collaborative working. Draft timetable for contract re-let has been prepared. The review of depot and office accommodation for Highways and Engineering is making good progress. Estimates of likely savings from the above indicate that the £200K could be achieved however figures will require revisiting when the way forward is determined. | March 2011 |
| Total | 200 | 1100 |  |  |  |